## Data
All Sprint Details
Sprint Name | Check Now 26.17 | Manual
Date From | 2026-01-25 | Manual
Date To | 2026-02-05 | Manual
Product | Check Now | Manual
Escaped Bugs | 0 | Manual
MidSprint_Addition | 2 | All Team data with tag MidSprint_Addition
Ad-hoc | 10 | All Team data with Ad-hoc
Planned SP | 57 | Manual
Actual SP | 102 | Manual
Estimated Development Effort | 569 | Sum all work item type "Original Estimate" in the activity development, frontend, and design from All Sprint data
Total Actual Development Effort | 776.46 | Sum all work item type "Completed Work "in the activity development, frontend, and design from All Sprint data
Estimated Testing Effort | 97 | Sum all work item type"Original Estimate" in the activity Testing from All Sprint data
Total Actual Testing Effort | 99.5 | Sum all work item type "Original Estimate" in the activity Testing from All Sprint data
Bug Fixing Actual Effort | 2 | Sum all work item type "Completed Work " with tag "Bug Fixing Actual Effort"
Sum of Actual Hours | 875.96 | Sum all work item typeCompleted Work " in the activity all
Sum of Working Hours | 680 | Sum Remaining Capacity from Team Capacity
All Sprint Data | [17 empty] | Team Capacity
EPIC | Parent | Work Item Type | Title | Story Points | State | Assigned To | Original Estimate | Completed Work | Remaining Work | Priority | Severity | Phase | Dev delivery date | QC Delivery date | Tags | Task Category | Activity | Team member | Team | Total Expected Working Hours per Sprint | Total official vacation | Total personal Days Off | Remaining Capacity | Team | Now
| 260177 | Task | Breadcrumb inputs/outputs |  | Done | Enas Diab <ediab@youxel.com> | 3 | 6 | 0 | 2 | [5 empty] | Development | Front End | Ahmed Talaat <atalaat@youxel.com> | Development | 70 | 0 | 1 | 63 | Design | 203
| 260177 | Task | BreadCrumb-menu |  | Done | Enas Diab <ediab@youxel.com> | 5 | 4 | 1 | 2 | [5 empty] | Development | Front End | Alaa Ezzat <aezzat@youxel.com> | Frontend | 70 | 0 | 1 | 63 | Development | 189
| 251892 | Task | Create Lottie Component Structure & inputs |  | Done | Hussein Abdallah <habdallah@youxel.com> | 2 | 2 | 0 | 2 |  |  |  |  | MidSprint_Addition | Development | Front End | Enas Diab <ediab@youxel.com> | Frontend | 40 | 0 | 1 | 36 | Front End | 218
| 251892 | Task | UI: Lottie Color |  | Done | Shimaa Mohamed Elsayed <shhadad@youxel.com> | 4 | 13.67 | 0 | 2 | [5 empty] | Design | Design | Galal Torkey <gtorkey@youxel.com> | Testing | 70 | 0 | 0 | 70 | Testing | 70
| 233816 | Task | UI:: Toggle Button |  | Done | Shimaa Mohamed Elsayed <shhadad@youxel.com> | 4 | 2.5 | 0 | 2 | [5 empty] | Design | Design | Hussein Abdallah <habdallah@youxel.com> | Frontend | 70 | 0 | 0 | 70 | IOS Dev | 0
| 233934 | Task | FE :: Edit in galleria component in UI kit |  | Done | Hussein Abdallah <habdallah@youxel.com> | 3 | 3 | 0 | 2 | [5 empty] | Development | Front End | Mahmoud Adel Ali <madeel@youxel.com> | Development | 70 | 0 | 2 | 56 | Andriod Dev | 0
| 255495 | Task | FE:: Add action menu column to table |  | Done | Hussein Abdallah <habdallah@youxel.com> | 4 | 4 | 0 | 2 | [5 empty] | Development | Front End | Mahmoud Ibrahim Elfeqy <mfeqy@youxel.com> | Development | 70 | 0 | 0 | 70 | Total | 680
| 255495 | Task | Design :: Unify status and tag components |  | Active | Mariam Mohamed Saeed <msaeed@youxel.com> | 5 | 4.4 | 0.6 | 2 | [5 empty] | Design | Design | Mariam Mohamed Saeed <msaeed@youxel.com> | Design | 70 | 0 | 0 | 70
| 250832 | Task | UI:: Contextual Button Component |  | Ready For Review | Shimaa Mohamed Elsayed <shhadad@youxel.com> | 5 | 5 | 0 | 2 | [5 empty] | Design | Design | Mohamed Mustafa Farrag <mfarrag@youxel.com> | Frontend | 70 | 0 | 3 | 49
| 250832 | Task | Design system: date and time documentation |  | Done | Mariam Mohamed Saeed <msaeed@youxel.com> | 3 | 7.67 | 0 | 2 | [5 empty] | Design | Design | Salma Sameh <ssameh@youxel.com> | Design | 70 | 0 | 0 | 70
| 250832 | Task | design systems: create date and time component |  | Done | Mariam Mohamed Saeed <msaeed@youxel.com> | 5 | 16.34 | 0 | 2 | [5 empty] | Design | Design | Shimaa Mohamed Elsayed <shhadad@youxel.com> | Design | 70 | 0 | 1 | 63
| 250832 | Task | UI:: DropDown/Checkboxes/Radio:: Add other option & Input |  | Done | Mariam Mohamed Saeed <msaeed@youxel.com> | 3 | 3.5 | 0 | 2 | [5 empty] | Design | Design | Total |  |  |  |  | 680
| 250832 | Task | Design system: typography |  | Done | Mariam Mohamed Saeed <msaeed@youxel.com> | 2 | 14.5 | 0 | 2 | [5 empty] | Design | Design
| 250832 | Task | UI:: Text Area:: Rich text editor |  | Done | Mariam Mohamed Saeed <msaeed@youxel.com> | 3 | 3.92 | 0 | 2 | [5 empty] | Design | Design
| 250832 | Task | Design system: Side Menu Documentation and add new variants |  | Done | Mariam Mohamed Saeed <msaeed@youxel.com> | 6 | 7.07 | 0 | 2 | [5 empty] | Design | Design
| 250832 | Task | UI:: Tree Select:: Documentation |  | Done | Mariam Mohamed Saeed <msaeed@youxel.com> | 4 | 6 | 0 | 2 | [5 empty] | Documentation | Design
| 250832 | Task | UI:: Tree Select:: Build Component |  | Done | Mariam Mohamed Saeed <msaeed@youxel.com> | 5 | 10.5 | 0 | 2 | [5 empty] | Design | Design
| 250832 | Task | UI:: Split button- Documentation |  | Done | Mariam Mohamed Saeed <msaeed@youxel.com> | 3 | 4.5 | 0 | 2 | [5 empty] | Documentation | Design
| 250832 | Task | UI:: Split button- Create Components |  | Ready For Review | Mariam Mohamed Saeed <msaeed@youxel.com> | 7 | 17 | 0 | 2 | [5 empty] | Design | Design
| 250832 | Task | UX:: Documentation Tabs / Tab Category |  | Done | Mariam Mohamed Saeed <msaeed@youxel.com> | 4 | 2 | 2 | 2 | [5 empty] | Documentation | Design
| 250832 | Task | UI:: Tabs Variants>> Survey |  | Done | Mariam Mohamed Saeed <msaeed@youxel.com> | 3 | 1.5 | 1.5 | 2 | [5 empty] | Design | Design
| 250832 | Task | Design system: pagination documentation |  | Ready For Review | Mariam Mohamed Saeed <msaeed@youxel.com> | 2 | 1.85 | 0.15 | 2 | [5 empty] | Design | Design
| 250832 | Task | Design system: spaces |  | New | Mariam Mohamed Saeed <msaeed@youxel.com> | 1 | 0 | 1 | 2 | [5 empty] | Design | Design
| 250832 | Task | Design system: recall text colors from semantics |  | New | Mariam Mohamed Saeed <msaeed@youxel.com> | 1 | 0 | 1 | 2 | [5 empty] | Design | Design
| 250832 | Task | UI:: Focus status For Inputs |  | New | Mariam Mohamed Saeed <msaeed@youxel.com> | 2 | 0 | 2 | 2 | [5 empty] | Design | Design
| 250832 | Task | UI: Progress icon shape |  | Done | Mariam Mohamed Saeed <msaeed@youxel.com> | 5 | 4 | 1 | 2 | [5 empty] | Design | Design
| 250832 | Task | UI:: File Upload/Multi Upload- Documentation |  | Ready For Review | Shimaa Mohamed Elsayed <shhadad@youxel.com> | 4 | 4 | 0 | 2 | [5 empty] | Documentation | Design
| 250832 | Task | UI:: File Upload/Multi Upload- View all component Variations |  | Ready For Review | Shimaa Mohamed Elsayed <shhadad@youxel.com> | 5 | 4 | 1 | 2 | [5 empty] | Design | Design
| 250832 | Task | UX:: Contextual Buttons Documentation |  | Ready For Review | Shimaa Mohamed Elsayed <shhadad@youxel.com> | 7 | 10.58 | 0 | 2 | [5 empty] | Documentation | Design
| 250832 | Task | UI:: File Upload Progress- Documentation |  | Ready For Review | Shimaa Mohamed Elsayed <shhadad@youxel.com> | 2 | 2 | 0 | 2 | [5 empty] | Documentation | Design
| 250832 | Task | UI:: File Upload Progress- View All Variations |  | Ready For Review | Shimaa Mohamed Elsayed <shhadad@youxel.com> | 3 | 5 | 0 | 2 | [5 empty] | Design | Design
| 250832 | Task | UI:: File Upload/ Single- Documentation |  | Ready For Review | Shimaa Mohamed Elsayed <shhadad@youxel.com> | 2 | 3.27 | 0 | 2 | [5 empty] | Design | Design
| 250832 | Task | UX:: Documentation:: Difference between Contextual Button / Link |  | Ready For Review | Shimaa Mohamed Elsayed <shhadad@youxel.com> | 3 | 4.25 | 0 | 2 | [5 empty] | Documentation | Design
| 242628 | Bug | Typing indicator appears immediately upon opening a conversation without typing |  | Closed | Galal Torkey <gtorkey@youxel.com> | 0 | 0.5 | 0 | 3 | 2 - High | [5 empty] | Front End
| 242628 | Bug | Typing indicator is triggered when focusing and unfocusing the input field without typing |  | Closed | Galal Torkey <gtorkey@youxel.com> | 0 | 0 | 0 | 3 | 2 - High | [5 empty] | Front End
| 242628 | Bug | Typing indicator is displayed to the receiver after the sender successfully sends image attachments, even though no text input or typing action occurs. |  | Closed | Galal Torkey <gtorkey@youxel.com> | 0 | 0 | 0 | 3 | 2 - High | [5 empty] | Front End
| 242628 | Bug | New Messages Indicator does not appear when a new message is received in Full Screen Chat |  | Closed | Galal Torkey <gtorkey@youxel.com> | 0 | 0 | 0 | 3 | 4 - Low | [5 empty] | Front End
| 242628 | Task | FE:: Seen Message Logic |  | Done | Enas Diab <ediab@youxel.com> | 4 | 4 | 0 | 2 |  |  |  |  | Next Sprint | Development | Front End
| 242628 | Task | FE:: Scroll to bottom and "New Messages" Button Cycle |  | Done | Alaa Ezzat <aezzat@youxel.com> | 4 | 4 | 0 | 2 |  |  |  |  | Ad-hoc | Development | Front End
| 242628 | Task | QC:: Automate Test Cases |  | Done | Galal Torkey <gtorkey@youxel.com> | 14 | 15 | 0 | 2 | [5 empty] | Test Automation | Testing
| 247747 | Task | UI:: Message Types Enhancement |  | Done | Shimaa Mohamed Elsayed <shhadad@youxel.com> | 2 | 1.5 | 0 | 2 |  |  |  |  | Ad-hoc | Design | Design
| 247747 | Bug | Conversation list does not show latest conversations after login until page refresh |  | New | Mohamed Mustafa Farrag <mfarrag@youxel.com> | 0 | 0 | 0.5 | 2 | 2 - High | [5 empty] | Front End
| 247748 | Task | QC:: Automate Test Cases |  | Done | Galal Torkey <gtorkey@youxel.com> | 14 | 15 | 0 | 2 | [5 empty] | Test Automation | Testing
| 247748 | Bug | Search does not return user when typing the full exact name while creating a new conversation |  | Resolved | Galal Torkey <gtorkey@youxel.com> | 0 | 2 | 0 | 2 | 2 - High | [5 empty] | Development
| 244767 | Task | FE:: Jump to Message integration |  | Done | Alaa Ezzat <aezzat@youxel.com> | 4 | 4 | 0 | 2 | [5 empty] | Development | Front End
| 244767 | Task | FE:: Fetch Messages while Scrolling Up/Down |  | Done | Alaa Ezzat <aezzat@youxel.com> | 5 | 5 | 0 | 2 | [5 empty] | Development | Front End
| 244767 | Task | FE:: Handle Socket Updates in Anchor Mode |  | Done | Alaa Ezzat <aezzat@youxel.com> | 2 | 3 | 0 | 2 | [5 empty] | Development | Front End
| 244767 | Task | FE:: Start Point for anchor Mode |  | Done | Alaa Ezzat <aezzat@youxel.com> | 3 | 3 | 0 | 2 | [5 empty] | Development | Front End
| 244767 | Task | FE:: Verify common properties (notes) with anchor mode |  | Ready For Review | Alaa Ezzat <aezzat@youxel.com> | 4 | 3 | 1 | 2 | [5 empty] | Development | Front End
| 244767 | Task | FE:: Exit Anchor Mode When Sending Message to see pending messages |  | Done | Alaa Ezzat <aezzat@youxel.com> | 2 | 5 | 0 | 2 | [5 empty] | Development | Front End
| 244767 | Task | FE:: Update Has More Flags |  | Done | Alaa Ezzat <aezzat@youxel.com> | 4 | 4 | 0 | 2 |  |  |  |  | Ad-hoc | Development | Front End
| 244767 | Task | FE:: Anchor Mode Investigation |  | Done | Alaa Ezzat <aezzat@youxel.com> | 0 | 20.5 | 0 | 2 | [5 empty] | Development | Front End
| 244764 | Bug | Undo option disappears after switching to another conversation |  | On Hold | Alaa Ezzat <aezzat@youxel.com> | 0 | 0 | 0 | 3 | 2 - High | [5 empty] | Front End
| 244764 | Task | FE:: Add Undo Text button type |  | Done | Alaa Ezzat <aezzat@youxel.com> | 0.5 | 0.5 | 0 | 2 | [5 empty] | Development | Front End
| 244770 | Bug | Unread marker is displayed above a deleted message when marking the following message as unread |  | Closed | Galal Torkey <gtorkey@youxel.com> | 0 | 2 | 0 | 3 | 2 - High | [5 empty] | Development
| 244770 | Task | Fix::. Unread marker is displayed above a deleted message when marking the following message as unread |  | Done | Mahmoud Ibrahim Elfeqy <mfeqy@youxel.com> | 2 | 2 | 0 | 2 |  |  |  |  | Bug Fixing Actual Effort | Development | Development
| 242629 | Task | UX:: Limitations for Files Uploaded/ Voice Messages |  | Ready For Review | Shimaa Mohamed Elsayed <shhadad@youxel.com> | 2 | 2 | 0 | 2 | [5 empty] | Design | Design
| 242629 | Task | UI: Error: on image |  | Ready For Review | Shimaa Mohamed Elsayed <shhadad@youxel.com> | 2 | 2 | 0 | 2 | [5 empty] | Design | Design
| 242629 | Task | UI UX :: handle error case when open image first time |  | Ready For Review | Shimaa Mohamed Elsayed <shhadad@youxel.com> | 2 | 0.25 | 1.75 | 2 | [5 empty] | Design | Design
| 242629 | Task | UI/UX:: Show Case Multiple Files in Message Bubble |  | Done | Shimaa Mohamed Elsayed <shhadad@youxel.com> | 2 | 1 | 0 | 2 | [5 empty] | Design | Design
| 244768 | Task | UI/UX: Create popup for Access Denied when try to go to message |  | Done | Shimaa Mohamed Elsayed <shhadad@youxel.com> | 2 | 1 | 0 | 2 | [5 empty] | Design | Design
| 244768 | Task | FE:: Create Forward Popup UI |  | Ready For Review | Alaa Ezzat <aezzat@youxel.com> | 7 | 6 | 1 | 2 | [5 empty] | Development | Front End
| 244768 | Task | FE:: Forward Message Integration |  | In Development | Alaa Ezzat <aezzat@youxel.com> | 4 | 5 | 1 | 2 | [5 empty] | Development | Front End
| 244768 | Task | FE:: Use Forward-message-box in input-message and message-box |  | In Development | Alaa Ezzat <aezzat@youxel.com> | 3 | 0 | 3 | 2 | [5 empty] | Development | Front End
| 244768 | Task | FE:: Update Input-message with Forward Mode |  | Ready For Review | Alaa Ezzat <aezzat@youxel.com> | 2 | 1 | 1 | 2 | [5 empty] | Development | Front End
| 244768 | Task | FE:: Jump to Forwarded Message |  | In Development | Alaa Ezzat <aezzat@youxel.com> | 3 | 2 | 1 | 2 | [5 empty] | Development | Front End
| 244768 | Task | FE:: Create popup for Access Denied when try to go to message |  | In Development | Alaa Ezzat <aezzat@youxel.com> | 4 | 3 | 1 | 2 | [5 empty] | Development | Front End
| 244768 | Task | FE :: Use content display component in replay and forward component |  | Done | Alaa Ezzat <aezzat@youxel.com> | 2 | 2 | 0 | 2 | [5 empty] | Development | Front End
| 244768 | Task | FE:: Create Reusable Component select-users |  | Done | Alaa Ezzat <aezzat@youxel.com> | 3 | 3 | 0 | 2 |  |  |  |  | Ad-hoc | Development | Front End
| 244772 | Task | FE:: Go To selected Message |  | Done | Mohamed Mustafa Farrag <mfarrag@youxel.com> | 2 | 2 | 0 | 2 | [5 empty] | Development | Front End
| 244772 | Task | FE:: Update Message Box UI for the selected searched Message |  | Done | Mohamed Mustafa Farrag <mfarrag@youxel.com> | 2 | 2 | 0 | 2 | [5 empty] | Development | Front End
| 244756 | Task | FE :: Add edit group name popups |  | Done | Mohamed Mustafa Farrag <mfarrag@youxel.com> | 4 | 4 | 0 | 2 | [5 empty] | Development | Front End
| 244756 | Task | FE :: Integrate with api to change group name |  | Done | Mohamed Mustafa Farrag <mfarrag@youxel.com> | 4 | 4 | 0 | 2 | [5 empty] | Development | Front End
| 244756 | Task | FE:: Update Caching after changing group name |  | Done | Mohamed Mustafa Farrag <mfarrag@youxel.com> | 4 | 4 | 0 | 2 | [5 empty] | Development | Front End
| 244761 | Task | FE:: Voice Recorder Component Logic |  | Done | Mohamed Mustafa Farrag <mfarrag@youxel.com> | 7 | 7 | 0 | 2 |  |  |  |  | Communication Module (Messages) | Development | Front End
| 244761 | Task | FE:: Get voice from storage and show it in message box |  | Ready For Review | Mohamed Mustafa Farrag <mfarrag@youxel.com> | 6 | 0 | 6 | 2 |  |  |  |  | Communication Module (Messages) | Development | Front End
| 244761 | Task | FE :: Indicate users when someone is recording |  | Done | Mohamed Mustafa Farrag <mfarrag@youxel.com> | 3 | 3 | 0 | 2 | [5 empty] | Development | Front End
| 244761 | Task | BE :: Update Messages to Support Sending Voice Records |  | Done | Mahmoud Ibrahim Elfeqy <mfeqy@youxel.com> | 8 | 8 | 0 | 2 |  |  |  |  | Communication Module (Messages) | Development | Development
| 244761 | Task | BE :: Searching for the possibility of implementation FFmpeg |  | Done | Mahmoud Ibrahim Elfeqy <mfeqy@youxel.com> | 6 | 6 | 0 | 2 | [5 empty] | Development | Development
| 244761 | Task | BE :: Add Essential Ffmpeg binaries |  | Done | Mahmoud Ibrahim Elfeqy <mfeqy@youxel.com> | 10 | 10 | 0 | 2 |  |  |  |  | Ad-hoc | Development | Development
| 244757 | Task | FE:: Change Group image Integration |  | Ready For Review | Mohamed Mustafa Farrag <mfarrag@youxel.com> | 5 | 5 | 0 | 2 | [5 empty] | Development | Front End
| 244757 | Task | FE:: Update Cashing after change group image |  | New | Mohamed Mustafa Farrag <mfarrag@youxel.com> | 2 | 0 | 2 | 2 | [5 empty] | Development | Front End
| 244758 | Task | FE:: Remove Group Image integration |  | New | Mohamed Mustafa Farrag <mfarrag@youxel.com> | 4 | 0 | 4 | 2 | [5 empty] | Development | Front End
| 244758 | Task | FE:: Update Caching after remove group image |  | New | Mohamed Mustafa Farrag <mfarrag@youxel.com> | 2 | 0 | 2 | 2 | [5 empty] | Development | Front End
| 244758 | Task | FE:: Remove Popup UI |  | New | Mohamed Mustafa Farrag <mfarrag@youxel.com> | 4 | 0 | 4 | 2 | [5 empty] | Development | Front End
| 263534 | Task | Analyze Requirements & Videos |  | Done | Galal Torkey <gtorkey@youxel.com> | 7 | 10 | 0 | 2 | [5 empty] | Gather Requirements | Business
| 263534 | Task | Reviewing CheckNow System (new) |  | Done | Galal Torkey <gtorkey@youxel.com> | 7 | 7 | 0 | 2 | [5 empty] | Review | Business
| 263534 | Task | QC:: Analyze Requirements & Identify Business Gaps |  | Done | Galal Torkey <gtorkey@youxel.com> | 7 | 7 | 0 | 2 | [5 empty] | Documentation | Testing
| 263834 | Task | FE:: add organization identifier input field with custom validations |  | Done | Hussein Abdallah <habdallah@youxel.com> | 3 | 6.5 | 0 | 2 | [5 empty] | Development | Front End
| 263834 | Task | FE:: add identfier to url domain |  | Done | Hussein Abdallah <habdallah@youxel.com> | 3 | 3 | 0 | 2 | [5 empty] | Development | Front End
| 263834 | Task | FE:: updated changed apis |  | Done | Hussein Abdallah <habdallah@youxel.com> | 3 | 7 | 0 | 2 | [5 empty] | Development | Front End
| 263834 | Task | BE :: Add System Commponents to Host |  | Done | Mahmoud Adel Ali <madeel@youxel.com> | 2 | 2 | 0 | 2 | [5 empty] | Development | Development
| 264506 | Task | Add Flat Relations Table and Trigger |  | Done | Mahmoud Adel Ali <madeel@youxel.com> | 4 | 4 | 0 | 2 | [5 empty] | Development | Development
| 264506 | Task | Search Tree Table |  | Done | Mahmoud Adel Ali <madeel@youxel.com> | 7 | 7 | 0 | 2 | [5 empty] | Development | Development
| 247302 | Task | UI:: Organization Identifier |  | Done | Shimaa Mohamed Elsayed <shhadad@youxel.com> | 3 | 4 | 0 | 2 | [5 empty] | Design | Design
| 247302 | Task | QC:: Design Test Cases |  | Done | Galal Torkey <gtorkey@youxel.com> | 2 | 2 | 0 | 2 | [5 empty] | Write Test Cases | Testing
| 253676 | Task | Setup Finbuckle + Tenant Domain Models – Package integration, Organization entity, UserOrganization entity, EF configs & migration |  | Done | Mahmoud Adel Ali <madeel@youxel.com> | 8 | 8 | 0 | 2 | [5 empty] | Development | Development
| 253676 | Task | Tenant Resolution Strategies – Header-based, subdomain, path resolvers + ICurrentTenant accessor |  | Done | Mahmoud Adel Ali <madeel@youxel.com> | 8 | 8 | 0 | 2 | [5 empty] | Development | Development
| 253676 | Task | Tenant-Aware Seed Data – Seeder infrastructure, refactor existing seeds, org onboarding defaults |  | Done | Mahmoud Adel Ali <madeel@youxel.com> | 8 | 8 | 0 | 2 | [5 empty] | Development | Development
| 253676 | Task | Add Tenant Entity and New Host Context |  | Done | Mahmoud Adel Ali <madeel@youxel.com> | 8 | 6 | 0 | 2 |  |  |  |  | Ad-hoc | Development | Development
| 247303 | Task | QC:: Design Test Cases |  | Done | Galal Torkey <gtorkey@youxel.com> | 1 | 1 | 0 | 2 | [5 empty] | Write Test Cases | Testing
| 247304 | Task | QC:: Design Test Cases |  | Done | Galal Torkey <gtorkey@youxel.com> | 2 | 1 | 1 | 2 | [5 empty] | Write Test Cases | Testing
| 247305 | Task | QC:: Design Test Cases |  | Done | Galal Torkey <gtorkey@youxel.com> | 2 | 2 | 0 | 2 | [5 empty] | Write Test Cases | Testing
| 247306 | Task | QC:: Design Test Cases |  | Done | Galal Torkey <gtorkey@youxel.com> | 2 | 1 | 1 | 2 | [5 empty] | Write Test Cases | Testing
| 247322 | Task | QC:: Design Test Cases |  | Done | Galal Torkey <gtorkey@youxel.com> | 2 | 2 | 0 | 2 | [5 empty] | Write Test Cases | Testing
| 247321 | Task | QC:: Design Test Cases |  | Done | Galal Torkey <gtorkey@youxel.com> | 3 | 2 | 1 | 2 | [5 empty] | Write Test Cases | Testing
| 247324 | Task | QC:: Design Test Cases |  | Done | Galal Torkey <gtorkey@youxel.com> | 2 | 2 | 0 | 2 | [5 empty] | Write Test Cases | Testing
| 247323 | Task | QC:: Design Test Cases |  | Done | Galal Torkey <gtorkey@youxel.com> | 3 | 2 | 1 | 2 | [5 empty] | Write Test Cases | Testing
| 247308 | Task | QC:: Design Test Cases |  | Done | Galal Torkey <gtorkey@youxel.com> | 1 | 1 | 0 | 2 | [5 empty] | Write Test Cases | Testing
| 247315 | Task | UI: Loading, error handle, Saving Location Types |  | Ready For Review | Shimaa Mohamed Elsayed <shhadad@youxel.com> | 2 | 1 | 1 | 2 | [5 empty] | Design | Design
| 247313 | Task | QC:: Design Test Cases |  | Done | Galal Torkey <gtorkey@youxel.com> | 2 | 2 | 0 | 2 | [5 empty] | Write Test Cases | Testing
| 247314 | Task | QC:: Design Test Cases |  | Done | Galal Torkey <gtorkey@youxel.com> | 2 | 2 | 0 | 2 | [5 empty] | Write Test Cases | Testing
| 247316 | Task | QC:: Design Test Cases |  | Done | Galal Torkey <gtorkey@youxel.com> | 2 | 2 | 0 | 2 | [5 empty] | Write Test Cases | Testing
| 247312 | Task | UI: Revisit The UX of the Delete Dialog |  | Done | Shimaa Mohamed Elsayed <shhadad@youxel.com> | 1 | 0.52 | 0 | 2 | [5 empty] | Design | Design
| 247312 | Task | QC:: Design Test Cases |  | Done | Galal Torkey <gtorkey@youxel.com> | 2 | 2 | 0 | 2 | [5 empty] | Write Test Cases | Testing
| 247310 | Task | UI: Check this action to reflect it in location listing |  | Done | Shimaa Mohamed Elsayed <shhadad@youxel.com> | 3 | 4 | 0 | 2 | [5 empty] | Design | Design
| 247310 | Task | BE :: Activate-Deactivate Locations |  | Done | Mahmoud Adel Ali <madeel@youxel.com> | 4 | 4 | 0 | 2 | [5 empty] | Development | Development
| 247310 | Task | UI:: Update All tables: Active & Inactive Status |  | Done | Shimaa Mohamed Elsayed <shhadad@youxel.com> | 1.5 | 1.5 | 0 | 2 |  |  |  |  | Ad-hoc | Design | Design
| 247319 | Task | QC:: Design Test Cases |  | Done | Galal Torkey <gtorkey@youxel.com> | 1 | 1 | 0 | 2 | [5 empty] | Write Test Cases | Testing
| 247311 | Task | QC:: Design Test Cases |  | Done | Galal Torkey <gtorkey@youxel.com> | 2 | 2 | 0 | 2 | [5 empty] | Write Test Cases | Testing
| 252836 | Task | Design:: update kpi indicator table |  | Done | Shimaa Mohamed Elsayed <shhadad@youxel.com> | 3 | 3 | 0 | 2 |  |  |  |  | Ad-hoc | Design | Design
| 252836 | Task | BE:: fix kpi indicators list translation |  | Done | Mahmoud Adel Ali <madeel@youxel.com> | 4 | 4 | 0 | 2 | [5 empty] | Development | Development
| 252836 | Task | BE:: fix kpi indicator delete api |  | Done | Mahmoud Adel Ali <madeel@youxel.com> | 4 | 4 | 0 | 2 | [5 empty] | Development | Development
| 252836 | Task | BE :: Implement Activate and Deactivate Features |  | Done | Mahmoud Adel Ali <madeel@youxel.com> | 4 | 2 | 0 | 2 | [5 empty] | Development | Development
| 264492 | Task | FE:: Create routes and components - service -interfaces |  | Done | Hussein Abdallah <habdallah@youxel.com> | 4 | 4 | 0 | 2 | [5 empty] | Development | Front End
| 264492 | Task | FE:: create KPI criteria form Ui |  | Done | Hussein Abdallah <habdallah@youxel.com> | 5 | 5 | 0 | 2 | [5 empty] | Development | Front End
| 264492 | Task | FE:: KPI criteria integration |  | Done | Hussein Abdallah <habdallah@youxel.com> | 5 | 5 | 0 | 2 | [5 empty] | Development | Front End
| 264492 | Task | FE:: Weight form ui |  | Ready For Review | Hussein Abdallah <habdallah@youxel.com> | 4 | 4 | 0 | 2 | [5 empty] | Development | Front End
| 264492 | Task | FE:: Weight form integration |  | Ready For Review | Hussein Abdallah <habdallah@youxel.com> | 4 | 3.5 | 0.5 | 2 | [5 empty] | Development | Front End
| 264492 | Task | Design :: add responsive design |  | Done | Shimaa Mohamed Elsayed <shhadad@youxel.com> | 2 | 1 | 0 | 2 |  |  |  |  | MidSprint_Addition | Design | Design
| 264494 | Task | FE:: create kpi definision view page ui |  | Done | Hussein Abdallah <habdallah@youxel.com> | 4 | 4 | 0 | 2 | [5 empty] | Development | Front End
| 264494 | Task | FE:: kpi definistion view integration |  | Done | Hussein Abdallah <habdallah@youxel.com> | 4 | 4 | 0 | 2 | [5 empty] | Development | Front End
| 252825 | Task | UX/Ideate: SCENARIO 3: Creae user task |  | Done | Salma Sameh <ssameh@youxel.com> | 7 | 10.65 | 0 | 2 | [5 empty] | Design | Design
| 252825 | Task | UX/Ideate: SCENARIO 6: Working With Variables & Data |  | Done | Salma Sameh <ssameh@youxel.com> | 7 | 10 | 0 | 2 | [5 empty] | Design | Design
| 252825 | Task | UX/Ideate: SCENARIO 5: Creating routers (gateways) |  | Done | Salma Sameh <ssameh@youxel.com> | 7 | 8 | 0 | 2 | [5 empty] | Design | Design
| 252825 | Task | UX/Ideate: SCENARIO 4: Creating events |  | Done | Salma Sameh <ssameh@youxel.com> | 7 | 7 | 0 | 2 | [5 empty] | Design | Design
| 252825 | Task | UX/Wireframes: Node space |  | Done | Salma Sameh <ssameh@youxel.com> | 6 | 10 | 0 | 2 | [5 empty] | Design | Design
| 252825 | Task | UX/Ideate: SCENARIO 9: Editing & Scaling Existing Workflows |  | Done | Salma Sameh <ssameh@youxel.com> | 4 | 7.25 | 0 | 2 | [5 empty] | Design | Design
| 252825 | Task | UX/Ideate: SCENARIO 7: Testing the Workflow & Handle errors |  | Done | Salma Sameh <ssameh@youxel.com> | 7 | 7 | 0 | 2 | [5 empty] | Design | Design
| 252825 | Task | UX/Ideate: Finalize all builder wireframes |  | Done | Salma Sameh <ssameh@youxel.com> | 6 | 7 | 0 | 2 | [5 empty] | Design | Design
| 252825 | Task | UX: Plan for usability testing |  | Done | Salma Sameh <ssameh@youxel.com> | 7 | 7.5 | 0 | 2 |  |  |  |  | Recurring | Design | Design
| 252825 | Task | UX: Prep + structure UI phase |  | Done | Salma Sameh <ssameh@youxel.com> | 7 | 5.5 | 1.5 | 2 | [5 empty] | Design | Design
| 252825 | Task | UX/Define: Builder Information architecture |  | Done | Salma Sameh <ssameh@youxel.com> | 5 | 5 | 0 | 2 | [5 empty] | Design | Design
| 252825 | Task | UX/Define: Create user flows (start event & user task) |  | Done | Salma Sameh <ssameh@youxel.com> | 4 | 4 | 0 | 2 | [5 empty] | Design | Design
| 252825 | Task | UX: Create workflow user personas (hypothesis) |  | Done | Salma Sameh <ssameh@youxel.com> | 7 | 3 | 4 | 2 | [5 empty] | Design | Design
| 252825 | Task | BE :: Creat Workflows Project Template |  | Done | Mahmoud Adel Ali <madeel@youxel.com> | 5 | 5 | 0 | 2 | [5 empty] | Development | Development
| 252825 | Task | UX/Define: Document all builder wireframes results |  | Done | Salma Sameh <ssameh@youxel.com> | 4 | 4 | 0 | 2 | [5 empty] | Design | Design
| 252825 | Task | Feqy :: Study FormBuilder & Survey Implementation |  | Done | Mahmoud Ibrahim Elfeqy <mfeqy@youxel.com> | 7 | 7 | 0 | 2 |  |  |  |  | Ad-hoc | Development | Development
| 252825 | Task | BE :: Template Adjusment (Version & Multi-Tenant) |  | Done | Mahmoud Adel Ali <madeel@youxel.com> | 7 | 7 | 0 | 2 | [5 empty] | Development | Development
| 252825 | Task | BE :: Setup Vault Configuration in Base Template |  | Done | Mahmoud Adel Ali <madeel@youxel.com> | 7 | 7 | 0 | 2 | [5 empty] | Development | Development
| 252825 | Task | BE :: Create Workflow Base Entities |  | Done | Ahmed Talaat <atalaat@youxel.com> | 7 | 7 | 0 | 2 | [5 empty] | Development | Development
| 252825 | Task | BE :: Redis Function Investigation & Research |  | Done | Mahmoud Ibrahim Elfeqy <mfeqy@youxel.com> | 7 | 7 | 0 | 2 | [5 empty] | Development | Development
| 252825 | Task | BE :: Redis Function POC |  | Done | Mahmoud Ibrahim Elfeqy <mfeqy@youxel.com> | 7 | 7 | 0 | 2 | [5 empty] | Development | Development
| 252825 | Task | BE :: Configure Entities And Add Database Migrations |  | Done | Ahmed Talaat <atalaat@youxel.com> | 14 | 4 | 10 | 2 |  |  |  |  | Next Sprint | Development | Development
| 252825 | Task | BE :: Add Complete Node Types Reference Document |  | Done | Mahmoud Ibrahim Elfeqy <mfeqy@youxel.com> | 7 | 7 | 0 | 2 |  |  |  |  | Ad-hoc | Development | Development
| 252825 | Task | Edit "Complete Node Types Reference" Document on Notion |  | Done | Ahmed Talaat <atalaat@youxel.com> | 5 | 5 | 0 | 2 | [5 empty] | Development | Development
| 252825 | Task | Investigate Flowable Multi-Instance Output |  | Done | Mahmoud Adel Ali <madeel@youxel.com> | 7 | 7 | 0 | 2 | [5 empty] | Development | Development
| 252825 | Task | Investigate Camunda Multi-Instance Output |  | Done | Mahmoud Ibrahim Elfeqy <mfeqy@youxel.com> | 7 | 7 | 0 | 2 | [5 empty] | Development | Development
| 252825 | Task | Update Business Status to be on Nodes |  | Done | Mahmoud Ibrahim Elfeqy <mfeqy@youxel.com> | 3 | 3 | 0 | 2 | [5 empty] | Development | Development
| 252825 | Task | Investigate Removing Edges |  | Done | Mahmoud Adel Ali <madeel@youxel.com> | 7 | 7 | 0 | 2 | [5 empty] | Development | Development
| 252825 | Task | UI: Prepare the wireframes for the UI phase V2.2 |  | Done | Salma Sameh <ssameh@youxel.com> | 4 | 3 | 1 | 2 |  |  |  |  | Next Sprint | Design | Design
| 262102 | Task | API Requests integration with Playwright |  | New | Galal Torkey <gtorkey@youxel.com> | 5 | 5 | 0 | 2 | [5 empty] | Documentation | Testing
| 260487 | Task | CMMI Documentation Preparing |  | Done | Galal Torkey <gtorkey@youxel.com> | 2 | 0 | 2 | 2 | [5 empty] | Documentation | Testing
| 263833 | Task | Maryam: Stand ups and Meetings |  | Done | Mariam Mohamed Saeed <msaeed@youxel.com> | 0 | 7.08 | 0 | 2 | [5 empty] | Meetings | Design
| 263833 | Task | Salma: Meetings |  | Done | Salma Sameh <ssameh@youxel.com> | 0 | 11.02 | 0 | 2 | [5 empty] | Design | Design
| 263833 | Task | Talaat :: Stand-Ups, Meetings and Team Support |  | Done | Ahmed Talaat <atalaat@youxel.com> | 0 | 47 | 0 | 2 | [5 empty] | Development | Development
| 263833 | Task | Alhussien :: stand-up - meetings |  | Done | Hussein Abdallah <habdallah@youxel.com> | 0 | 22 | 0 | 2 | [5 empty] | Documentation | Front End
| 263833 | Task | Feqy :: Stand-Ups, Meetings and Team Support |  | Done | Mahmoud Ibrahim Elfeqy <mfeqy@youxel.com> | 0 | 21 | 0 | 2 | [5 empty] | Development | Development
| 263833 | Task | Galal::Meetings and Logs |  | Done | Galal Torkey <gtorkey@youxel.com> | 10 | 9 | 1 | 2 | [5 empty] | Meetings | Testing
| 263833 | Task | M Adel :: Stand-Ups, Meetings and Team Support |  | Done | Mahmoud Adel Ali <madeel@youxel.com> | 0 | 14 | 0 | 2 | [5 empty] | Development | Development
| 263833 | Task | Shaimaa:: Stand-ups, Meetings, Reviews and Team Support |  | Done | Shimaa Mohamed Elsayed <shhadad@youxel.com> | 0 | 13.67 | 0 | 2 | [5 empty] | Meetings | Design
| 263833 | Task | Alaa:: Meetings |  | Done | Alaa Ezzat <aezzat@youxel.com> | 0 | 16 | 0 | 2 | [5 empty] | Development | Front End

## Analysis
CMMI Measures
Measure | Description | Calculation | Frequency | Analysis
Completion rate | Measures the difference between the actual done story points VS. the Planned story points | Actual SP / Planned SP | Sprint | +90%
Effort estimation accuracy percentage | Total Planned Development hours / Total Actual Development Hours | Sum Total Planned hours/Total Actual Dev. Effort) | Sprint | 90% - till 120%
Project Rework Rate | Project Calculate man hours used in fixing the bugs returned from testing compared to the total actual dev. hours. | Bug Fixing Actual Effort /Total Actual Dev. Effort) *100 | Sprint | 0% – 10%
Escaped Bugs | defects that bypass one or more testing or quality assurance stages and are later post released | Number of bypass one or more testing or quality assurance stages | Sprint / release | 2% -15%
Utilization | This measure is related to the Actual effort VS. working hours | (Sum of Actual hours / Sum working hours) *100 | Sprint | (90%-100%
Effort Variance | Calculate the variance of the estimated dev. Hours compared to the total actual dev. hours. | ((Total Actual Dev. Effort - Estimated Dev. Effort)/ Estimated Dev. Effort )*100 | Sprint | 5 – 10%
Measure | Description | Formula | Value | Target Range | Status
Completion Rate | Measures the difference between the actual done story points vs. the planned story points |  |  | ≥ 90%
Effort Estimation Accuracy % (Dev) | Planned development hours vs. actual development hours |  |  | 90% – 120%
Project Rework Rate | Bug fixing effort compared to total actual development effort |  |  | 0% – 10%
Escaped Bugs | Defects found after release |  |  | 2% – 15%
Utilization | Actual effort vs. available working hours |  |  | 90% – 100%
Effort Variance (Dev) | Variance between estimated and actual development effort |  |  | 5% – 10%
Row Labels | Sum of Original Estimate | Sum of Completed Work | Sum of Remaining Work
Ahmed Talaat <atalaat@youxel.com> | 26 | 63 | 10 | from data table per name
Alaa Ezzat <aezzat@youxel.com> | 56.5 | 90 | 9
Enas Diab <ediab@youxel.com> | 12 | 14 | 1
Galal Torkey <gtorkey@youxel.com> | 97 | 99.5 | 7
Hussein Abdallah <habdallah@youxel.com> | 48 | 77 | 0.5
Mahmoud Adel Ali <madeel@youxel.com> | 94 | 104 | 0
Mahmoud Ibrahim Elfeqy <mfeqy@youxel.com> | 64 | 85 | 0
Mariam Mohamed Saeed <msaeed@youxel.com> | 64 | 111.83 | 9.25
Mohamed Mustafa Farrag <mfarrag@youxel.com> | 49 | 31 | 18.5
Salma Sameh <ssameh@youxel.com> | 89 | 109.92 | 6.5
Shimaa Mohamed Elsayed <shhadad@youxel.com> | 66.5 | 90.71 | 3.75
Grand Total | 666 | 875.96 | 65.5

## Kpi Indicators Per Staff
Kpi Indicators Per Staff
Team Member | Check Now 25.9 | Check Now 25.10 | Check Now 25.11 | Check Now 25.12 | Check Now 25.13 | Check Now 25.14 | Check Now 26.15 | Check Now 26.16 | Check Now 26.17
Ahmed Talaat <atalaat@youxel.com> | 46.09% | 105.8% | 98.84% | 107.6% | 107.2% | 65.37% | 94.96% | 102.3% | 87.12%
Alaa Ezzat <aezzat@youxel.com> | 34.91% | 99.61% | 82.33% | 97.32% | 94.16% | 84.95% | 93.15% | 70.69% | 81.7%
Enas Diab <ediab@youxel.com> | 68.26% | 63.79% | 76.1% | 91.94% | 89% | 90.06% | 89.75% | 62.87% | 89.89%
Galal Torkey <gtorkey@youxel.com> | NA | NA | NA | NA | NA | 88.98% | 97.8% | 89.61% | 100.1%
Hussein Abdallah <habdallah@youxel.com> | 54.75% | 73.97% | 71.91% | 79.76% | 74.88% | 82.03% | 96.37% | 94.37% | 93.39%
Mahmoud Adel Ali <madeel@youxel.com> | 91.15% | 58.26% | 104.4% | 106.3% | 104.3% | 102.3% | 104.7% | 98.51% | 106.6%
Mahmoud Ibrahim Elfeqy <mfeqy@youxel.com> | 57.04% | 99.15% | 94.24% | 100.2% | 112.2% | 96.28% | 95.53% | 97.77% | 97.2%
Mariam Mohamed Saeed <msaeed@youxel.com> | NA | NA | NA | NA | NA | NA | NA | 69.06% | 81.81%
Mohamed Mustafa Farrag <mfarrag@youxel.com> | 35.23% | 86.3% | 47.14% | 54.83% | 75.52% | 84.74% | 87.89% | 70.95% | 71.12%
Salma Sameh <ssameh@youxel.com> | 32.55% | 55.67% | 66.46% | 53.9% | 64.52% | 52.53% | 67.32% | 76.73% | 101%
Shimaa Mohamed Elsayed <shhadad@youxel.com> | 49.13% | 116.9% | 82.43% | 68.75% | 67.47% | 63.56% | 89.05% | 89.02% | 98.48%
Performance Rate Per Staff | [9 empty] | Utilization Per Staff
Team Member | Check Now 25.9 | Check Now 25.10 | Check Now 25.11 | Check Now 25.11 | Check Now 25.13 | Check Now 25.14 | Check Now 26.15 | Check Now 26.16 | Check Now 26.17 | Team Member | Check Now 25.9 | Check Now 25.10 | Check Now 25.11 | Check Now 25.12 | Check Now 25.13 | Check Now 25.14 | Check Now 26.15 | Check Now 26.16 | Check Now 26.17
Ahmed Talaat <atalaat@youxel.com> | 79% | 91.8% | 86.21% | 87.88% | 67.5% | 29.46% | 76.19% | 100% | 35.62% | Ahmed Talaat <atalaat@youxel.com> | 102.9% | 174.3% | 116% | 200% | 237.5% | 128.1% | 97.22% | 122.9% | 100%
Alaa Ezzat <aezzat@youxel.com> | 74.31% | 90.91% | 96.84% | 78.05% | 63.27% | 78.16% | 73.68% | 48.65% | 57.07% | Alaa Ezzat <aezzat@youxel.com> | 60.5% | 114.3% | 145% | 117.1% | 115.1% | 122.9% | 84.13% | 125% | 142.9%
Enas Diab <ediab@youxel.com> | 97.47% | 69.7% | 55.43% | 54.65% | 54.39% | 60.81% | 50% | 26.87% | 80% | Enas Diab <ediab@youxel.com> | 110.7% | 171.9% | 197.2% | 205.6% | 168.8% | 206.2% | 161.1% | 175% | 38.89%
Galal Torkey <gtorkey@youxel.com> | NA | NA | NA | NA | NA | 76.8% | 86.84% | 84.39% | 91.08% | Galal Torkey <gtorkey@youxel.com> | NA | NA | NA | NA | NA | 82.86% | 104.3% | 118.6% | 142.1%
Hussein Abdallah <habdallah@youxel.com> | 71.53% | 61.54% | 84.46% | 84.8% | 61.05% | 82.78% | 61.24% | 76.39% | 61.94% | Hussein Abdallah <habdallah@youxel.com> | 77.78% | 150% | 117.9% | 173% | 109.3% | 104.8% | 141.3% | 125.9% | 110%
Mahmoud Adel Ali <madeel@youxel.com> | 94.37% | 94.38% | 93.84% | 118.3% | 107.4% | 86.32% | 91.3% | 71.91% | 90.38% | Mahmoud Adel Ali <madeel@youxel.com> | 116.1% | 93.88% | 179.4% | 126.8% | 128.6% | 150.8% | 164.3% | 141.3% | 185.7%
Mahmoud Ibrahim Elfeqy <mfeqy@youxel.com> | 77.53% | 85.06% | 81.54% | 84.52% | 77.5% | 73.91% | 64.71% | 74.58% | 75.29% | Mahmoud Ibrahim Elfeqy <mfeqy@youxel.com> | 97.14% | 121.4% | 157.1% | 133.3% | 266.7% | 115% | 125.9% | 128.6% | 121.4%
Mariam Mohamed Saeed <msaeed@youxel.com> | NA | NA | NA | NA | NA | NA | NA | 73.12% | 52.86% | Mariam Mohamed Saeed <msaeed@youxel.com> | NA | NA | NA | NA | NA | NA | NA | 91.43% | 159.8%
Mohamed Mustafa Farrag <mfarrag@youxel.com> | 84% | 96.26% | 80% | 100% | 100% | 99.3% | 63.04% | 100% | 98.99% | Mohamed Mustafa Farrag <mfarrag@youxel.com> | 44.29% | 87.14% | 31.43% | 37.14% | 88.57% | 80% | 52.86% | 42.86% | 63.27%
Salma Sameh <ssameh@youxel.com> | 82.92% | 94.19% | 65.83% | 72.98% | 75.45% | 81.36% | 88.28% | 83.24% | 76.45% | Salma Sameh <ssameh@youxel.com> | 109.7% | 123.4% | 102.2% | 101.3% | 85.96% | 100.1% | 76.67% | 134.2% | 157%
Shimaa Mohamed Elsayed <shhadad@youxel.com> | 75.81% | 86.27% | 89.99% | 82% | 70.86% | 88.33% | 52.02% | 69.56% | 70.4% | Shimaa Mohamed Elsayed <shhadad@youxel.com> | 77.16% | 576.3% | 119.3% | 92.73% | 95.45% | 121.9% | 86.46% | 107.1% | 144%
Done Tasks Per Staff | [9 empty] | MidSprint_Addition Per Staff
Team Member | Check Now 25.9 | Check Now 25.10 | Check Now 25.11 | Check Now 25.11 | Check Now 25.13 | Check Now 25.14 | Check Now 26.15 | Check Now 26.16 | Check Now 26.17 | Team Member | Check Now 25.9 | Check Now 25.10 | Check Now 25.11 | Check Now 25.12 | Check Now 25.13 | Check Now 25.14 | Check Now 26.15 | Check Now 26.16 | Check Now 26.17
Ahmed Talaat <atalaat@youxel.com> | 28.57% | 100% | 100% | 100% | 100% | 66.67% | 100% | 100% | 100% | Ahmed Talaat <atalaat@youxel.com> | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Alaa Ezzat <aezzat@youxel.com> | 20% | 100% | 69.23% | 100% | 100% | 81.48% | 100% | 69.23% | 80% | Alaa Ezzat <aezzat@youxel.com> | 0% | 0% | 19.23% | 87.5% | 12.5% | 7.407% | 21.05% | 7.692% | 0%
Enas Diab <ediab@youxel.com> | 53.85% | 46.67% | 64.71% | 86.36% | 87.5% | 81.82% | 90.91% | 57.14% | 100% | Enas Diab <ediab@youxel.com> | 0% | 40% | 5.882% | 13.64% | 0% | 0% | 0% | 28.57% | 0%
Galal Torkey <gtorkey@youxel.com> | NA | NA | NA | NA | NA | 93.33% | 100% | 86.96% | 96.67% | Galal Torkey <gtorkey@youxel.com> | NA | NA | NA | NA | NA | 0% | 0% | 0% | 0%
Hussein Abdallah <habdallah@youxel.com> | 46.67% | 66.67% | 61.76% | 65% | 73.91% | 78.57% | 100% | 95% | 100% | Hussein Abdallah <habdallah@youxel.com> | 0% | 0% | 2.941% | 5% | 21.74% | 0% | 0% | 0% | 7.143%
Mahmoud Adel Ali <madeel@youxel.com> | 86.67% | 42.86% | 96.67% | 100% | 100% | 100% | 100% | 100% | 100% | Mahmoud Adel Ali <madeel@youxel.com> | 6.667% | 14.29% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Mahmoud Ibrahim Elfeqy <mfeqy@youxel.com> | 45.45% | 100% | 88.89% | 100% | 100% | 100% | 100% | 100% | 100% | Mahmoud Ibrahim Elfeqy <mfeqy@youxel.com> | 9.091% | 0% | 0% | 0% | 0% | 8.333% | 0% | 0% | 0%
Mariam Mohamed Saeed <msaeed@youxel.com> | NA | NA | NA | NA | NA | NA | NA | 64.71% | 78.95% | Mariam Mohamed Saeed <msaeed@youxel.com> | NA | NA | NA | NA | NA | NA | NA | 0% | 0%
Mohamed Mustafa Farrag <mfarrag@youxel.com> | 20% | 83.33% | 40% | 44.44% | 66.67% | 81.25% | 100% | 66.67% | 64.29% | Mohamed Mustafa Farrag <mfarrag@youxel.com> | 0% | 8.333% | 0% | 0% | 0% | 37.5% | 0% | 0% | 0%
Salma Sameh <ssameh@youxel.com> | 7.143% | 35% | 61.54% | 41.67% | 58.33% | 37.5% | 60% | 66.67% | 100% | Salma Sameh <ssameh@youxel.com> | 0% | 35% | 30.77% | 25% | 0% | 6.25% | 0% | 0% | 0%
Shimaa Mohamed Elsayed <shhadad@youxel.com> | 37.5% | 60% | 75% | 61.54% | 62.5% | 48.15% | 100% | 92% | 100% | Shimaa Mohamed Elsayed <shhadad@youxel.com> | 0% | 0% | 0% | 7.692% | 37.5% | 29.63% | 11.11% | 0% | 4.167%
Ad-hoc % Per Staff
[10 empty] | Team Member | Check Now 26.15 | Check Now 26.16 | Check Now 26.17
[10 empty] | Ahmed Talaat <atalaat@youxel.com> | 0% | 0% | 0%
[10 empty] | Alaa Ezzat <aezzat@youxel.com> | 21.05% | 30.77% | 15%
[10 empty] | Enas Diab <ediab@youxel.com> | 9.091% | 14.29% | 0%
[10 empty] | Galal Torkey <gtorkey@youxel.com> | 0% | 0% | 0%
[10 empty] | Hussein Abdallah <habdallah@youxel.com> | 13.04% | 0% | 0%
[10 empty] | Mahmoud Adel Ali <madeel@youxel.com> | 7.692% | 9.091% | 5.882%
[10 empty] | Mahmoud Ibrahim Elfeqy <mfeqy@youxel.com> | 0% | 22.22% | 27.27%
[10 empty] | Mariam Mohamed Saeed <msaeed@youxel.com> | NA | 0% | 0%
[10 empty] | Mohamed Mustafa Farrag <mfarrag@youxel.com> | 0% | 0% | 0%
[10 empty] | Salma Sameh <ssameh@youxel.com> | 0% | 0% | 0%
[10 empty] | Shimaa Mohamed Elsayed <shhadad@youxel.com> | 0% | 16% | 12.5%

## Kpi Indicators Per Team
Item | Check Now 25.9 | Check Now 25.10 | Check Now 25.11 | Check Now 25.12 | Check Now 25.13 | Check Now 25.14 | Check Now 26.15 | Check Now 26.16 | Check Now 26.17
Escaped Bugs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MidSprint_Addition | 2 | 23 | 14 | 18 | 10 | 25 | 8 | 11 | 2
Ad-hoc | NA | NA | NA | NA | NA | NA | 9 | 12 | 10
Actual SP | 31 | 31 | 66 | 72 | 78 | 57 | 73 | 61 | 57
Planned SP | 87 | 97 | 113 | 124 | 142 | 191 | 82 | 44 | 102
Estimated Development Effort | 721.5 | 716 | 775.5 | 578 | 436.5 | 694.5 | 476 | 639.5 | 569
Total Actual Development Effort | 562.13 | 599.79 | 667.21 | 596.76 | 547.89 | 699.58 | 619.26 | 757.18 | 776.46
Estimated Testing Effort | 0 | 0 | 0 | 0 | 0 | 48 | 66 | 73 | 97
Total Actual Testing Effort | 0 | 0 | 0 | 0 | 0 | 58 | 73 | 83 | 99.5
Bug Fixing Actual Effort | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 7 | 2
Sum of Actual Hours | 567.76 | 599.79 | 667.21 | 596.76 | 547.89 | 757.58 | 692.26 | 840.18 | 875.96
Sum of Working Hours | 680 | 455 | 517 | 506 | 444.5 | 572 | 653 | 708 | 680
Kpi Indicators Per Team
Team | Check Now 25.9 | Check Now 25.10 | Check Now 25.11 | Check Now 25.12 | Check Now 25.13 | Check Now 25.14 | Check Now 26.15 | Check Now 26.16 | Check Now 26.17
Design | 79.81% | 62.69% | 74.43% | 61.53% | 65.69% | 58.84% | 82.35% | 80.4% | 93.87%
Development | 65.55% | 85.39% | 100.3% | 103.7% | 104.9% | 93.8% | 98.77% | 99.67% | 97.38%
Front End | 70.97% | 82.83% | 68.23% | 80.21% | 85.23% | 79.4% | 82.18% | 77.45% | 81.11%
Testing | NA | NA | NA | NA | NA | 88.98% | 97.8% | 89.61% | 100.1%
Performance Rate Per Team | [9 empty] | Utilization Per Team
Team | Check Now 25.9 | Check Now 25.10 | Check Now 25.11 | Check Now 25.12 | Check Now 25.13 | Check Now 25.14 | Check Now 26.15 | Check Now 26.16 | Check Now 26.17 | Team | Check Now 25.9 | Check Now 25.10 | Check Now 25.11 | Check Now 25.12 | Check Now 25.13 | Check Now 25.14 | Check Now 26.15 | Check Now 26.16 | Check Now 26.17
Design | 82.94% | 92.08% | 76.58% | 76.87% | 73.56% | 84.96% | 71.16% | 74.35% | 66.12% | Design | 473.1% | 162.8% | 108.4% | 97.54% | 89.83% | 109.2% | 81.19% | 106.2% | 153.9%
Development | 82.94% | 90.3% | 89.3% | 96.38% | 90.06% | 66.52% | 79.06% | 82.91% | 70.23% | Development | 104.6% | 124.7% | 152.7% | 144.3% | 169.1% | 131.9% | 129.6% | 130.9% | 133.3%
Front End | 82.94% | 79.6% | 80.97% | 71.89% | 63.45% | 78.73% | 63.95% | 65.32% | 68.67% | Front End | 193.8% | 132.4% | 123% | 112% | 118.8% | 121.1% | 103.2% | 118.8% | 97.25%
Testing | NA | NA | NA | NA | NA | 76.8% | 86.84% | 84.39% | 91.08% | Testing | NA | NA | NA | NA | NA | 82.86% | 104.3% | 118.6% | 142.1%
Done Tasks Per Team | [9 empty] | MidSprint_Addition Per Team
Team | Check Now 25.9 | Check Now 25.10 | Check Now 25.11 | Check Now 25.12 | Check Now 25.13 | Check Now 25.14 | Check Now 26.15 | Check Now 26.16 | Check Now 26.17 | Team | Check Now 25.9 | Check Now 25.10 | Check Now 25.11 | Check Now 25.12 | Check Now 25.13 | Check Now 25.14 | Check Now 26.15 | Check Now 26.16 | Check Now 26.17
Design | 22.73% | 40% | 68.97% | 52% | 60% | 44.19% | 85.71% | 78.43% | 93.22% | Design | 0% | 28% | 13.79% | 16% | 15% | 20.93% | 7.143% | 0% | 1.695%
Development | 55% | 77.5% | 95.92% | 100% | 100% | 96.15% | 100% | 100% | 100% | Development | 3.846% | 5% | 0% | 0% | 0% | 3.846% | 0% | 0% | 0%
Front End | 50% | 76.67% | 56.78% | 78.05% | 86.67% | 73.64% | 84.38% | 75% | 82.35% | Front End | 0% | 23.33% | 8.475% | 17.07% | 9.333% | 11.63% | 6.25% | 10.58% | 1.961%
Testing | NA | NA | NA | NA | NA | 93.33% | 100% | 86.96% | 96.67% | Testing | NA | NA | NA | NA | NA | 0% | 0% | 0% | 0%
Ad-hoc % Per Team
[10 empty] | Team | Check Now 26.15 | Check Now 26.16 | Check Now 26.17
[10 empty] | Design | 0% | 7.843% | 5.085%
[10 empty] | Development | 3.333% | 9.677% | 12.5%
[10 empty] | Front End | 8.333% | 4.808% | 5.882%
[10 empty] | Testing | 0% | 0% | 0%

## Check Now 26.17 Full Analysis
Sprint Name: Check Now 26.17
Date: 25 JAN to 05 FEB
Row Labels | Performance Rate | Utilization Per Staff |  | Team | Performance Rate | Utilization Per Staff
Ahmed Talaat <atalaat@youxel.com> | 35.62% | 100% |  | Design | 66.12% | 153.9%
Alaa Ezzat <aezzat@youxel.com> | 57.07% | 142.9% |  | Development | 70.23% | 133.3%
Enas Diab <ediab@youxel.com> | 80% | 38.89% |  | Front End | 68.67% | 97.25%
Galal Torkey <gtorkey@youxel.com> | 91.08% | 142.1% |  | Testing | 91.08% | 142.1%
Hussein Abdallah <habdallah@youxel.com> | 61.94% | 110% |  | Grand Total | 70.74% | 128.8%
Mahmoud Adel Ali <madeel@youxel.com> | 90.38% | 185.7%
Mahmoud Ibrahim Elfeqy <mfeqy@youxel.com> | 75.29% | 121.4%
Mariam Mohamed Saeed <msaeed@youxel.com> | 52.86% | 159.8%
Mohamed Mustafa Farrag <mfarrag@youxel.com> | 98.99% | 63.27%
Salma Sameh <ssameh@youxel.com> | 76.45% | 157%
Shimaa Mohamed Elsayed <shhadad@youxel.com> | 70.4% | 144%
Grand Total | 70.74% | 128.8%
Row Labels | Grand Total | Done Tasks % |  | Row Labels | Grand Total | Done Tasks %
Ahmed Talaat <atalaat@youxel.com> | 4 | 100% |  | Design | 59 | 93.22%
Alaa Ezzat <aezzat@youxel.com> | 20 | 80% |  | Development | 32 | 100%
Enas Diab <ediab@youxel.com> | 3 | 100% |  | Front End | 51 | 82.35%
Galal Torkey <gtorkey@youxel.com> | 30 | 96.67% |  | Testing | 30 | 96.67%
Hussein Abdallah <habdallah@youxel.com> | 14 | 100% |  | Grand Total | 172 | 91.86%
Mahmoud Adel Ali <madeel@youxel.com> | 17 | 100%
Mahmoud Ibrahim Elfeqy <mfeqy@youxel.com> | 11 | 100%
Mariam Mohamed Saeed <msaeed@youxel.com> | 19 | 78.95%
Mohamed Mustafa Farrag <mfarrag@youxel.com> | 14 | 64.29%
Salma Sameh <ssameh@youxel.com> | 16 | 100%
Shimaa Mohamed Elsayed <shhadad@youxel.com> | 24 | 100%
Grand Total | 172 | 91.86%
Team member | Team | MidSprint_Addition % |  | Team | MidSprint_Addition %
Ahmed Talaat <atalaat@youxel.com> | Development | 0% |  | Design | 1.695%
Alaa Ezzat <aezzat@youxel.com> | Frontend | 0% |  | Development | 0%
Enas Diab <ediab@youxel.com> | Frontend | 0% |  | Front End | 1.961%
Galal Torkey <gtorkey@youxel.com> | Testing | 0% |  | Testing | 0%
Hussein Abdallah <habdallah@youxel.com> | Frontend | 7.143% |  | Grand Total | 1.163%
Mahmoud Adel Ali <madeel@youxel.com> | Development | 0%
Mahmoud Ibrahim Elfeqy <mfeqy@youxel.com> | Development | 0%
Mariam Mohamed Saeed <msaeed@youxel.com> | Design | 0%
Mohamed Mustafa Farrag <mfarrag@youxel.com> | Frontend | 0%
Salma Sameh <ssameh@youxel.com> | Design | 0%
Shimaa Mohamed Elsayed <shhadad@youxel.com> | Design | 4.167%
Grand Total |  | 1.163%
Team member | Team | Ad-hoc % |  | Team | Ad-hoc %
Ahmed Talaat <atalaat@youxel.com> | Development | 0% |  | Design | 5.085%
Alaa Ezzat <aezzat@youxel.com> | Frontend | 15% |  | Development | 12.5%
Enas Diab <ediab@youxel.com> | Frontend | 0% |  | Front End | 5.882%
Galal Torkey <gtorkey@youxel.com> | Testing | 0% |  | Testing | 0%
Hussein Abdallah <habdallah@youxel.com> | Frontend | 0% |  | Grand Total | 5.814%
Mahmoud Adel Ali <madeel@youxel.com> | Development | 5.882%
Mahmoud Ibrahim Elfeqy <mfeqy@youxel.com> | Development | 27.27%
Mariam Mohamed Saeed <msaeed@youxel.com> | Design | 0%
Mohamed Mustafa Farrag <mfarrag@youxel.com> | Frontend | 0%
Salma Sameh <ssameh@youxel.com> | Design | 0%
Shimaa Mohamed Elsayed <shhadad@youxel.com> | Design | 12.5%
Grand Total |  | 5.814%
Team member | Team | Actual productivity | Productivity Index
Ahmed Talaat <atalaat@youxel.com> | Development | 1 | 2.4231
Alaa Ezzat <aezzat@youxel.com> | Frontend | 1.4286 | 1.5929
Enas Diab <ediab@youxel.com> | Frontend | 0.38889 | 1.1667
Galal Torkey <gtorkey@youxel.com> | Testing | 1.4214 | 1.0258
Hussein Abdallah <habdallah@youxel.com> | Frontend | 1.1 | 1.6042
Mahmoud Adel Ali <madeel@youxel.com> | Development | 1.8571 | 1.1064
Mahmoud Ibrahim Elfeqy <mfeqy@youxel.com> | Development | 1.2143 | 1.3281
Mariam Mohamed Saeed <msaeed@youxel.com> | Design | 1.5976 | 1.7473
Mohamed Mustafa Farrag <mfarrag@youxel.com> | Frontend | 0.63265 | 0.63265
Salma Sameh <ssameh@youxel.com> | Design | 1.5703 | 1.2351
Shimaa Mohamed Elsayed <shhadad@youxel.com> | Design | 1.4398 | 1.3641
Grand Total |  | 1.2882 | 1.3153

## Kpi Indicators
Row Labels | Performance Rate | Weight | Utilization Per Staff | Weight | Done Tasks % | Weight | KPI
Ahmed Talaat <atalaat@youxel.com> | 35.62% | 20% | 100% | 10% | 100% | 70% | 87.12%
Alaa Ezzat <aezzat@youxel.com> | 57.07% | 20% | 142.9% | 10% | 80% | 70% | 81.7%
Enas Diab <ediab@youxel.com> | 80% | 20% | 38.89% | 10% | 100% | 70% | 89.89%
Galal Torkey <gtorkey@youxel.com> | 91.08% | 20% | 142.1% | 10% | 96.67% | 70% | 100.1%
Hussein Abdallah <habdallah@youxel.com> | 61.94% | 20% | 110% | 10% | 100% | 70% | 93.39%
Mahmoud Adel Ali <madeel@youxel.com> | 90.38% | 20% | 185.7% | 10% | 100% | 70% | 106.6%
Mahmoud Ibrahim Elfeqy <mfeqy@youxel.com> | 75.29% | 20% | 121.4% | 10% | 100% | 70% | 97.2%
Mariam Mohamed Saeed <msaeed@youxel.com> | 52.86% | 20% | 159.8% | 10% | 78.95% | 70% | 81.81%
Mohamed Mustafa Farrag <mfarrag@youxel.com> | 98.99% | 20% | 63.27% | 10% | 64.29% | 70% | 71.12%
Salma Sameh <ssameh@youxel.com> | 76.45% | 20% | 157% | 10% | 100% | 70% | 101%
Shimaa Mohamed Elsayed <shhadad@youxel.com> | 70.4% | 20% | 144% | 10% | 100% | 70% | 98.48%
Grand Total | 70.74% | 20% | 128.8% | 10% | 91.86% | 70% | 91.33%
Team | Performance Rate | Weight | Utilization Per Staff | Weight | Done Tasks % | Weight | KPI
Design | 66.12% | 20% | 153.9% | 10% | 93.22% | 70% | 93.87%
Development | 70.23% | 20% | 133.3% | 10% | 100% | 70% | 97.38%
Front End | 68.67% | 20% | 97.25% | 10% | 82.35% | 70% | 81.11%
Testing | 91.08% | 20% | 142.1% | 10% | 96.67% | 70% | 100.1%
Grand Total | 70.74% | 20% | 128.8% | 10% | 91.86% | 70% | 91.33%

## Capacity
CHECK NOW (Check Now 26.17)
Team member | Team | Total Expected Working Hours per Sprint | Total official vacation | Total personal Days Off | Remaining Capacity | Team | Now
Ahmed Talaat <atalaat@youxel.com> | Development | 70 | 0 | 1 | 63 | Design | 203
Alaa Ezzat <aezzat@youxel.com> | Frontend | 70 | 0 | 1 | 63 | Development | 189
Enas Diab <ediab@youxel.com> | Frontend | 40 | 0 | 1 | 36 | Front End | 218
Galal Torkey <gtorkey@youxel.com> | Testing | 70 | 0 | 0 | 70 | Testing | 70
Hussein Abdallah <habdallah@youxel.com> | Frontend | 70 | 0 | 0 | 70 | IOS Dev | 0
Mahmoud Adel Ali <madeel@youxel.com> | Development | 70 | 0 | 2 | 56 | Andriod Dev | 0
Mahmoud Ibrahim Elfeqy <mfeqy@youxel.com> | Development | 70 | 0 | 0 | 70 | Total | 680
Mariam Mohamed Saeed <msaeed@youxel.com> | Design | 70 | 0 | 0 | 70
Mohamed Mustafa Farrag <mfarrag@youxel.com> | Frontend | 70 | 0 | 3 | 49
Salma Sameh <ssameh@youxel.com> | Design | 70 | 0 | 0 | 70
Shimaa Mohamed Elsayed <shhadad@youxel.com> | Design | 70 | 0 | 1 | 63
Total |  |  |  |  | 680

## Check Now 26.17
Sprint Name: Check Now 26.17
Date: 25 JAN to 05 FEB
US
EPIC | Parent | Work Item Type | Title | Story Points | State | Assigned To | Original Estimate | Completed Work | Remaining Work | Priority | Severity | Phase | Dev delivery date | QC Delivery date | Tags | Task Category | Activity
CHECK UI Library | 260293 | User Story | Breadcrumb Component | 3 | Ready for release |  |  |  |  | 2 |  |  |  |  | CHECK UI Library
CHECK UI Library | 227974 | User Story | Lottie Component | 3 | Ready for release |  |  |  |  | 2 |  |  |  |  | CHECK UI Library
CHECK UI Library | 228363 | User Story | Input Switch Component | 5 | Ready for release |  |  |  |  | 2 |  | Development |  |  | CHECK UI Library
CHECK UI Library | 228369 | User Story | Galleria Component | 3 | Ready for release |  |  |  |  | 2 |  |  |  |  | CHECK UI Library
CHECK UI Library | 255494 | User Story | Table component | 3 | In Development |  |  |  |  | 2 |  |  |  |  | CHECK UI Library
CHECK UI Library | 227974 | User Story | Design System Adjustments | 5 | Active |  |  |  |  | 2 |  |  |  |  | CHECK UI Library
Communication Module (Messages) | 228964 | User Story | Create Chat App | 8 | In Development |  |  |  |  | 1 |  |  |  |  | Communication Module (Messages)
Communication Module (Messages) | 228960 | User Story | As a user I can send text message in a conversation | 5 | In Development |  |  |  |  | 1 |  |  |  |  | Communication Module (Messages)
Communication Module (Messages) | 228960 | User Story | As a user I can see list of my conversations | 3 | In Development |  |  |  |  | 1 |  |  |  |  | Communication Module (Messages)
Communication Module (Messages) | 228960 | User Story | As a user I can start new conversation | 3 | Ready For Testing |  |  |  |  | 1 |  |  |  |  | Communication Module (Messages)
Communication Module (Messages) | 228960 | User Story | As a user I can reply on any message | 5 | Ready For Review |  |  |  |  | 2 |  |  |  |  | Communication Module (Messages)
Communication Module (Messages) | 228960 | User Story | As a user I can delete my messages | 3 | Done Development |  |  |  |  | 1 |  |  |  |  | Communication Module (Messages)
Communication Module (Messages) | 228960 | User Story | As a user I can mark message as unread | 5 | Ready For Testing |  |  |  |  | 2 |  |  |  |  | Communication Module (Messages)
Communication Module (Messages) | 228960 | User Story | As a user I can send attachment in a conversation | 5 | In Development |  |  |  |  | 2 |  |  |  |  | Communication Module (Messages)
Communication Module (Messages) | 228960 | User Story | As a user I can forward a message | 5 | In Development |  |  |  |  | 2 |  |  |  |  | Communication Module (Messages)
Communication Module (Messages) | 228960 | User Story | As a user I can search in the conversation for certain message (Full screen) | 5 | Ready For Testing |  |  |  |  | 2 |  |  |  |  | Communication Module (Messages)
Communication Module (Messages) | 228961 | User Story | As a owner of a group I can change the group name | 3 | Ready For Testing |  |  |  |  | 3 |  |  |  |  | Communication Module (Messages)
Communication Module (Messages) | 228960 | User Story | As a user I can record an audio and send it over conversation | 5 | Ready For Review |  |  |  |  | 2 |  |  |  |  | Communication Module (Messages)
Communication Module (Messages) | 228961 | User Story | As a owner of the group I can change the group image | 3 | In Development |  |  |  |  | 3 |  |  |  |  | Communication Module (Messages)
Communication Module (Messages) | 228961 | User Story | As owner of the group I can remove the group image | 3 | New |  |  |  |  | 3 |  |  |  |  | Communication Module (Messages)
Administration Module | 241399 | User Story | QC Review (Design & BRD) | 0 | Done Development |  |  |  |  | 2 |  |  |  |  | Administration Module
Administration Module | 241399 | User Story | Administration Portal API | 5 | In Development |  |  |  |  | 2 |  |  |  |  | Administration Module
Administration Module | 241399 | User Story | Locations Flat Relations | 3 | Done Development |  |  |  |  | 2
Administration Module | 195967 | User Story | Set/Edit Company information | 3 | Ready For Testing |  |  |  |  | 1 |  |  |  |  | Administration Module
Administration Module | 195967 | User Story | Multitenancy | 8 | Done Development |  |  |  |  | 2 |  |  |  |  | Administration Module
Administration Module | 195967 | User Story | Upload/Change Company Logo | 3 | Ready For Testing |  |  |  |  | 1 |  |  |  |  | Administration Module
Administration Module | 195967 | User Story | Set Company Identity | 5 | Ready For Testing |  |  |  |  | 1 |  |  |  |  | Administration Module
Administration Module | 195967 | User Story | Set / Edit the supported langauges | 5 | Ready For Testing |  |  |  |  | 1 |  |  |  |  | Administration Module
Administration Module | 195968 | User Story | User should be able to view POI categories | 3 | Ready For Testing |  |  |  |  | 1 |  |  |  |  | Administration Module
Administration Module | 195968 | User Story | User should be able to manage location subcategory | 5 | Ready For Testing |  |  |  |  | 2 |  |  |  |  | Administration Module
Administration Module | 195968 | User Story | User should be able to manage Location categories | 5 | Ready For Testing |  |  |  |  | 2 |  |  |  |  | Administration Module
Administration Module | 195968 | User Story | User should be able to manage location importance | 5 | Ready For Testing |  |  |  |  | 2 |  |  |  |  | Administration Module
Administration Module | 195968 | User Story | User should be able to manage location account | 5 | Ready For Testing |  |  |  |  | 2 |  |  |  |  | Administration Module
Administration Module | 195968 | User Story | User should be able to view location tree (org chart) | 8 | Ready For Testing |  |  |  |  | 1 |  |  |  |  | Administration Module
Administration Module | 195968 | User Story | User should be able to add location optional information | 5 | Ready For Review |  |  |  |  | 1 |  |  |  |  | Administration Module
Administration Module | 195968 | User Story | User should be able to add loction with its mandatory information | 5 | Ready For Testing |  |  |  |  | 1 |  |  |  |  | Administration Module
Administration Module | 195968 | User Story | User should be able to add location attachments | 5 | Ready For Testing |  |  |  |  | 1 |  |  |  |  | Administration Module
Administration Module | 195968 | User Story | User should be able to edit locations | 5 | Ready For Testing |  |  |  |  | 1 |  |  |  |  | Administration Module
Administration Module | 195968 | User Story | User should be able to delete parent location | 3 | In Development |  |  |  |  | 1 |  |  |  |  | Administration Module
Administration Module | 195968 | User Story | User should be able to move sub-locations from one parent to another | 5 | In Development |  |  |  |  | 1 |  |  |  |  | Administration Module
Administration Module | 195968 | User Story | User should be able to activate/deactivate Location | 3 | Ready For Review |  |  |  |  | 1 |  |  |  |  | Administration Module
Administration Module | 195968 | User Story | User should be able to handle location translation | 5 | Ready For Testing |  |  |  |  | 1 |  |  |  |  | Administration Module
Administration Module | 195968 | User Story | User should be able to delete sub location | 3 | In Development |  |  |  |  | 1 |  |  |  |  | Administration Module
Administration Module | 195969 | User Story | Manage KPI Indicators (CRUD + Localization) | 5 | In Development |  |  |  |  | 2 |  |  |  |  | Administration Module
Administration Module | 195969 | User Story | Kpi Definistion Form | 5 | Ready For Review |  |  |  |  | 2 |  | Development |  |  | Administration Module
Administration Module | 195969 | User Story | Kpi Definisions View | 5 | Ready For Testing |  |  |  |  | 2 |  |  |  |  | Administration Module
Workflow Library | 193289 | User Story | Create Workflow System | 5 | In Development |  |  |  |  | 2 |  |  |  |  | Workflow Library
Learning, Development, and Process Improvement | 240010 | User Story | Automation Testing Cycle | 0 | Active |  |  |  |  | 2 |  | Testing
Learning, Development, and Process Improvement | 260486 | User Story | CMMI Reports | 0 | Released |  |  |  |  | 2 |  |  |  |  | CMMI
Meetings & Support | 247821 | User Story | Meeting logs iteration 26.17 | 0 | Released |  |  |  |  | 2
US + All
EPIC | Parent | Work Item Type | Title | Story Points | State | Assigned To | Original Estimate | Completed Work | Remaining Work | Priority | Severity | Phase | Dev delivery date | QC Delivery date | Tags | Task Category | Activity
CHECK UI Library | 260293 | User Story | Breadcrumb Component | 3 | Ready for release |  |  |  |  | 2 |  |  |  |  | CHECK UI Library
| 260177 | Task | Breadcrumb inputs/outputs |  | Done | Enas Diab <ediab@youxel.com> | 3 | 6 | 0 | 2 | [5 empty] | Development | Front End
| 260177 | Task | BreadCrumb-menu |  | Done | Enas Diab <ediab@youxel.com> | 5 | 4 | 1 | 2 | [5 empty] | Development | Front End
CHECK UI Library | 227974 | User Story | Lottie Component | 3 | Ready for release |  |  |  |  | 2 |  |  |  |  | CHECK UI Library
| 251892 | Task | Create Lottie Component Structure & inputs |  | Done | Hussein Abdallah <habdallah@youxel.com> | 2 | 2 | 0 | 2 |  |  |  |  | MidSprint_Addition | Development | Front End
| 251892 | Task | UI: Lottie Color |  | Done | Shimaa Mohamed Elsayed <shhadad@youxel.com> | 4 | 13.67 | 0 | 2 | [5 empty] | Design | Design
CHECK UI Library | 228363 | User Story | Input Switch Component | 5 | Ready for release |  |  |  |  | 2 |  | Development |  |  | CHECK UI Library
| 233816 | Task | UI:: Toggle Button |  | Done | Shimaa Mohamed Elsayed <shhadad@youxel.com> | 4 | 2.5 | 0 | 2 | [5 empty] | Design | Design
CHECK UI Library | 228369 | User Story | Galleria Component | 3 | Ready for release |  |  |  |  | 2 |  |  |  |  | CHECK UI Library
| 233934 | Task | FE :: Edit in galleria component in UI kit |  | Done | Hussein Abdallah <habdallah@youxel.com> | 3 | 3 | 0 | 2 | [5 empty] | Development | Front End
CHECK UI Library | 255494 | User Story | Table component | 3 | In Development |  |  |  |  | 2 |  |  |  |  | CHECK UI Library
| 255495 | Task | FE:: Add action menu column to table |  | Done | Hussein Abdallah <habdallah@youxel.com> | 4 | 4 | 0 | 2 | [5 empty] | Development | Front End
| 255495 | Task | Design :: Unify status and tag components |  | Active | Mariam Mohamed Saeed <msaeed@youxel.com> | 5 | 4.4 | 0.6 | 2 | [5 empty] | Design | Design
CHECK UI Library | 227974 | User Story | Design System Adjustments | 5 | Active |  |  |  |  | 2 |  |  |  |  | CHECK UI Library
| 250832 | Task | UI:: Contextual Button Component |  | Ready For Review | Shimaa Mohamed Elsayed <shhadad@youxel.com> | 5 | 5 | 0 | 2 | [5 empty] | Design | Design
| 250832 | Task | Design system: date and time documentation |  | Done | Mariam Mohamed Saeed <msaeed@youxel.com> | 3 | 7.67 | 0 | 2 | [5 empty] | Design | Design
| 250832 | Task | design systems: create date and time component |  | Done | Mariam Mohamed Saeed <msaeed@youxel.com> | 5 | 16.34 | 0 | 2 | [5 empty] | Design | Design
| 250832 | Task | UI:: DropDown/Checkboxes/Radio:: Add other option & Input |  | Done | Mariam Mohamed Saeed <msaeed@youxel.com> | 3 | 3.5 | 0 | 2 | [5 empty] | Design | Design
| 250832 | Task | Design system: typography |  | Done | Mariam Mohamed Saeed <msaeed@youxel.com> | 2 | 14.5 | 0 | 2 | [5 empty] | Design | Design
| 250832 | Task | UI:: Text Area:: Rich text editor |  | Done | Mariam Mohamed Saeed <msaeed@youxel.com> | 3 | 3.92 | 0 | 2 | [5 empty] | Design | Design
| 250832 | Task | Design system: Side Menu Documentation and add new variants |  | Done | Mariam Mohamed Saeed <msaeed@youxel.com> | 6 | 7.07 | 0 | 2 | [5 empty] | Design | Design
| 250832 | Task | UI:: Tree Select:: Documentation |  | Done | Mariam Mohamed Saeed <msaeed@youxel.com> | 4 | 6 | 0 | 2 | [5 empty] | Documentation | Design
| 250832 | Task | UI:: Tree Select:: Build Component |  | Done | Mariam Mohamed Saeed <msaeed@youxel.com> | 5 | 10.5 | 0 | 2 | [5 empty] | Design | Design
| 250832 | Task | UI:: Split button- Documentation |  | Done | Mariam Mohamed Saeed <msaeed@youxel.com> | 3 | 4.5 | 0 | 2 | [5 empty] | Documentation | Design
| 250832 | Task | UI:: Split button- Create Components |  | Ready For Review | Mariam Mohamed Saeed <msaeed@youxel.com> | 7 | 17 | 0 | 2 | [5 empty] | Design | Design
| 250832 | Task | UX:: Documentation Tabs / Tab Category |  | Done | Mariam Mohamed Saeed <msaeed@youxel.com> | 4 | 2 | 2 | 2 | [5 empty] | Documentation | Design
| 250832 | Task | UI:: Tabs Variants>> Survey |  | Done | Mariam Mohamed Saeed <msaeed@youxel.com> | 3 | 1.5 | 1.5 | 2 | [5 empty] | Design | Design
| 250832 | Task | Design system: pagination documentation |  | Ready For Review | Mariam Mohamed Saeed <msaeed@youxel.com> | 2 | 1.85 | 0.15 | 2 | [5 empty] | Design | Design
| 250832 | Task | Design system: spaces |  | New | Mariam Mohamed Saeed <msaeed@youxel.com> | 1 | 0 | 1 | 2 | [5 empty] | Design | Design
| 250832 | Task | Design system: recall text colors from semantics |  | New | Mariam Mohamed Saeed <msaeed@youxel.com> | 1 | 0 | 1 | 2 | [5 empty] | Design | Design
| 250832 | Task | UI:: Focus status For Inputs |  | New | Mariam Mohamed Saeed <msaeed@youxel.com> | 2 | 0 | 2 | 2 | [5 empty] | Design | Design
| 250832 | Task | UI: Progress icon shape |  | Done | Mariam Mohamed Saeed <msaeed@youxel.com> | 5 | 4 | 1 | 2 | [5 empty] | Design | Design
| 250832 | Task | UI:: File Upload/Multi Upload- Documentation |  | Ready For Review | Shimaa Mohamed Elsayed <shhadad@youxel.com> | 4 | 4 | 0 | 2 | [5 empty] | Documentation | Design
| 250832 | Task | UI:: File Upload/Multi Upload- View all component Variations |  | Ready For Review | Shimaa Mohamed Elsayed <shhadad@youxel.com> | 5 | 4 | 1 | 2 | [5 empty] | Design | Design
| 250832 | Task | UX:: Contextual Buttons Documentation |  | Ready For Review | Shimaa Mohamed Elsayed <shhadad@youxel.com> | 7 | 10.58 | 0 | 2 | [5 empty] | Documentation | Design
| 250832 | Task | UI:: File Upload Progress- Documentation |  | Ready For Review | Shimaa Mohamed Elsayed <shhadad@youxel.com> | 2 | 2 | 0 | 2 | [5 empty] | Documentation | Design
| 250832 | Task | UI:: File Upload Progress- View All Variations |  | Ready For Review | Shimaa Mohamed Elsayed <shhadad@youxel.com> | 3 | 5 | 0 | 2 | [5 empty] | Design | Design
| 250832 | Task | UI:: File Upload/ Single- Documentation |  | Ready For Review | Shimaa Mohamed Elsayed <shhadad@youxel.com> | 2 | 3.27 | 0 | 2 | [5 empty] | Design | Design
| 250832 | Task | UX:: Documentation:: Difference between Contextual Button / Link |  | Ready For Review | Shimaa Mohamed Elsayed <shhadad@youxel.com> | 3 | 4.25 | 0 | 2 | [5 empty] | Documentation | Design
Communication Module (Messages) | 228964 | User Story | Create Chat App | 8 | In Development |  |  |  |  | 1 |  |  |  |  | Communication Module (Messages)
Communication Module (Messages) | 228960 | User Story | As a user I can send text message in a conversation | 5 | In Development |  |  |  |  | 1 |  |  |  |  | Communication Module (Messages)
| 242628 | Bug | Typing indicator appears immediately upon opening a conversation without typing |  | Closed | Galal Torkey <gtorkey@youxel.com> | 0 | 0.5 | 0 | 3 | 2 - High | [5 empty] | Front End
| 242628 | Bug | Typing indicator is triggered when focusing and unfocusing the input field without typing |  | Closed | Galal Torkey <gtorkey@youxel.com> | 0 | 0 | 0 | 3 | 2 - High | [5 empty] | Front End
| 242628 | Bug | Typing indicator is displayed to the receiver after the sender successfully sends image attachments, even though no text input or typing action occurs. |  | Closed | Galal Torkey <gtorkey@youxel.com> | 0 | 0 | 0 | 3 | 2 - High | [5 empty] | Front End
| 242628 | Bug | New Messages Indicator does not appear when a new message is received in Full Screen Chat |  | Closed | Galal Torkey <gtorkey@youxel.com> | 0 | 0 | 0 | 3 | 4 - Low | [5 empty] | Front End
| 242628 | Task | FE:: Seen Message Logic |  | Done | Enas Diab <ediab@youxel.com> | 4 | 4 | 0 | 2 |  |  |  |  | Next Sprint | Development | Front End
| 242628 | Task | FE:: Scroll to bottom and "New Messages" Button Cycle |  | Done | Alaa Ezzat <aezzat@youxel.com> | 4 | 4 | 0 | 2 |  |  |  |  | Ad-hoc | Development | Front End
| 242628 | Task | QC:: Automate Test Cases |  | Done | Galal Torkey <gtorkey@youxel.com> | 14 | 15 | 0 | 2 | [5 empty] | Test Automation | Testing
Communication Module (Messages) | 228960 | User Story | As a user I can see list of my conversations | 3 | In Development |  |  |  |  | 1 |  |  |  |  | Communication Module (Messages)
| 247747 | Task | UI:: Message Types Enhancement |  | Done | Shimaa Mohamed Elsayed <shhadad@youxel.com> | 2 | 1.5 | 0 | 2 |  |  |  |  | Ad-hoc | Design | Design
| 247747 | Bug | Conversation list does not show latest conversations after login until page refresh |  | New | Mohamed Mustafa Farrag <mfarrag@youxel.com> | 0 | 0 | 0.5 | 2 | 2 - High | [5 empty] | Front End
Communication Module (Messages) | 228960 | User Story | As a user I can start new conversation | 3 | Ready For Testing |  |  |  |  | 1 |  |  |  |  | Communication Module (Messages)
| 247748 | Task | QC:: Automate Test Cases |  | Done | Galal Torkey <gtorkey@youxel.com> | 14 | 15 | 0 | 2 | [5 empty] | Test Automation | Testing
| 247748 | Bug | Search does not return user when typing the full exact name while creating a new conversation |  | Resolved | Galal Torkey <gtorkey@youxel.com> | 0 | 2 | 0 | 2 | 2 - High | [5 empty] | Development
Communication Module (Messages) | 228960 | User Story | As a user I can reply on any message | 5 | Ready For Review |  |  |  |  | 2 |  |  |  |  | Communication Module (Messages)
| 244767 | Task | FE:: Jump to Message integration |  | Done | Alaa Ezzat <aezzat@youxel.com> | 4 | 4 | 0 | 2 | [5 empty] | Development | Front End
| 244767 | Task | FE:: Fetch Messages while Scrolling Up/Down |  | Done | Alaa Ezzat <aezzat@youxel.com> | 5 | 5 | 0 | 2 | [5 empty] | Development | Front End
| 244767 | Task | FE:: Handle Socket Updates in Anchor Mode |  | Done | Alaa Ezzat <aezzat@youxel.com> | 2 | 3 | 0 | 2 | [5 empty] | Development | Front End
| 244767 | Task | FE:: Start Point for anchor Mode |  | Done | Alaa Ezzat <aezzat@youxel.com> | 3 | 3 | 0 | 2 | [5 empty] | Development | Front End
| 244767 | Task | FE:: Verify common properties (notes) with anchor mode |  | Ready For Review | Alaa Ezzat <aezzat@youxel.com> | 4 | 3 | 1 | 2 | [5 empty] | Development | Front End
| 244767 | Task | FE:: Exit Anchor Mode When Sending Message to see pending messages |  | Done | Alaa Ezzat <aezzat@youxel.com> | 2 | 5 | 0 | 2 | [5 empty] | Development | Front End
| 244767 | Task | FE:: Update Has More Flags |  | Done | Alaa Ezzat <aezzat@youxel.com> | 4 | 4 | 0 | 2 |  |  |  |  | Ad-hoc | Development | Front End
| 244767 | Task | FE:: Anchor Mode Investigation |  | Done | Alaa Ezzat <aezzat@youxel.com> | 0 | 20.5 | 0 | 2 | [5 empty] | Development | Front End
Communication Module (Messages) | 228960 | User Story | As a user I can delete my messages | 3 | Done Development |  |  |  |  | 1 |  |  |  |  | Communication Module (Messages)
| 244764 | Bug | Undo option disappears after switching to another conversation |  | On Hold | Alaa Ezzat <aezzat@youxel.com> | 0 | 0 | 0 | 3 | 2 - High | [5 empty] | Front End
| 244764 | Task | FE:: Add Undo Text button type |  | Done | Alaa Ezzat <aezzat@youxel.com> | 0.5 | 0.5 | 0 | 2 | [5 empty] | Development | Front End
Communication Module (Messages) | 228960 | User Story | As a user I can mark message as unread | 5 | Ready For Testing |  |  |  |  | 2 |  |  |  |  | Communication Module (Messages)
| 244770 | Bug | Unread marker is displayed above a deleted message when marking the following message as unread |  | Closed | Galal Torkey <gtorkey@youxel.com> | 0 | 2 | 0 | 3 | 2 - High | [5 empty] | Development
| 244770 | Task | Fix::. Unread marker is displayed above a deleted message when marking the following message as unread |  | Done | Mahmoud Ibrahim Elfeqy <mfeqy@youxel.com> | 2 | 2 | 0 | 2 |  |  |  |  | Bug Fixing Actual Effort | Development | Development
Communication Module (Messages) | 228960 | User Story | As a user I can send attachment in a conversation | 5 | In Development |  |  |  |  | 2 |  |  |  |  | Communication Module (Messages)
| 242629 | Task | UX:: Limitations for Files Uploaded/ Voice Messages |  | Ready For Review | Shimaa Mohamed Elsayed <shhadad@youxel.com> | 2 | 2 | 0 | 2 | [5 empty] | Design | Design
| 242629 | Task | UI: Error: on image |  | Ready For Review | Shimaa Mohamed Elsayed <shhadad@youxel.com> | 2 | 2 | 0 | 2 | [5 empty] | Design | Design
| 242629 | Task | UI UX :: handle error case when open image first time |  | Ready For Review | Shimaa Mohamed Elsayed <shhadad@youxel.com> | 2 | 0.25 | 1.75 | 2 | [5 empty] | Design | Design
| 242629 | Task | UI/UX:: Show Case Multiple Files in Message Bubble |  | Done | Shimaa Mohamed Elsayed <shhadad@youxel.com> | 2 | 1 | 0 | 2 | [5 empty] | Design | Design
Communication Module (Messages) | 228960 | User Story | As a user I can forward a message | 5 | In Development |  |  |  |  | 2 |  |  |  |  | Communication Module (Messages)
| 244768 | Task | UI/UX: Create popup for Access Denied when try to go to message |  | Done | Shimaa Mohamed Elsayed <shhadad@youxel.com> | 2 | 1 | 0 | 2 | [5 empty] | Design | Design
| 244768 | Task | FE:: Create Forward Popup UI |  | Ready For Review | Alaa Ezzat <aezzat@youxel.com> | 7 | 6 | 1 | 2 | [5 empty] | Development | Front End
| 244768 | Task | FE:: Forward Message Integration |  | In Development | Alaa Ezzat <aezzat@youxel.com> | 4 | 5 | 1 | 2 | [5 empty] | Development | Front End
| 244768 | Task | FE:: Use Forward-message-box in input-message and message-box |  | In Development | Alaa Ezzat <aezzat@youxel.com> | 3 | 0 | 3 | 2 | [5 empty] | Development | Front End
| 244768 | Task | FE:: Update Input-message with Forward Mode |  | Ready For Review | Alaa Ezzat <aezzat@youxel.com> | 2 | 1 | 1 | 2 | [5 empty] | Development | Front End
| 244768 | Task | FE:: Jump to Forwarded Message |  | In Development | Alaa Ezzat <aezzat@youxel.com> | 3 | 2 | 1 | 2 | [5 empty] | Development | Front End
| 244768 | Task | FE:: Create popup for Access Denied when try to go to message |  | In Development | Alaa Ezzat <aezzat@youxel.com> | 4 | 3 | 1 | 2 | [5 empty] | Development | Front End
| 244768 | Task | FE :: Use content display component in replay and forward component |  | Done | Alaa Ezzat <aezzat@youxel.com> | 2 | 2 | 0 | 2 | [5 empty] | Development | Front End
| 244768 | Task | FE:: Create Reusable Component select-users |  | Done | Alaa Ezzat <aezzat@youxel.com> | 3 | 3 | 0 | 2 |  |  |  |  | Ad-hoc | Development | Front End
Communication Module (Messages) | 228960 | User Story | As a user I can search in the conversation for certain message (Full screen) | 5 | Ready For Testing |  |  |  |  | 2 |  |  |  |  | Communication Module (Messages)
| 244772 | Task | FE:: Go To selected Message |  | Done | Mohamed Mustafa Farrag <mfarrag@youxel.com> | 2 | 2 | 0 | 2 | [5 empty] | Development | Front End
| 244772 | Task | FE:: Update Message Box UI for the selected searched Message |  | Done | Mohamed Mustafa Farrag <mfarrag@youxel.com> | 2 | 2 | 0 | 2 | [5 empty] | Development | Front End
Communication Module (Messages) | 228961 | User Story | As a owner of a group I can change the group name | 3 | Ready For Testing |  |  |  |  | 3 |  |  |  |  | Communication Module (Messages)
| 244756 | Task | FE :: Add edit group name popups |  | Done | Mohamed Mustafa Farrag <mfarrag@youxel.com> | 4 | 4 | 0 | 2 | [5 empty] | Development | Front End
| 244756 | Task | FE :: Integrate with api to change group name |  | Done | Mohamed Mustafa Farrag <mfarrag@youxel.com> | 4 | 4 | 0 | 2 | [5 empty] | Development | Front End
| 244756 | Task | FE:: Update Caching after changing group name |  | Done | Mohamed Mustafa Farrag <mfarrag@youxel.com> | 4 | 4 | 0 | 2 | [5 empty] | Development | Front End
Communication Module (Messages) | 228960 | User Story | As a user I can record an audio and send it over conversation | 5 | Ready For Review |  |  |  |  | 2 |  |  |  |  | Communication Module (Messages)
| 244761 | Task | FE:: Voice Recorder Component Logic |  | Done | Mohamed Mustafa Farrag <mfarrag@youxel.com> | 7 | 7 | 0 | 2 |  |  |  |  | Communication Module (Messages) | Development | Front End
| 244761 | Task | FE:: Get voice from storage and show it in message box |  | Ready For Review | Mohamed Mustafa Farrag <mfarrag@youxel.com> | 6 | 0 | 6 | 2 |  |  |  |  | Communication Module (Messages) | Development | Front End
| 244761 | Task | FE :: Indicate users when someone is recording |  | Done | Mohamed Mustafa Farrag <mfarrag@youxel.com> | 3 | 3 | 0 | 2 | [5 empty] | Development | Front End
| 244761 | Task | BE :: Update Messages to Support Sending Voice Records |  | Done | Mahmoud Ibrahim Elfeqy <mfeqy@youxel.com> | 8 | 8 | 0 | 2 |  |  |  |  | Communication Module (Messages) | Development | Development
| 244761 | Task | BE :: Searching for the possibility of implementation FFmpeg |  | Done | Mahmoud Ibrahim Elfeqy <mfeqy@youxel.com> | 6 | 6 | 0 | 2 | [5 empty] | Development | Development
| 244761 | Task | BE :: Add Essential Ffmpeg binaries |  | Done | Mahmoud Ibrahim Elfeqy <mfeqy@youxel.com> | 10 | 10 | 0 | 2 |  |  |  |  | Ad-hoc | Development | Development
Communication Module (Messages) | 228961 | User Story | As a owner of the group I can change the group image | 3 | In Development |  |  |  |  | 3 |  |  |  |  | Communication Module (Messages)
| 244757 | Task | FE:: Change Group image Integration |  | Ready For Review | Mohamed Mustafa Farrag <mfarrag@youxel.com> | 5 | 5 | 0 | 2 | [5 empty] | Development | Front End
| 244757 | Task | FE:: Update Cashing after change group image |  | New | Mohamed Mustafa Farrag <mfarrag@youxel.com> | 2 | 0 | 2 | 2 | [5 empty] | Development | Front End
Communication Module (Messages) | 228961 | User Story | As owner of the group I can remove the group image | 3 | New |  |  |  |  | 3 |  |  |  |  | Communication Module (Messages)
| 244758 | Task | FE:: Remove Group Image integration |  | New | Mohamed Mustafa Farrag <mfarrag@youxel.com> | 4 | 0 | 4 | 2 | [5 empty] | Development | Front End
| 244758 | Task | FE:: Update Caching after remove group image |  | New | Mohamed Mustafa Farrag <mfarrag@youxel.com> | 2 | 0 | 2 | 2 | [5 empty] | Development | Front End
| 244758 | Task | FE:: Remove Popup UI |  | New | Mohamed Mustafa Farrag <mfarrag@youxel.com> | 4 | 0 | 4 | 2 | [5 empty] | Development | Front End
Administration Module | 241399 | User Story | QC Review (Design & BRD) | 0 | Done Development |  |  |  |  | 2 |  |  |  |  | Administration Module
| 263534 | Task | Analyze Requirements & Videos |  | Done | Galal Torkey <gtorkey@youxel.com> | 7 | 10 | 0 | 2 | [5 empty] | Gather Requirements | Business
| 263534 | Task | Reviewing CheckNow System (new) |  | Done | Galal Torkey <gtorkey@youxel.com> | 7 | 7 | 0 | 2 | [5 empty] | Review | Business
| 263534 | Task | QC:: Analyze Requirements & Identify Business Gaps |  | Done | Galal Torkey <gtorkey@youxel.com> | 7 | 7 | 0 | 2 | [5 empty] | Documentation | Testing
Administration Module | 241399 | User Story | Administration Portal API | 5 | In Development |  |  |  |  | 2 |  |  |  |  | Administration Module
| 263834 | Task | FE:: add organization identifier input field with custom validations |  | Done | Hussein Abdallah <habdallah@youxel.com> | 3 | 6.5 | 0 | 2 | [5 empty] | Development | Front End
| 263834 | Task | FE:: add identfier to url domain |  | Done | Hussein Abdallah <habdallah@youxel.com> | 3 | 3 | 0 | 2 | [5 empty] | Development | Front End
| 263834 | Task | FE:: updated changed apis |  | Done | Hussein Abdallah <habdallah@youxel.com> | 3 | 7 | 0 | 2 | [5 empty] | Development | Front End
| 263834 | Task | BE :: Add System Commponents to Host |  | Done | Mahmoud Adel Ali <madeel@youxel.com> | 2 | 2 | 0 | 2 | [5 empty] | Development | Development
Administration Module | 241399 | User Story | Locations Flat Relations | 3 | Done Development |  |  |  |  | 2
| 264506 | Task | Add Flat Relations Table and Trigger |  | Done | Mahmoud Adel Ali <madeel@youxel.com> | 4 | 4 | 0 | 2 | [5 empty] | Development | Development
| 264506 | Task | Search Tree Table |  | Done | Mahmoud Adel Ali <madeel@youxel.com> | 7 | 7 | 0 | 2 | [5 empty] | Development | Development
Administration Module | 195967 | User Story | Set/Edit Company information | 3 | Ready For Testing |  |  |  |  | 1 |  |  |  |  | Administration Module
| 247302 | Task | UI:: Organization Identifier |  | Done | Shimaa Mohamed Elsayed <shhadad@youxel.com> | 3 | 4 | 0 | 2 | [5 empty] | Design | Design
| 247302 | Task | QC:: Design Test Cases |  | Done | Galal Torkey <gtorkey@youxel.com> | 2 | 2 | 0 | 2 | [5 empty] | Write Test Cases | Testing
Administration Module | 195967 | User Story | Multitenancy | 8 | Done Development |  |  |  |  | 2 |  |  |  |  | Administration Module
| 253676 | Task | Setup Finbuckle + Tenant Domain Models – Package integration, Organization entity, UserOrganization entity, EF configs & migration |  | Done | Mahmoud Adel Ali <madeel@youxel.com> | 8 | 8 | 0 | 2 | [5 empty] | Development | Development
| 253676 | Task | Tenant Resolution Strategies – Header-based, subdomain, path resolvers + ICurrentTenant accessor |  | Done | Mahmoud Adel Ali <madeel@youxel.com> | 8 | 8 | 0 | 2 | [5 empty] | Development | Development
| 253676 | Task | Tenant-Aware Seed Data – Seeder infrastructure, refactor existing seeds, org onboarding defaults |  | Done | Mahmoud Adel Ali <madeel@youxel.com> | 8 | 8 | 0 | 2 | [5 empty] | Development | Development
| 253676 | Task | Add Tenant Entity and New Host Context |  | Done | Mahmoud Adel Ali <madeel@youxel.com> | 8 | 6 | 0 | 2 |  |  |  |  | Ad-hoc | Development | Development
Administration Module | 195967 | User Story | Upload/Change Company Logo | 3 | Ready For Testing |  |  |  |  | 1 |  |  |  |  | Administration Module
| 247303 | Task | QC:: Design Test Cases |  | Done | Galal Torkey <gtorkey@youxel.com> | 1 | 1 | 0 | 2 | [5 empty] | Write Test Cases | Testing
Administration Module | 195967 | User Story | Set Company Identity | 5 | Ready For Testing |  |  |  |  | 1 |  |  |  |  | Administration Module
| 247304 | Task | QC:: Design Test Cases |  | Done | Galal Torkey <gtorkey@youxel.com> | 2 | 1 | 1 | 2 | [5 empty] | Write Test Cases | Testing
Administration Module | 195967 | User Story | Set / Edit the supported langauges | 5 | Ready For Testing |  |  |  |  | 1 |  |  |  |  | Administration Module
| 247305 | Task | QC:: Design Test Cases |  | Done | Galal Torkey <gtorkey@youxel.com> | 2 | 2 | 0 | 2 | [5 empty] | Write Test Cases | Testing
Administration Module | 195968 | User Story | User should be able to view POI categories | 3 | Ready For Testing |  |  |  |  | 1 |  |  |  |  | Administration Module
| 247306 | Task | QC:: Design Test Cases |  | Done | Galal Torkey <gtorkey@youxel.com> | 2 | 1 | 1 | 2 | [5 empty] | Write Test Cases | Testing
Administration Module | 195968 | User Story | User should be able to manage location subcategory | 5 | Ready For Testing |  |  |  |  | 2 |  |  |  |  | Administration Module
| 247322 | Task | QC:: Design Test Cases |  | Done | Galal Torkey <gtorkey@youxel.com> | 2 | 2 | 0 | 2 | [5 empty] | Write Test Cases | Testing
Administration Module | 195968 | User Story | User should be able to manage Location categories | 5 | Ready For Testing |  |  |  |  | 2 |  |  |  |  | Administration Module
| 247321 | Task | QC:: Design Test Cases |  | Done | Galal Torkey <gtorkey@youxel.com> | 3 | 2 | 1 | 2 | [5 empty] | Write Test Cases | Testing
Administration Module | 195968 | User Story | User should be able to manage location importance | 5 | Ready For Testing |  |  |  |  | 2 |  |  |  |  | Administration Module
| 247324 | Task | QC:: Design Test Cases |  | Done | Galal Torkey <gtorkey@youxel.com> | 2 | 2 | 0 | 2 | [5 empty] | Write Test Cases | Testing
Administration Module | 195968 | User Story | User should be able to manage location account | 5 | Ready For Testing |  |  |  |  | 2 |  |  |  |  | Administration Module
| 247323 | Task | QC:: Design Test Cases |  | Done | Galal Torkey <gtorkey@youxel.com> | 3 | 2 | 1 | 2 | [5 empty] | Write Test Cases | Testing
Administration Module | 195968 | User Story | User should be able to view location tree (org chart) | 8 | Ready For Testing |  |  |  |  | 1 |  |  |  |  | Administration Module
| 247308 | Task | QC:: Design Test Cases |  | Done | Galal Torkey <gtorkey@youxel.com> | 1 | 1 | 0 | 2 | [5 empty] | Write Test Cases | Testing
Administration Module | 195968 | User Story | User should be able to add location optional information | 5 | Ready For Review |  |  |  |  | 1 |  |  |  |  | Administration Module
| 247315 | Task | UI: Loading, error handle, Saving Location Types |  | Ready For Review | Shimaa Mohamed Elsayed <shhadad@youxel.com> | 2 | 1 | 1 | 2 | [5 empty] | Design | Design
Administration Module | 195968 | User Story | User should be able to add loction with its mandatory information | 5 | Ready For Testing |  |  |  |  | 1 |  |  |  |  | Administration Module
| 247313 | Task | QC:: Design Test Cases |  | Done | Galal Torkey <gtorkey@youxel.com> | 2 | 2 | 0 | 2 | [5 empty] | Write Test Cases | Testing
Administration Module | 195968 | User Story | User should be able to add location attachments | 5 | Ready For Testing |  |  |  |  | 1 |  |  |  |  | Administration Module
| 247314 | Task | QC:: Design Test Cases |  | Done | Galal Torkey <gtorkey@youxel.com> | 2 | 2 | 0 | 2 | [5 empty] | Write Test Cases | Testing
Administration Module | 195968 | User Story | User should be able to edit locations | 5 | Ready For Testing |  |  |  |  | 1 |  |  |  |  | Administration Module
| 247316 | Task | QC:: Design Test Cases |  | Done | Galal Torkey <gtorkey@youxel.com> | 2 | 2 | 0 | 2 | [5 empty] | Write Test Cases | Testing
Administration Module | 195968 | User Story | User should be able to delete parent location | 3 | In Development |  |  |  |  | 1 |  |  |  |  | Administration Module
| 247312 | Task | UI: Revisit The UX of the Delete Dialog |  | Done | Shimaa Mohamed Elsayed <shhadad@youxel.com> | 1 | 0.52 | 0 | 2 | [5 empty] | Design | Design
| 247312 | Task | QC:: Design Test Cases |  | Done | Galal Torkey <gtorkey@youxel.com> | 2 | 2 | 0 | 2 | [5 empty] | Write Test Cases | Testing
Administration Module | 195968 | User Story | User should be able to move sub-locations from one parent to another | 5 | In Development |  |  |  |  | 1 |  |  |  |  | Administration Module
Administration Module | 195968 | User Story | User should be able to activate/deactivate Location | 3 | Ready For Review |  |  |  |  | 1 |  |  |  |  | Administration Module
| 247310 | Task | UI: Check this action to reflect it in location listing |  | Done | Shimaa Mohamed Elsayed <shhadad@youxel.com> | 3 | 4 | 0 | 2 | [5 empty] | Design | Design
| 247310 | Task | BE :: Activate-Deactivate Locations |  | Done | Mahmoud Adel Ali <madeel@youxel.com> | 4 | 4 | 0 | 2 | [5 empty] | Development | Development
| 247310 | Task | UI:: Update All tables: Active & Inactive Status |  | Done | Shimaa Mohamed Elsayed <shhadad@youxel.com> | 1.5 | 1.5 | 0 | 2 |  |  |  |  | Ad-hoc | Design | Design
Administration Module | 195968 | User Story | User should be able to handle location translation | 5 | Ready For Testing |  |  |  |  | 1 |  |  |  |  | Administration Module
| 247319 | Task | QC:: Design Test Cases |  | Done | Galal Torkey <gtorkey@youxel.com> | 1 | 1 | 0 | 2 | [5 empty] | Write Test Cases | Testing
Administration Module | 195968 | User Story | User should be able to delete sub location | 3 | In Development |  |  |  |  | 1 |  |  |  |  | Administration Module
| 247311 | Task | QC:: Design Test Cases |  | Done | Galal Torkey <gtorkey@youxel.com> | 2 | 2 | 0 | 2 | [5 empty] | Write Test Cases | Testing
Administration Module | 195969 | User Story | Manage KPI Indicators (CRUD + Localization) | 5 | In Development |  |  |  |  | 2 |  |  |  |  | Administration Module
| 252836 | Task | Design:: update kpi indicator table |  | Done | Shimaa Mohamed Elsayed <shhadad@youxel.com> | 3 | 3 | 0 | 2 |  |  |  |  | Ad-hoc | Design | Design
| 252836 | Task | BE:: fix kpi indicators list translation |  | Done | Mahmoud Adel Ali <madeel@youxel.com> | 4 | 4 | 0 | 2 | [5 empty] | Development | Development
| 252836 | Task | BE:: fix kpi indicator delete api |  | Done | Mahmoud Adel Ali <madeel@youxel.com> | 4 | 4 | 0 | 2 | [5 empty] | Development | Development
| 252836 | Task | BE :: Implement Activate and Deactivate Features |  | Done | Mahmoud Adel Ali <madeel@youxel.com> | 4 | 2 | 0 | 2 | [5 empty] | Development | Development
Administration Module | 195969 | User Story | Kpi Definistion Form | 5 | Ready For Review |  |  |  |  | 2 |  | Development |  |  | Administration Module
| 264492 | Task | FE:: Create routes and components - service -interfaces |  | Done | Hussein Abdallah <habdallah@youxel.com> | 4 | 4 | 0 | 2 | [5 empty] | Development | Front End
| 264492 | Task | FE:: create KPI criteria form Ui |  | Done | Hussein Abdallah <habdallah@youxel.com> | 5 | 5 | 0 | 2 | [5 empty] | Development | Front End
| 264492 | Task | FE:: KPI criteria integration |  | Done | Hussein Abdallah <habdallah@youxel.com> | 5 | 5 | 0 | 2 | [5 empty] | Development | Front End
| 264492 | Task | FE:: Weight form ui |  | Ready For Review | Hussein Abdallah <habdallah@youxel.com> | 4 | 4 | 0 | 2 | [5 empty] | Development | Front End
| 264492 | Task | FE:: Weight form integration |  | Ready For Review | Hussein Abdallah <habdallah@youxel.com> | 4 | 3.5 | 0.5 | 2 | [5 empty] | Development | Front End
| 264492 | Task | Design :: add responsive design |  | Done | Shimaa Mohamed Elsayed <shhadad@youxel.com> | 2 | 1 | 0 | 2 |  |  |  |  | MidSprint_Addition | Design | Design
Administration Module | 195969 | User Story | Kpi Definisions View | 5 | Ready For Testing |  |  |  |  | 2 |  |  |  |  | Administration Module
| 264494 | Task | FE:: create kpi definision view page ui |  | Done | Hussein Abdallah <habdallah@youxel.com> | 4 | 4 | 0 | 2 | [5 empty] | Development | Front End
| 264494 | Task | FE:: kpi definistion view integration |  | Done | Hussein Abdallah <habdallah@youxel.com> | 4 | 4 | 0 | 2 | [5 empty] | Development | Front End
Workflow Library | 193289 | User Story | Create Workflow System | 5 | In Development |  |  |  |  | 2 |  |  |  |  | Workflow Library
| 252825 | Task | UX/Ideate: SCENARIO 3: Creae user task |  | Done | Salma Sameh <ssameh@youxel.com> | 7 | 10.65 | 0 | 2 | [5 empty] | Design | Design
| 252825 | Task | UX/Ideate: SCENARIO 6: Working With Variables & Data |  | Done | Salma Sameh <ssameh@youxel.com> | 7 | 10 | 0 | 2 | [5 empty] | Design | Design
| 252825 | Task | UX/Ideate: SCENARIO 5: Creating routers (gateways) |  | Done | Salma Sameh <ssameh@youxel.com> | 7 | 8 | 0 | 2 | [5 empty] | Design | Design
| 252825 | Task | UX/Ideate: SCENARIO 4: Creating events |  | Done | Salma Sameh <ssameh@youxel.com> | 7 | 7 | 0 | 2 | [5 empty] | Design | Design
| 252825 | Task | UX/Wireframes: Node space |  | Done | Salma Sameh <ssameh@youxel.com> | 6 | 10 | 0 | 2 | [5 empty] | Design | Design
| 252825 | Task | UX/Ideate: SCENARIO 9: Editing & Scaling Existing Workflows |  | Done | Salma Sameh <ssameh@youxel.com> | 4 | 7.25 | 0 | 2 | [5 empty] | Design | Design
| 252825 | Task | UX/Ideate: SCENARIO 7: Testing the Workflow & Handle errors |  | Done | Salma Sameh <ssameh@youxel.com> | 7 | 7 | 0 | 2 | [5 empty] | Design | Design
| 252825 | Task | UX/Ideate: Finalize all builder wireframes |  | Done | Salma Sameh <ssameh@youxel.com> | 6 | 7 | 0 | 2 | [5 empty] | Design | Design
| 252825 | Task | UX: Plan for usability testing |  | Done | Salma Sameh <ssameh@youxel.com> | 7 | 7.5 | 0 | 2 |  |  |  |  | Recurring | Design | Design
| 252825 | Task | UX: Prep + structure UI phase |  | Done | Salma Sameh <ssameh@youxel.com> | 7 | 5.5 | 1.5 | 2 | [5 empty] | Design | Design
| 252825 | Task | UX/Define: Builder Information architecture |  | Done | Salma Sameh <ssameh@youxel.com> | 5 | 5 | 0 | 2 | [5 empty] | Design | Design
| 252825 | Task | UX/Define: Create user flows (start event & user task) |  | Done | Salma Sameh <ssameh@youxel.com> | 4 | 4 | 0 | 2 | [5 empty] | Design | Design
| 252825 | Task | UX: Create workflow user personas (hypothesis) |  | Done | Salma Sameh <ssameh@youxel.com> | 7 | 3 | 4 | 2 | [5 empty] | Design | Design
| 252825 | Task | BE :: Creat Workflows Project Template |  | Done | Mahmoud Adel Ali <madeel@youxel.com> | 5 | 5 | 0 | 2 | [5 empty] | Development | Development
| 252825 | Task | UX/Define: Document all builder wireframes results |  | Done | Salma Sameh <ssameh@youxel.com> | 4 | 4 | 0 | 2 | [5 empty] | Design | Design
| 252825 | Task | Feqy :: Study FormBuilder & Survey Implementation |  | Done | Mahmoud Ibrahim Elfeqy <mfeqy@youxel.com> | 7 | 7 | 0 | 2 |  |  |  |  | Ad-hoc | Development | Development
| 252825 | Task | BE :: Template Adjusment (Version & Multi-Tenant) |  | Done | Mahmoud Adel Ali <madeel@youxel.com> | 7 | 7 | 0 | 2 | [5 empty] | Development | Development
| 252825 | Task | BE :: Setup Vault Configuration in Base Template |  | Done | Mahmoud Adel Ali <madeel@youxel.com> | 7 | 7 | 0 | 2 | [5 empty] | Development | Development
| 252825 | Task | BE :: Create Workflow Base Entities |  | Done | Ahmed Talaat <atalaat@youxel.com> | 7 | 7 | 0 | 2 | [5 empty] | Development | Development
| 252825 | Task | BE :: Redis Function Investigation & Research |  | Done | Mahmoud Ibrahim Elfeqy <mfeqy@youxel.com> | 7 | 7 | 0 | 2 | [5 empty] | Development | Development
| 252825 | Task | BE :: Redis Function POC |  | Done | Mahmoud Ibrahim Elfeqy <mfeqy@youxel.com> | 7 | 7 | 0 | 2 | [5 empty] | Development | Development
| 252825 | Task | BE :: Configure Entities And Add Database Migrations |  | Done | Ahmed Talaat <atalaat@youxel.com> | 14 | 4 | 10 | 2 |  |  |  |  | Next Sprint | Development | Development
| 252825 | Task | BE :: Add Complete Node Types Reference Document |  | Done | Mahmoud Ibrahim Elfeqy <mfeqy@youxel.com> | 7 | 7 | 0 | 2 |  |  |  |  | Ad-hoc | Development | Development
| 252825 | Task | Edit "Complete Node Types Reference" Document on Notion |  | Done | Ahmed Talaat <atalaat@youxel.com> | 5 | 5 | 0 | 2 | [5 empty] | Development | Development
| 252825 | Task | Investigate Flowable Multi-Instance Output |  | Done | Mahmoud Adel Ali <madeel@youxel.com> | 7 | 7 | 0 | 2 | [5 empty] | Development | Development
| 252825 | Task | Investigate Camunda Multi-Instance Output |  | Done | Mahmoud Ibrahim Elfeqy <mfeqy@youxel.com> | 7 | 7 | 0 | 2 | [5 empty] | Development | Development
| 252825 | Task | Update Business Status to be on Nodes |  | Done | Mahmoud Ibrahim Elfeqy <mfeqy@youxel.com> | 3 | 3 | 0 | 2 | [5 empty] | Development | Development
| 252825 | Task | Investigate Removing Edges |  | Done | Mahmoud Adel Ali <madeel@youxel.com> | 7 | 7 | 0 | 2 | [5 empty] | Development | Development
| 252825 | Task | UI: Prepare the wireframes for the UI phase V2.2 |  | Done | Salma Sameh <ssameh@youxel.com> | 4 | 3 | 1 | 2 |  |  |  |  | Next Sprint | Design | Design
Learning, Development, and Process Improvement | 240010 | User Story | Automation Testing Cycle | 0 | Active |  |  |  |  | 2 |  | Testing
| 262102 | Task | API Requests integration with Playwright |  | New | Galal Torkey <gtorkey@youxel.com> | 5 | 5 | 0 | 2 | [5 empty] | Documentation | Testing
Learning, Development, and Process Improvement | 260486 | User Story | CMMI Reports | 0 | Released |  |  |  |  | 2 |  |  |  |  | CMMI
| 260487 | Task | CMMI Documentation Preparing |  | Done | Galal Torkey <gtorkey@youxel.com> | 2 | 0 | 2 | 2 | [5 empty] | Documentation | Testing
Meetings & Support | 247821 | User Story | Meeting logs iteration 26.17 | 0 | Released |  |  |  |  | 2
| 263833 | Task | Maryam: Stand ups and Meetings |  | Done | Mariam Mohamed Saeed <msaeed@youxel.com> | 0 | 7.08 | 0 | 2 | [5 empty] | Meetings | Design
| 263833 | Task | Salma: Meetings |  | Done | Salma Sameh <ssameh@youxel.com> | 0 | 11.02 | 0 | 2 | [5 empty] | Design | Design
| 263833 | Task | Talaat :: Stand-Ups, Meetings and Team Support |  | Done | Ahmed Talaat <atalaat@youxel.com> | 0 | 47 | 0 | 2 | [5 empty] | Development | Development
| 263833 | Task | Alhussien :: stand-up - meetings |  | Done | Hussein Abdallah <habdallah@youxel.com> | 0 | 22 | 0 | 2 | [5 empty] | Documentation | Front End
| 263833 | Task | Feqy :: Stand-Ups, Meetings and Team Support |  | Done | Mahmoud Ibrahim Elfeqy <mfeqy@youxel.com> | 0 | 21 | 0 | 2 | [5 empty] | Development | Development
| 263833 | Task | Galal::Meetings and Logs |  | Done | Galal Torkey <gtorkey@youxel.com> | 10 | 9 | 1 | 2 | [5 empty] | Meetings | Testing
| 263833 | Task | M Adel :: Stand-Ups, Meetings and Team Support |  | Done | Mahmoud Adel Ali <madeel@youxel.com> | 0 | 14 | 0 | 2 | [5 empty] | Development | Development
| 263833 | Task | Shaimaa:: Stand-ups, Meetings, Reviews and Team Support |  | Done | Shimaa Mohamed Elsayed <shhadad@youxel.com> | 0 | 13.67 | 0 | 2 | [5 empty] | Meetings | Design
| 263833 | Task | Alaa:: Meetings |  | Done | Alaa Ezzat <aezzat@youxel.com> | 0 | 16 | 0 | 2 | [5 empty] | Development | Front End
All
EPIC | Parent | Work Item Type | Title | Story Points | State | Assigned To | Original Estimate | Completed Work | Remaining Work | Priority | Severity | Phase | Dev delivery date | QC Delivery date | Tags | Task Category | Activity
| 260177 | Task | Breadcrumb inputs/outputs |  | Done | Enas Diab <ediab@youxel.com> | 3 | 6 | 0 | 2 | [5 empty] | Development | Front End
| 260177 | Task | BreadCrumb-menu |  | Done | Enas Diab <ediab@youxel.com> | 5 | 4 | 1 | 2 | [5 empty] | Development | Front End
| 251892 | Task | Create Lottie Component Structure & inputs |  | Done | Hussein Abdallah <habdallah@youxel.com> | 2 | 2 | 0 | 2 |  |  |  |  | MidSprint_Addition | Development | Front End
| 251892 | Task | UI: Lottie Color |  | Done | Shimaa Mohamed Elsayed <shhadad@youxel.com> | 4 | 13.67 | 0 | 2 | [5 empty] | Design | Design
| 233816 | Task | UI:: Toggle Button |  | Done | Shimaa Mohamed Elsayed <shhadad@youxel.com> | 4 | 2.5 | 0 | 2 | [5 empty] | Design | Design
| 233934 | Task | FE :: Edit in galleria component in UI kit |  | Done | Hussein Abdallah <habdallah@youxel.com> | 3 | 3 | 0 | 2 | [5 empty] | Development | Front End
| 255495 | Task | FE:: Add action menu column to table |  | Done | Hussein Abdallah <habdallah@youxel.com> | 4 | 4 | 0 | 2 | [5 empty] | Development | Front End
| 255495 | Task | Design :: Unify status and tag components |  | Active | Mariam Mohamed Saeed <msaeed@youxel.com> | 5 | 4.4 | 0.6 | 2 | [5 empty] | Design | Design
| 250832 | Task | UI:: Contextual Button Component |  | Ready For Review | Shimaa Mohamed Elsayed <shhadad@youxel.com> | 5 | 5 | 0 | 2 | [5 empty] | Design | Design
| 250832 | Task | Design system: date and time documentation |  | Done | Mariam Mohamed Saeed <msaeed@youxel.com> | 3 | 7.67 | 0 | 2 | [5 empty] | Design | Design
| 250832 | Task | design systems: create date and time component |  | Done | Mariam Mohamed Saeed <msaeed@youxel.com> | 5 | 16.34 | 0 | 2 | [5 empty] | Design | Design
| 250832 | Task | UI:: DropDown/Checkboxes/Radio:: Add other option & Input |  | Done | Mariam Mohamed Saeed <msaeed@youxel.com> | 3 | 3.5 | 0 | 2 | [5 empty] | Design | Design
| 250832 | Task | Design system: typography |  | Done | Mariam Mohamed Saeed <msaeed@youxel.com> | 2 | 14.5 | 0 | 2 | [5 empty] | Design | Design
| 250832 | Task | UI:: Text Area:: Rich text editor |  | Done | Mariam Mohamed Saeed <msaeed@youxel.com> | 3 | 3.92 | 0 | 2 | [5 empty] | Design | Design
| 250832 | Task | Design system: Side Menu Documentation and add new variants |  | Done | Mariam Mohamed Saeed <msaeed@youxel.com> | 6 | 7.07 | 0 | 2 | [5 empty] | Design | Design
| 250832 | Task | UI:: Tree Select:: Documentation |  | Done | Mariam Mohamed Saeed <msaeed@youxel.com> | 4 | 6 | 0 | 2 | [5 empty] | Documentation | Design
| 250832 | Task | UI:: Tree Select:: Build Component |  | Done | Mariam Mohamed Saeed <msaeed@youxel.com> | 5 | 10.5 | 0 | 2 | [5 empty] | Design | Design
| 250832 | Task | UI:: Split button- Documentation |  | Done | Mariam Mohamed Saeed <msaeed@youxel.com> | 3 | 4.5 | 0 | 2 | [5 empty] | Documentation | Design
| 250832 | Task | UI:: Split button- Create Components |  | Ready For Review | Mariam Mohamed Saeed <msaeed@youxel.com> | 7 | 17 | 0 | 2 | [5 empty] | Design | Design
| 250832 | Task | UX:: Documentation Tabs / Tab Category |  | Done | Mariam Mohamed Saeed <msaeed@youxel.com> | 4 | 2 | 2 | 2 | [5 empty] | Documentation | Design
| 250832 | Task | UI:: Tabs Variants>> Survey |  | Done | Mariam Mohamed Saeed <msaeed@youxel.com> | 3 | 1.5 | 1.5 | 2 | [5 empty] | Design | Design
| 250832 | Task | Design system: pagination documentation |  | Ready For Review | Mariam Mohamed Saeed <msaeed@youxel.com> | 2 | 1.85 | 0.15 | 2 | [5 empty] | Design | Design
| 250832 | Task | Design system: spaces |  | New | Mariam Mohamed Saeed <msaeed@youxel.com> | 1 | 0 | 1 | 2 | [5 empty] | Design | Design
| 250832 | Task | Design system: recall text colors from semantics |  | New | Mariam Mohamed Saeed <msaeed@youxel.com> | 1 | 0 | 1 | 2 | [5 empty] | Design | Design
| 250832 | Task | UI:: Focus status For Inputs |  | New | Mariam Mohamed Saeed <msaeed@youxel.com> | 2 | 0 | 2 | 2 | [5 empty] | Design | Design
| 250832 | Task | UI: Progress icon shape |  | Done | Mariam Mohamed Saeed <msaeed@youxel.com> | 5 | 4 | 1 | 2 | [5 empty] | Design | Design
| 250832 | Task | UI:: File Upload/Multi Upload- Documentation |  | Ready For Review | Shimaa Mohamed Elsayed <shhadad@youxel.com> | 4 | 4 | 0 | 2 | [5 empty] | Documentation | Design
| 250832 | Task | UI:: File Upload/Multi Upload- View all component Variations |  | Ready For Review | Shimaa Mohamed Elsayed <shhadad@youxel.com> | 5 | 4 | 1 | 2 | [5 empty] | Design | Design
| 250832 | Task | UX:: Contextual Buttons Documentation |  | Ready For Review | Shimaa Mohamed Elsayed <shhadad@youxel.com> | 7 | 10.58 | 0 | 2 | [5 empty] | Documentation | Design
| 250832 | Task | UI:: File Upload Progress- Documentation |  | Ready For Review | Shimaa Mohamed Elsayed <shhadad@youxel.com> | 2 | 2 | 0 | 2 | [5 empty] | Documentation | Design
| 250832 | Task | UI:: File Upload Progress- View All Variations |  | Ready For Review | Shimaa Mohamed Elsayed <shhadad@youxel.com> | 3 | 5 | 0 | 2 | [5 empty] | Design | Design
| 250832 | Task | UI:: File Upload/ Single- Documentation |  | Ready For Review | Shimaa Mohamed Elsayed <shhadad@youxel.com> | 2 | 3.27 | 0 | 2 | [5 empty] | Design | Design
| 250832 | Task | UX:: Documentation:: Difference between Contextual Button / Link |  | Ready For Review | Shimaa Mohamed Elsayed <shhadad@youxel.com> | 3 | 4.25 | 0 | 2 | [5 empty] | Documentation | Design
| 242628 | Bug | Typing indicator appears immediately upon opening a conversation without typing |  | Closed | Galal Torkey <gtorkey@youxel.com> | 0 | 0.5 | 0 | 3 | 2 - High | [5 empty] | Front End
| 242628 | Bug | Typing indicator is triggered when focusing and unfocusing the input field without typing |  | Closed | Galal Torkey <gtorkey@youxel.com> | 0 | 0 | 0 | 3 | 2 - High | [5 empty] | Front End
| 242628 | Bug | Typing indicator is displayed to the receiver after the sender successfully sends image attachments, even though no text input or typing action occurs. |  | Closed | Galal Torkey <gtorkey@youxel.com> | 0 | 0 | 0 | 3 | 2 - High | [5 empty] | Front End
| 242628 | Bug | New Messages Indicator does not appear when a new message is received in Full Screen Chat |  | Closed | Galal Torkey <gtorkey@youxel.com> | 0 | 0 | 0 | 3 | 4 - Low | [5 empty] | Front End
| 242628 | Task | FE:: Seen Message Logic |  | Done | Enas Diab <ediab@youxel.com> | 4 | 4 | 0 | 2 |  |  |  |  | Next Sprint | Development | Front End
| 242628 | Task | FE:: Scroll to bottom and "New Messages" Button Cycle |  | Done | Alaa Ezzat <aezzat@youxel.com> | 4 | 4 | 0 | 2 |  |  |  |  | Ad-hoc | Development | Front End
| 242628 | Task | QC:: Automate Test Cases |  | Done | Galal Torkey <gtorkey@youxel.com> | 14 | 15 | 0 | 2 | [5 empty] | Test Automation | Testing
| 247747 | Task | UI:: Message Types Enhancement |  | Done | Shimaa Mohamed Elsayed <shhadad@youxel.com> | 2 | 1.5 | 0 | 2 |  |  |  |  | Ad-hoc | Design | Design
| 247747 | Bug | Conversation list does not show latest conversations after login until page refresh |  | New | Mohamed Mustafa Farrag <mfarrag@youxel.com> | 0 | 0 | 0.5 | 2 | 2 - High | [5 empty] | Front End
| 247748 | Task | QC:: Automate Test Cases |  | Done | Galal Torkey <gtorkey@youxel.com> | 14 | 15 | 0 | 2 | [5 empty] | Test Automation | Testing
| 247748 | Bug | Search does not return user when typing the full exact name while creating a new conversation |  | Resolved | Galal Torkey <gtorkey@youxel.com> | 0 | 2 | 0 | 2 | 2 - High | [5 empty] | Development
| 244767 | Task | FE:: Jump to Message integration |  | Done | Alaa Ezzat <aezzat@youxel.com> | 4 | 4 | 0 | 2 | [5 empty] | Development | Front End
| 244767 | Task | FE:: Fetch Messages while Scrolling Up/Down |  | Done | Alaa Ezzat <aezzat@youxel.com> | 5 | 5 | 0 | 2 | [5 empty] | Development | Front End
| 244767 | Task | FE:: Handle Socket Updates in Anchor Mode |  | Done | Alaa Ezzat <aezzat@youxel.com> | 2 | 3 | 0 | 2 | [5 empty] | Development | Front End
| 244767 | Task | FE:: Start Point for anchor Mode |  | Done | Alaa Ezzat <aezzat@youxel.com> | 3 | 3 | 0 | 2 | [5 empty] | Development | Front End
| 244767 | Task | FE:: Verify common properties (notes) with anchor mode |  | Ready For Review | Alaa Ezzat <aezzat@youxel.com> | 4 | 3 | 1 | 2 | [5 empty] | Development | Front End
| 244767 | Task | FE:: Exit Anchor Mode When Sending Message to see pending messages |  | Done | Alaa Ezzat <aezzat@youxel.com> | 2 | 5 | 0 | 2 | [5 empty] | Development | Front End
| 244767 | Task | FE:: Update Has More Flags |  | Done | Alaa Ezzat <aezzat@youxel.com> | 4 | 4 | 0 | 2 |  |  |  |  | Ad-hoc | Development | Front End
| 244767 | Task | FE:: Anchor Mode Investigation |  | Done | Alaa Ezzat <aezzat@youxel.com> | 0 | 20.5 | 0 | 2 | [5 empty] | Development | Front End
| 244764 | Bug | Undo option disappears after switching to another conversation |  | On Hold | Alaa Ezzat <aezzat@youxel.com> | 0 | 0 | 0 | 3 | 2 - High | [5 empty] | Front End
| 244764 | Task | FE:: Add Undo Text button type |  | Done | Alaa Ezzat <aezzat@youxel.com> | 0.5 | 0.5 | 0 | 2 | [5 empty] | Development | Front End
| 244770 | Bug | Unread marker is displayed above a deleted message when marking the following message as unread |  | Closed | Galal Torkey <gtorkey@youxel.com> | 0 | 2 | 0 | 3 | 2 - High | [5 empty] | Development
| 244770 | Task | Fix::. Unread marker is displayed above a deleted message when marking the following message as unread |  | Done | Mahmoud Ibrahim Elfeqy <mfeqy@youxel.com> | 2 | 2 | 0 | 2 |  |  |  |  | Bug Fixing Actual Effort | Development | Development
| 242629 | Task | UX:: Limitations for Files Uploaded/ Voice Messages |  | Ready For Review | Shimaa Mohamed Elsayed <shhadad@youxel.com> | 2 | 2 | 0 | 2 | [5 empty] | Design | Design
| 242629 | Task | UI: Error: on image |  | Ready For Review | Shimaa Mohamed Elsayed <shhadad@youxel.com> | 2 | 2 | 0 | 2 | [5 empty] | Design | Design
| 242629 | Task | UI UX :: handle error case when open image first time |  | Ready For Review | Shimaa Mohamed Elsayed <shhadad@youxel.com> | 2 | 0.25 | 1.75 | 2 | [5 empty] | Design | Design
| 242629 | Task | UI/UX:: Show Case Multiple Files in Message Bubble |  | Done | Shimaa Mohamed Elsayed <shhadad@youxel.com> | 2 | 1 | 0 | 2 | [5 empty] | Design | Design
| 244768 | Task | UI/UX: Create popup for Access Denied when try to go to message |  | Done | Shimaa Mohamed Elsayed <shhadad@youxel.com> | 2 | 1 | 0 | 2 | [5 empty] | Design | Design
| 244768 | Task | FE:: Create Forward Popup UI |  | Ready For Review | Alaa Ezzat <aezzat@youxel.com> | 7 | 6 | 1 | 2 | [5 empty] | Development | Front End
| 244768 | Task | FE:: Forward Message Integration |  | In Development | Alaa Ezzat <aezzat@youxel.com> | 4 | 5 | 1 | 2 | [5 empty] | Development | Front End
| 244768 | Task | FE:: Use Forward-message-box in input-message and message-box |  | In Development | Alaa Ezzat <aezzat@youxel.com> | 3 | 0 | 3 | 2 | [5 empty] | Development | Front End
| 244768 | Task | FE:: Update Input-message with Forward Mode |  | Ready For Review | Alaa Ezzat <aezzat@youxel.com> | 2 | 1 | 1 | 2 | [5 empty] | Development | Front End
| 244768 | Task | FE:: Jump to Forwarded Message |  | In Development | Alaa Ezzat <aezzat@youxel.com> | 3 | 2 | 1 | 2 | [5 empty] | Development | Front End
| 244768 | Task | FE:: Create popup for Access Denied when try to go to message |  | In Development | Alaa Ezzat <aezzat@youxel.com> | 4 | 3 | 1 | 2 | [5 empty] | Development | Front End
| 244768 | Task | FE :: Use content display component in replay and forward component |  | Done | Alaa Ezzat <aezzat@youxel.com> | 2 | 2 | 0 | 2 | [5 empty] | Development | Front End
| 244768 | Task | FE:: Create Reusable Component select-users |  | Done | Alaa Ezzat <aezzat@youxel.com> | 3 | 3 | 0 | 2 |  |  |  |  | Ad-hoc | Development | Front End
| 244772 | Task | FE:: Go To selected Message |  | Done | Mohamed Mustafa Farrag <mfarrag@youxel.com> | 2 | 2 | 0 | 2 | [5 empty] | Development | Front End
| 244772 | Task | FE:: Update Message Box UI for the selected searched Message |  | Done | Mohamed Mustafa Farrag <mfarrag@youxel.com> | 2 | 2 | 0 | 2 | [5 empty] | Development | Front End
| 244756 | Task | FE :: Add edit group name popups |  | Done | Mohamed Mustafa Farrag <mfarrag@youxel.com> | 4 | 4 | 0 | 2 | [5 empty] | Development | Front End
| 244756 | Task | FE :: Integrate with api to change group name |  | Done | Mohamed Mustafa Farrag <mfarrag@youxel.com> | 4 | 4 | 0 | 2 | [5 empty] | Development | Front End
| 244756 | Task | FE:: Update Caching after changing group name |  | Done | Mohamed Mustafa Farrag <mfarrag@youxel.com> | 4 | 4 | 0 | 2 | [5 empty] | Development | Front End
| 244761 | Task | FE:: Voice Recorder Component Logic |  | Done | Mohamed Mustafa Farrag <mfarrag@youxel.com> | 7 | 7 | 0 | 2 |  |  |  |  | Communication Module (Messages) | Development | Front End
| 244761 | Task | FE:: Get voice from storage and show it in message box |  | Ready For Review | Mohamed Mustafa Farrag <mfarrag@youxel.com> | 6 | 0 | 6 | 2 |  |  |  |  | Communication Module (Messages) | Development | Front End
| 244761 | Task | FE :: Indicate users when someone is recording |  | Done | Mohamed Mustafa Farrag <mfarrag@youxel.com> | 3 | 3 | 0 | 2 | [5 empty] | Development | Front End
| 244761 | Task | BE :: Update Messages to Support Sending Voice Records |  | Done | Mahmoud Ibrahim Elfeqy <mfeqy@youxel.com> | 8 | 8 | 0 | 2 |  |  |  |  | Communication Module (Messages) | Development | Development
| 244761 | Task | BE :: Searching for the possibility of implementation FFmpeg |  | Done | Mahmoud Ibrahim Elfeqy <mfeqy@youxel.com> | 6 | 6 | 0 | 2 | [5 empty] | Development | Development
| 244761 | Task | BE :: Add Essential Ffmpeg binaries |  | Done | Mahmoud Ibrahim Elfeqy <mfeqy@youxel.com> | 10 | 10 | 0 | 2 |  |  |  |  | Ad-hoc | Development | Development
| 244757 | Task | FE:: Change Group image Integration |  | Ready For Review | Mohamed Mustafa Farrag <mfarrag@youxel.com> | 5 | 5 | 0 | 2 | [5 empty] | Development | Front End
| 244757 | Task | FE:: Update Cashing after change group image |  | New | Mohamed Mustafa Farrag <mfarrag@youxel.com> | 2 | 0 | 2 | 2 | [5 empty] | Development | Front End
| 244758 | Task | FE:: Remove Group Image integration |  | New | Mohamed Mustafa Farrag <mfarrag@youxel.com> | 4 | 0 | 4 | 2 | [5 empty] | Development | Front End
| 244758 | Task | FE:: Update Caching after remove group image |  | New | Mohamed Mustafa Farrag <mfarrag@youxel.com> | 2 | 0 | 2 | 2 | [5 empty] | Development | Front End
| 244758 | Task | FE:: Remove Popup UI |  | New | Mohamed Mustafa Farrag <mfarrag@youxel.com> | 4 | 0 | 4 | 2 | [5 empty] | Development | Front End
| 263534 | Task | Analyze Requirements & Videos |  | Done | Galal Torkey <gtorkey@youxel.com> | 7 | 10 | 0 | 2 | [5 empty] | Gather Requirements | Business
| 263534 | Task | Reviewing CheckNow System (new) |  | Done | Galal Torkey <gtorkey@youxel.com> | 7 | 7 | 0 | 2 | [5 empty] | Review | Business
| 263534 | Task | QC:: Analyze Requirements & Identify Business Gaps |  | Done | Galal Torkey <gtorkey@youxel.com> | 7 | 7 | 0 | 2 | [5 empty] | Documentation | Testing
| 263834 | Task | FE:: add organization identifier input field with custom validations |  | Done | Hussein Abdallah <habdallah@youxel.com> | 3 | 6.5 | 0 | 2 | [5 empty] | Development | Front End
| 263834 | Task | FE:: add identfier to url domain |  | Done | Hussein Abdallah <habdallah@youxel.com> | 3 | 3 | 0 | 2 | [5 empty] | Development | Front End
| 263834 | Task | FE:: updated changed apis |  | Done | Hussein Abdallah <habdallah@youxel.com> | 3 | 7 | 0 | 2 | [5 empty] | Development | Front End
| 263834 | Task | BE :: Add System Commponents to Host |  | Done | Mahmoud Adel Ali <madeel@youxel.com> | 2 | 2 | 0 | 2 | [5 empty] | Development | Development
| 264506 | Task | Add Flat Relations Table and Trigger |  | Done | Mahmoud Adel Ali <madeel@youxel.com> | 4 | 4 | 0 | 2 | [5 empty] | Development | Development
| 264506 | Task | Search Tree Table |  | Done | Mahmoud Adel Ali <madeel@youxel.com> | 7 | 7 | 0 | 2 | [5 empty] | Development | Development
| 247302 | Task | UI:: Organization Identifier |  | Done | Shimaa Mohamed Elsayed <shhadad@youxel.com> | 3 | 4 | 0 | 2 | [5 empty] | Design | Design
| 247302 | Task | QC:: Design Test Cases |  | Done | Galal Torkey <gtorkey@youxel.com> | 2 | 2 | 0 | 2 | [5 empty] | Write Test Cases | Testing
| 253676 | Task | Setup Finbuckle + Tenant Domain Models – Package integration, Organization entity, UserOrganization entity, EF configs & migration |  | Done | Mahmoud Adel Ali <madeel@youxel.com> | 8 | 8 | 0 | 2 | [5 empty] | Development | Development
| 253676 | Task | Tenant Resolution Strategies – Header-based, subdomain, path resolvers + ICurrentTenant accessor |  | Done | Mahmoud Adel Ali <madeel@youxel.com> | 8 | 8 | 0 | 2 | [5 empty] | Development | Development
| 253676 | Task | Tenant-Aware Seed Data – Seeder infrastructure, refactor existing seeds, org onboarding defaults |  | Done | Mahmoud Adel Ali <madeel@youxel.com> | 8 | 8 | 0 | 2 | [5 empty] | Development | Development
| 253676 | Task | Add Tenant Entity and New Host Context |  | Done | Mahmoud Adel Ali <madeel@youxel.com> | 8 | 6 | 0 | 2 |  |  |  |  | Ad-hoc | Development | Development
| 247303 | Task | QC:: Design Test Cases |  | Done | Galal Torkey <gtorkey@youxel.com> | 1 | 1 | 0 | 2 | [5 empty] | Write Test Cases | Testing
| 247304 | Task | QC:: Design Test Cases |  | Done | Galal Torkey <gtorkey@youxel.com> | 2 | 1 | 1 | 2 | [5 empty] | Write Test Cases | Testing
| 247305 | Task | QC:: Design Test Cases |  | Done | Galal Torkey <gtorkey@youxel.com> | 2 | 2 | 0 | 2 | [5 empty] | Write Test Cases | Testing
| 247306 | Task | QC:: Design Test Cases |  | Done | Galal Torkey <gtorkey@youxel.com> | 2 | 1 | 1 | 2 | [5 empty] | Write Test Cases | Testing
| 247322 | Task | QC:: Design Test Cases |  | Done | Galal Torkey <gtorkey@youxel.com> | 2 | 2 | 0 | 2 | [5 empty] | Write Test Cases | Testing
| 247321 | Task | QC:: Design Test Cases |  | Done | Galal Torkey <gtorkey@youxel.com> | 3 | 2 | 1 | 2 | [5 empty] | Write Test Cases | Testing
| 247324 | Task | QC:: Design Test Cases |  | Done | Galal Torkey <gtorkey@youxel.com> | 2 | 2 | 0 | 2 | [5 empty] | Write Test Cases | Testing
| 247323 | Task | QC:: Design Test Cases |  | Done | Galal Torkey <gtorkey@youxel.com> | 3 | 2 | 1 | 2 | [5 empty] | Write Test Cases | Testing
| 247308 | Task | QC:: Design Test Cases |  | Done | Galal Torkey <gtorkey@youxel.com> | 1 | 1 | 0 | 2 | [5 empty] | Write Test Cases | Testing
| 247315 | Task | UI: Loading, error handle, Saving Location Types |  | Ready For Review | Shimaa Mohamed Elsayed <shhadad@youxel.com> | 2 | 1 | 1 | 2 | [5 empty] | Design | Design
| 247313 | Task | QC:: Design Test Cases |  | Done | Galal Torkey <gtorkey@youxel.com> | 2 | 2 | 0 | 2 | [5 empty] | Write Test Cases | Testing
| 247314 | Task | QC:: Design Test Cases |  | Done | Galal Torkey <gtorkey@youxel.com> | 2 | 2 | 0 | 2 | [5 empty] | Write Test Cases | Testing
| 247316 | Task | QC:: Design Test Cases |  | Done | Galal Torkey <gtorkey@youxel.com> | 2 | 2 | 0 | 2 | [5 empty] | Write Test Cases | Testing
| 247312 | Task | UI: Revisit The UX of the Delete Dialog |  | Done | Shimaa Mohamed Elsayed <shhadad@youxel.com> | 1 | 0.52 | 0 | 2 | [5 empty] | Design | Design
| 247312 | Task | QC:: Design Test Cases |  | Done | Galal Torkey <gtorkey@youxel.com> | 2 | 2 | 0 | 2 | [5 empty] | Write Test Cases | Testing
| 247310 | Task | UI: Check this action to reflect it in location listing |  | Done | Shimaa Mohamed Elsayed <shhadad@youxel.com> | 3 | 4 | 0 | 2 | [5 empty] | Design | Design
| 247310 | Task | BE :: Activate-Deactivate Locations |  | Done | Mahmoud Adel Ali <madeel@youxel.com> | 4 | 4 | 0 | 2 | [5 empty] | Development | Development
| 247310 | Task | UI:: Update All tables: Active & Inactive Status |  | Done | Shimaa Mohamed Elsayed <shhadad@youxel.com> | 1.5 | 1.5 | 0 | 2 |  |  |  |  | Ad-hoc | Design | Design
| 247319 | Task | QC:: Design Test Cases |  | Done | Galal Torkey <gtorkey@youxel.com> | 1 | 1 | 0 | 2 | [5 empty] | Write Test Cases | Testing
| 247311 | Task | QC:: Design Test Cases |  | Done | Galal Torkey <gtorkey@youxel.com> | 2 | 2 | 0 | 2 | [5 empty] | Write Test Cases | Testing
| 252836 | Task | Design:: update kpi indicator table |  | Done | Shimaa Mohamed Elsayed <shhadad@youxel.com> | 3 | 3 | 0 | 2 |  |  |  |  | Ad-hoc | Design | Design
| 252836 | Task | BE:: fix kpi indicators list translation |  | Done | Mahmoud Adel Ali <madeel@youxel.com> | 4 | 4 | 0 | 2 | [5 empty] | Development | Development
| 252836 | Task | BE:: fix kpi indicator delete api |  | Done | Mahmoud Adel Ali <madeel@youxel.com> | 4 | 4 | 0 | 2 | [5 empty] | Development | Development
| 252836 | Task | BE :: Implement Activate and Deactivate Features |  | Done | Mahmoud Adel Ali <madeel@youxel.com> | 4 | 2 | 0 | 2 | [5 empty] | Development | Development
| 264492 | Task | FE:: Create routes and components - service -interfaces |  | Done | Hussein Abdallah <habdallah@youxel.com> | 4 | 4 | 0 | 2 | [5 empty] | Development | Front End
| 264492 | Task | FE:: create KPI criteria form Ui |  | Done | Hussein Abdallah <habdallah@youxel.com> | 5 | 5 | 0 | 2 | [5 empty] | Development | Front End
| 264492 | Task | FE:: KPI criteria integration |  | Done | Hussein Abdallah <habdallah@youxel.com> | 5 | 5 | 0 | 2 | [5 empty] | Development | Front End
| 264492 | Task | FE:: Weight form ui |  | Ready For Review | Hussein Abdallah <habdallah@youxel.com> | 4 | 4 | 0 | 2 | [5 empty] | Development | Front End
| 264492 | Task | FE:: Weight form integration |  | Ready For Review | Hussein Abdallah <habdallah@youxel.com> | 4 | 3.5 | 0.5 | 2 | [5 empty] | Development | Front End
| 264492 | Task | Design :: add responsive design |  | Done | Shimaa Mohamed Elsayed <shhadad@youxel.com> | 2 | 1 | 0 | 2 |  |  |  |  | MidSprint_Addition | Design | Design
| 264494 | Task | FE:: create kpi definision view page ui |  | Done | Hussein Abdallah <habdallah@youxel.com> | 4 | 4 | 0 | 2 | [5 empty] | Development | Front End
| 264494 | Task | FE:: kpi definistion view integration |  | Done | Hussein Abdallah <habdallah@youxel.com> | 4 | 4 | 0 | 2 | [5 empty] | Development | Front End
| 252825 | Task | UX/Ideate: SCENARIO 3: Creae user task |  | Done | Salma Sameh <ssameh@youxel.com> | 7 | 10.65 | 0 | 2 | [5 empty] | Design | Design
| 252825 | Task | UX/Ideate: SCENARIO 6: Working With Variables & Data |  | Done | Salma Sameh <ssameh@youxel.com> | 7 | 10 | 0 | 2 | [5 empty] | Design | Design
| 252825 | Task | UX/Ideate: SCENARIO 5: Creating routers (gateways) |  | Done | Salma Sameh <ssameh@youxel.com> | 7 | 8 | 0 | 2 | [5 empty] | Design | Design
| 252825 | Task | UX/Ideate: SCENARIO 4: Creating events |  | Done | Salma Sameh <ssameh@youxel.com> | 7 | 7 | 0 | 2 | [5 empty] | Design | Design
| 252825 | Task | UX/Wireframes: Node space |  | Done | Salma Sameh <ssameh@youxel.com> | 6 | 10 | 0 | 2 | [5 empty] | Design | Design
| 252825 | Task | UX/Ideate: SCENARIO 9: Editing & Scaling Existing Workflows |  | Done | Salma Sameh <ssameh@youxel.com> | 4 | 7.25 | 0 | 2 | [5 empty] | Design | Design
| 252825 | Task | UX/Ideate: SCENARIO 7: Testing the Workflow & Handle errors |  | Done | Salma Sameh <ssameh@youxel.com> | 7 | 7 | 0 | 2 | [5 empty] | Design | Design
| 252825 | Task | UX/Ideate: Finalize all builder wireframes |  | Done | Salma Sameh <ssameh@youxel.com> | 6 | 7 | 0 | 2 | [5 empty] | Design | Design
| 252825 | Task | UX: Plan for usability testing |  | Done | Salma Sameh <ssameh@youxel.com> | 7 | 7.5 | 0 | 2 |  |  |  |  | Recurring | Design | Design
| 252825 | Task | UX: Prep + structure UI phase |  | Done | Salma Sameh <ssameh@youxel.com> | 7 | 5.5 | 1.5 | 2 | [5 empty] | Design | Design
| 252825 | Task | UX/Define: Builder Information architecture |  | Done | Salma Sameh <ssameh@youxel.com> | 5 | 5 | 0 | 2 | [5 empty] | Design | Design
| 252825 | Task | UX/Define: Create user flows (start event & user task) |  | Done | Salma Sameh <ssameh@youxel.com> | 4 | 4 | 0 | 2 | [5 empty] | Design | Design
| 252825 | Task | UX: Create workflow user personas (hypothesis) |  | Done | Salma Sameh <ssameh@youxel.com> | 7 | 3 | 4 | 2 | [5 empty] | Design | Design
| 252825 | Task | BE :: Creat Workflows Project Template |  | Done | Mahmoud Adel Ali <madeel@youxel.com> | 5 | 5 | 0 | 2 | [5 empty] | Development | Development
| 252825 | Task | UX/Define: Document all builder wireframes results |  | Done | Salma Sameh <ssameh@youxel.com> | 4 | 4 | 0 | 2 | [5 empty] | Design | Design
| 252825 | Task | Feqy :: Study FormBuilder & Survey Implementation |  | Done | Mahmoud Ibrahim Elfeqy <mfeqy@youxel.com> | 7 | 7 | 0 | 2 |  |  |  |  | Ad-hoc | Development | Development
| 252825 | Task | BE :: Template Adjusment (Version & Multi-Tenant) |  | Done | Mahmoud Adel Ali <madeel@youxel.com> | 7 | 7 | 0 | 2 | [5 empty] | Development | Development
| 252825 | Task | BE :: Setup Vault Configuration in Base Template |  | Done | Mahmoud Adel Ali <madeel@youxel.com> | 7 | 7 | 0 | 2 | [5 empty] | Development | Development
| 252825 | Task | BE :: Create Workflow Base Entities |  | Done | Ahmed Talaat <atalaat@youxel.com> | 7 | 7 | 0 | 2 | [5 empty] | Development | Development
| 252825 | Task | BE :: Redis Function Investigation & Research |  | Done | Mahmoud Ibrahim Elfeqy <mfeqy@youxel.com> | 7 | 7 | 0 | 2 | [5 empty] | Development | Development
| 252825 | Task | BE :: Redis Function POC |  | Done | Mahmoud Ibrahim Elfeqy <mfeqy@youxel.com> | 7 | 7 | 0 | 2 | [5 empty] | Development | Development
| 252825 | Task | BE :: Configure Entities And Add Database Migrations |  | Done | Ahmed Talaat <atalaat@youxel.com> | 14 | 4 | 10 | 2 |  |  |  |  | Next Sprint | Development | Development
| 252825 | Task | BE :: Add Complete Node Types Reference Document |  | Done | Mahmoud Ibrahim Elfeqy <mfeqy@youxel.com> | 7 | 7 | 0 | 2 |  |  |  |  | Ad-hoc | Development | Development
| 252825 | Task | Edit "Complete Node Types Reference" Document on Notion |  | Done | Ahmed Talaat <atalaat@youxel.com> | 5 | 5 | 0 | 2 | [5 empty] | Development | Development
| 252825 | Task | Investigate Flowable Multi-Instance Output |  | Done | Mahmoud Adel Ali <madeel@youxel.com> | 7 | 7 | 0 | 2 | [5 empty] | Development | Development
| 252825 | Task | Investigate Camunda Multi-Instance Output |  | Done | Mahmoud Ibrahim Elfeqy <mfeqy@youxel.com> | 7 | 7 | 0 | 2 | [5 empty] | Development | Development
| 252825 | Task | Update Business Status to be on Nodes |  | Done | Mahmoud Ibrahim Elfeqy <mfeqy@youxel.com> | 3 | 3 | 0 | 2 | [5 empty] | Development | Development
| 252825 | Task | Investigate Removing Edges |  | Done | Mahmoud Adel Ali <madeel@youxel.com> | 7 | 7 | 0 | 2 | [5 empty] | Development | Development
| 252825 | Task | UI: Prepare the wireframes for the UI phase V2.2 |  | Done | Salma Sameh <ssameh@youxel.com> | 4 | 3 | 1 | 2 |  |  |  |  | Next Sprint | Design | Design
| 262102 | Task | API Requests integration with Playwright |  | New | Galal Torkey <gtorkey@youxel.com> | 5 | 5 | 0 | 2 | [5 empty] | Documentation | Testing
| 260487 | Task | CMMI Documentation Preparing |  | Done | Galal Torkey <gtorkey@youxel.com> | 2 | 0 | 2 | 2 | [5 empty] | Documentation | Testing
| 263833 | Task | Maryam: Stand ups and Meetings |  | Done | Mariam Mohamed Saeed <msaeed@youxel.com> | 0 | 7.08 | 0 | 2 | [5 empty] | Meetings | Design
| 263833 | Task | Salma: Meetings |  | Done | Salma Sameh <ssameh@youxel.com> | 0 | 11.02 | 0 | 2 | [5 empty] | Design | Design
| 263833 | Task | Talaat :: Stand-Ups, Meetings and Team Support |  | Done | Ahmed Talaat <atalaat@youxel.com> | 0 | 47 | 0 | 2 | [5 empty] | Development | Development
| 263833 | Task | Alhussien :: stand-up - meetings |  | Done | Hussein Abdallah <habdallah@youxel.com> | 0 | 22 | 0 | 2 | [5 empty] | Documentation | Front End
| 263833 | Task | Feqy :: Stand-Ups, Meetings and Team Support |  | Done | Mahmoud Ibrahim Elfeqy <mfeqy@youxel.com> | 0 | 21 | 0 | 2 | [5 empty] | Development | Development
| 263833 | Task | Galal::Meetings and Logs |  | Done | Galal Torkey <gtorkey@youxel.com> | 10 | 9 | 1 | 2 | [5 empty] | Meetings | Testing
| 263833 | Task | M Adel :: Stand-Ups, Meetings and Team Support |  | Done | Mahmoud Adel Ali <madeel@youxel.com> | 0 | 14 | 0 | 2 | [5 empty] | Development | Development
| 263833 | Task | Shaimaa:: Stand-ups, Meetings, Reviews and Team Support |  | Done | Shimaa Mohamed Elsayed <shhadad@youxel.com> | 0 | 13.67 | 0 | 2 | [5 empty] | Meetings | Design
| 263833 | Task | Alaa:: Meetings |  | Done | Alaa Ezzat <aezzat@youxel.com> | 0 | 16 | 0 | 2 | [5 empty] | Development | Front End
[7 empty] | 666 | 875.96 | 65.5
Tasks
EPIC | Parent | Work Item Type | Title | Story Points | State | Assigned To | Original Estimate | Completed Work | Remaining Work | Priority | Severity | Phase | Dev delivery date | QC Delivery date | Tags | Task Category | Activity
| 260177 | Task | Breadcrumb inputs/outputs |  | Done | Enas Diab <ediab@youxel.com> | 3 | 6 | 0 | 2 | [5 empty] | Development | Front End
| 260177 | Task | BreadCrumb-menu |  | Done | Enas Diab <ediab@youxel.com> | 5 | 4 | 1 | 2 | [5 empty] | Development | Front End
| 251892 | Task | Create Lottie Component Structure & inputs |  | Done | Hussein Abdallah <habdallah@youxel.com> | 2 | 2 | 0 | 2 |  |  |  |  | MidSprint_Addition | Development | Front End
| 251892 | Task | UI: Lottie Color |  | Done | Shimaa Mohamed Elsayed <shhadad@youxel.com> | 4 | 13.67 | 0 | 2 | [5 empty] | Design | Design
| 233816 | Task | UI:: Toggle Button |  | Done | Shimaa Mohamed Elsayed <shhadad@youxel.com> | 4 | 2.5 | 0 | 2 | [5 empty] | Design | Design
| 233934 | Task | FE :: Edit in galleria component in UI kit |  | Done | Hussein Abdallah <habdallah@youxel.com> | 3 | 3 | 0 | 2 | [5 empty] | Development | Front End
| 255495 | Task | FE:: Add action menu column to table |  | Done | Hussein Abdallah <habdallah@youxel.com> | 4 | 4 | 0 | 2 | [5 empty] | Development | Front End
| 255495 | Task | Design :: Unify status and tag components |  | Active | Mariam Mohamed Saeed <msaeed@youxel.com> | 5 | 4.4 | 0.6 | 2 | [5 empty] | Design | Design
| 250832 | Task | UI:: Contextual Button Component |  | Ready For Review | Shimaa Mohamed Elsayed <shhadad@youxel.com> | 5 | 5 | 0 | 2 | [5 empty] | Design | Design
| 250832 | Task | Design system: date and time documentation |  | Done | Mariam Mohamed Saeed <msaeed@youxel.com> | 3 | 7.67 | 0 | 2 | [5 empty] | Design | Design
| 250832 | Task | design systems: create date and time component |  | Done | Mariam Mohamed Saeed <msaeed@youxel.com> | 5 | 16.34 | 0 | 2 | [5 empty] | Design | Design
| 250832 | Task | UI:: DropDown/Checkboxes/Radio:: Add other option & Input |  | Done | Mariam Mohamed Saeed <msaeed@youxel.com> | 3 | 3.5 | 0 | 2 | [5 empty] | Design | Design
| 250832 | Task | Design system: typography |  | Done | Mariam Mohamed Saeed <msaeed@youxel.com> | 2 | 14.5 | 0 | 2 | [5 empty] | Design | Design
| 250832 | Task | UI:: Text Area:: Rich text editor |  | Done | Mariam Mohamed Saeed <msaeed@youxel.com> | 3 | 3.92 | 0 | 2 | [5 empty] | Design | Design
| 250832 | Task | Design system: Side Menu Documentation and add new variants |  | Done | Mariam Mohamed Saeed <msaeed@youxel.com> | 6 | 7.07 | 0 | 2 | [5 empty] | Design | Design
| 250832 | Task | UI:: Tree Select:: Documentation |  | Done | Mariam Mohamed Saeed <msaeed@youxel.com> | 4 | 6 | 0 | 2 | [5 empty] | Documentation | Design
| 250832 | Task | UI:: Tree Select:: Build Component |  | Done | Mariam Mohamed Saeed <msaeed@youxel.com> | 5 | 10.5 | 0 | 2 | [5 empty] | Design | Design
| 250832 | Task | UI:: Split button- Documentation |  | Done | Mariam Mohamed Saeed <msaeed@youxel.com> | 3 | 4.5 | 0 | 2 | [5 empty] | Documentation | Design
| 250832 | Task | UI:: Split button- Create Components |  | Ready For Review | Mariam Mohamed Saeed <msaeed@youxel.com> | 7 | 17 | 0 | 2 | [5 empty] | Design | Design
| 250832 | Task | UX:: Documentation Tabs / Tab Category |  | Done | Mariam Mohamed Saeed <msaeed@youxel.com> | 4 | 2 | 2 | 2 | [5 empty] | Documentation | Design
| 250832 | Task | UI:: Tabs Variants>> Survey |  | Done | Mariam Mohamed Saeed <msaeed@youxel.com> | 3 | 1.5 | 1.5 | 2 | [5 empty] | Design | Design
| 250832 | Task | Design system: pagination documentation |  | Ready For Review | Mariam Mohamed Saeed <msaeed@youxel.com> | 2 | 1.85 | 0.15 | 2 | [5 empty] | Design | Design
| 250832 | Task | Design system: spaces |  | New | Mariam Mohamed Saeed <msaeed@youxel.com> | 1 | 0 | 1 | 2 | [5 empty] | Design | Design
| 250832 | Task | Design system: recall text colors from semantics |  | New | Mariam Mohamed Saeed <msaeed@youxel.com> | 1 | 0 | 1 | 2 | [5 empty] | Design | Design
| 250832 | Task | UI:: Focus status For Inputs |  | New | Mariam Mohamed Saeed <msaeed@youxel.com> | 2 | 0 | 2 | 2 | [5 empty] | Design | Design
| 250832 | Task | UI: Progress icon shape |  | Done | Mariam Mohamed Saeed <msaeed@youxel.com> | 5 | 4 | 1 | 2 | [5 empty] | Design | Design
| 250832 | Task | UI:: File Upload/Multi Upload- Documentation |  | Ready For Review | Shimaa Mohamed Elsayed <shhadad@youxel.com> | 4 | 4 | 0 | 2 | [5 empty] | Documentation | Design
| 250832 | Task | UI:: File Upload/Multi Upload- View all component Variations |  | Ready For Review | Shimaa Mohamed Elsayed <shhadad@youxel.com> | 5 | 4 | 1 | 2 | [5 empty] | Design | Design
| 250832 | Task | UX:: Contextual Buttons Documentation |  | Ready For Review | Shimaa Mohamed Elsayed <shhadad@youxel.com> | 7 | 10.58 | 0 | 2 | [5 empty] | Documentation | Design
| 250832 | Task | UI:: File Upload Progress- Documentation |  | Ready For Review | Shimaa Mohamed Elsayed <shhadad@youxel.com> | 2 | 2 | 0 | 2 | [5 empty] | Documentation | Design
| 250832 | Task | UI:: File Upload Progress- View All Variations |  | Ready For Review | Shimaa Mohamed Elsayed <shhadad@youxel.com> | 3 | 5 | 0 | 2 | [5 empty] | Design | Design
| 250832 | Task | UI:: File Upload/ Single- Documentation |  | Ready For Review | Shimaa Mohamed Elsayed <shhadad@youxel.com> | 2 | 3.27 | 0 | 2 | [5 empty] | Design | Design
| 250832 | Task | UX:: Documentation:: Difference between Contextual Button / Link |  | Ready For Review | Shimaa Mohamed Elsayed <shhadad@youxel.com> | 3 | 4.25 | 0 | 2 | [5 empty] | Documentation | Design
| 242628 | Task | FE:: Seen Message Logic |  | Done | Enas Diab <ediab@youxel.com> | 4 | 4 | 0 | 2 |  |  |  |  | Next Sprint | Development | Front End
| 242628 | Task | FE:: Scroll to bottom and "New Messages" Button Cycle |  | Done | Alaa Ezzat <aezzat@youxel.com> | 4 | 4 | 0 | 2 |  |  |  |  | Ad-hoc | Development | Front End
| 242628 | Task | QC:: Automate Test Cases |  | Done | Galal Torkey <gtorkey@youxel.com> | 14 | 15 | 0 | 2 | [5 empty] | Test Automation | Testing
| 247747 | Task | UI:: Message Types Enhancement |  | Done | Shimaa Mohamed Elsayed <shhadad@youxel.com> | 2 | 1.5 | 0 | 2 |  |  |  |  | Ad-hoc | Design | Design
| 247748 | Task | QC:: Automate Test Cases |  | Done | Galal Torkey <gtorkey@youxel.com> | 14 | 15 | 0 | 2 | [5 empty] | Test Automation | Testing
| 244767 | Task | FE:: Jump to Message integration |  | Done | Alaa Ezzat <aezzat@youxel.com> | 4 | 4 | 0 | 2 | [5 empty] | Development | Front End
| 244767 | Task | FE:: Fetch Messages while Scrolling Up/Down |  | Done | Alaa Ezzat <aezzat@youxel.com> | 5 | 5 | 0 | 2 | [5 empty] | Development | Front End
| 244767 | Task | FE:: Handle Socket Updates in Anchor Mode |  | Done | Alaa Ezzat <aezzat@youxel.com> | 2 | 3 | 0 | 2 | [5 empty] | Development | Front End
| 244767 | Task | FE:: Start Point for anchor Mode |  | Done | Alaa Ezzat <aezzat@youxel.com> | 3 | 3 | 0 | 2 | [5 empty] | Development | Front End
| 244767 | Task | FE:: Verify common properties (notes) with anchor mode |  | Ready For Review | Alaa Ezzat <aezzat@youxel.com> | 4 | 3 | 1 | 2 | [5 empty] | Development | Front End
| 244767 | Task | FE:: Exit Anchor Mode When Sending Message to see pending messages |  | Done | Alaa Ezzat <aezzat@youxel.com> | 2 | 5 | 0 | 2 | [5 empty] | Development | Front End
| 244767 | Task | FE:: Update Has More Flags |  | Done | Alaa Ezzat <aezzat@youxel.com> | 4 | 4 | 0 | 2 |  |  |  |  | Ad-hoc | Development | Front End
| 244767 | Task | FE:: Anchor Mode Investigation |  | Done | Alaa Ezzat <aezzat@youxel.com> | 0 | 20.5 | 0 | 2 | [5 empty] | Development | Front End
| 244764 | Task | FE:: Add Undo Text button type |  | Done | Alaa Ezzat <aezzat@youxel.com> | 0.5 | 0.5 | 0 | 2 | [5 empty] | Development | Front End
| 244770 | Task | Fix::. Unread marker is displayed above a deleted message when marking the following message as unread |  | Done | Mahmoud Ibrahim Elfeqy <mfeqy@youxel.com> | 2 | 2 | 0 | 2 |  |  |  |  | Bug Fixing Actual Effort | Development | Development
| 242629 | Task | UX:: Limitations for Files Uploaded/ Voice Messages |  | Ready For Review | Shimaa Mohamed Elsayed <shhadad@youxel.com> | 2 | 2 | 0 | 2 | [5 empty] | Design | Design
| 242629 | Task | UI: Error: on image |  | Ready For Review | Shimaa Mohamed Elsayed <shhadad@youxel.com> | 2 | 2 | 0 | 2 | [5 empty] | Design | Design
| 242629 | Task | UI UX :: handle error case when open image first time |  | Ready For Review | Shimaa Mohamed Elsayed <shhadad@youxel.com> | 2 | 0.25 | 1.75 | 2 | [5 empty] | Design | Design
| 242629 | Task | UI/UX:: Show Case Multiple Files in Message Bubble |  | Done | Shimaa Mohamed Elsayed <shhadad@youxel.com> | 2 | 1 | 0 | 2 | [5 empty] | Design | Design
| 244768 | Task | UI/UX: Create popup for Access Denied when try to go to message |  | Done | Shimaa Mohamed Elsayed <shhadad@youxel.com> | 2 | 1 | 0 | 2 | [5 empty] | Design | Design
| 244768 | Task | FE:: Create Forward Popup UI |  | Ready For Review | Alaa Ezzat <aezzat@youxel.com> | 7 | 6 | 1 | 2 | [5 empty] | Development | Front End
| 244768 | Task | FE:: Forward Message Integration |  | In Development | Alaa Ezzat <aezzat@youxel.com> | 4 | 5 | 1 | 2 | [5 empty] | Development | Front End
| 244768 | Task | FE:: Use Forward-message-box in input-message and message-box |  | In Development | Alaa Ezzat <aezzat@youxel.com> | 3 | 0 | 3 | 2 | [5 empty] | Development | Front End
| 244768 | Task | FE:: Update Input-message with Forward Mode |  | Ready For Review | Alaa Ezzat <aezzat@youxel.com> | 2 | 1 | 1 | 2 | [5 empty] | Development | Front End
| 244768 | Task | FE:: Jump to Forwarded Message |  | In Development | Alaa Ezzat <aezzat@youxel.com> | 3 | 2 | 1 | 2 | [5 empty] | Development | Front End
| 244768 | Task | FE:: Create popup for Access Denied when try to go to message |  | In Development | Alaa Ezzat <aezzat@youxel.com> | 4 | 3 | 1 | 2 | [5 empty] | Development | Front End
| 244768 | Task | FE :: Use content display component in replay and forward component |  | Done | Alaa Ezzat <aezzat@youxel.com> | 2 | 2 | 0 | 2 | [5 empty] | Development | Front End
| 244768 | Task | FE:: Create Reusable Component select-users |  | Done | Alaa Ezzat <aezzat@youxel.com> | 3 | 3 | 0 | 2 |  |  |  |  | Ad-hoc | Development | Front End
| 244772 | Task | FE:: Go To selected Message |  | Done | Mohamed Mustafa Farrag <mfarrag@youxel.com> | 2 | 2 | 0 | 2 | [5 empty] | Development | Front End
| 244772 | Task | FE:: Update Message Box UI for the selected searched Message |  | Done | Mohamed Mustafa Farrag <mfarrag@youxel.com> | 2 | 2 | 0 | 2 | [5 empty] | Development | Front End
| 244756 | Task | FE :: Add edit group name popups |  | Done | Mohamed Mustafa Farrag <mfarrag@youxel.com> | 4 | 4 | 0 | 2 | [5 empty] | Development | Front End
| 244756 | Task | FE :: Integrate with api to change group name |  | Done | Mohamed Mustafa Farrag <mfarrag@youxel.com> | 4 | 4 | 0 | 2 | [5 empty] | Development | Front End
| 244756 | Task | FE:: Update Caching after changing group name |  | Done | Mohamed Mustafa Farrag <mfarrag@youxel.com> | 4 | 4 | 0 | 2 | [5 empty] | Development | Front End
| 244761 | Task | FE:: Voice Recorder Component Logic |  | Done | Mohamed Mustafa Farrag <mfarrag@youxel.com> | 7 | 7 | 0 | 2 |  |  |  |  | Communication Module (Messages) | Development | Front End
| 244761 | Task | FE:: Get voice from storage and show it in message box |  | Ready For Review | Mohamed Mustafa Farrag <mfarrag@youxel.com> | 6 | 0 | 6 | 2 |  |  |  |  | Communication Module (Messages) | Development | Front End
| 244761 | Task | FE :: Indicate users when someone is recording |  | Done | Mohamed Mustafa Farrag <mfarrag@youxel.com> | 3 | 3 | 0 | 2 | [5 empty] | Development | Front End
| 244761 | Task | BE :: Update Messages to Support Sending Voice Records |  | Done | Mahmoud Ibrahim Elfeqy <mfeqy@youxel.com> | 8 | 8 | 0 | 2 |  |  |  |  | Communication Module (Messages) | Development | Development
| 244761 | Task | BE :: Searching for the possibility of implementation FFmpeg |  | Done | Mahmoud Ibrahim Elfeqy <mfeqy@youxel.com> | 6 | 6 | 0 | 2 | [5 empty] | Development | Development
| 244761 | Task | BE :: Add Essential Ffmpeg binaries |  | Done | Mahmoud Ibrahim Elfeqy <mfeqy@youxel.com> | 10 | 10 | 0 | 2 |  |  |  |  | Ad-hoc | Development | Development
| 244757 | Task | FE:: Change Group image Integration |  | Ready For Review | Mohamed Mustafa Farrag <mfarrag@youxel.com> | 5 | 5 | 0 | 2 | [5 empty] | Development | Front End
| 244757 | Task | FE:: Update Cashing after change group image |  | New | Mohamed Mustafa Farrag <mfarrag@youxel.com> | 2 | 0 | 2 | 2 | [5 empty] | Development | Front End
| 244758 | Task | FE:: Remove Group Image integration |  | New | Mohamed Mustafa Farrag <mfarrag@youxel.com> | 4 | 0 | 4 | 2 | [5 empty] | Development | Front End
| 244758 | Task | FE:: Update Caching after remove group image |  | New | Mohamed Mustafa Farrag <mfarrag@youxel.com> | 2 | 0 | 2 | 2 | [5 empty] | Development | Front End
| 244758 | Task | FE:: Remove Popup UI |  | New | Mohamed Mustafa Farrag <mfarrag@youxel.com> | 4 | 0 | 4 | 2 | [5 empty] | Development | Front End
| 263534 | Task | Analyze Requirements & Videos |  | Done | Galal Torkey <gtorkey@youxel.com> | 7 | 10 | 0 | 2 | [5 empty] | Gather Requirements | Business
| 263534 | Task | Reviewing CheckNow System (new) |  | Done | Galal Torkey <gtorkey@youxel.com> | 7 | 7 | 0 | 2 | [5 empty] | Review | Business
| 263534 | Task | QC:: Analyze Requirements & Identify Business Gaps |  | Done | Galal Torkey <gtorkey@youxel.com> | 7 | 7 | 0 | 2 | [5 empty] | Documentation | Testing
| 263834 | Task | FE:: add organization identifier input field with custom validations |  | Done | Hussein Abdallah <habdallah@youxel.com> | 3 | 6.5 | 0 | 2 | [5 empty] | Development | Front End
| 263834 | Task | FE:: add identfier to url domain |  | Done | Hussein Abdallah <habdallah@youxel.com> | 3 | 3 | 0 | 2 | [5 empty] | Development | Front End
| 263834 | Task | FE:: updated changed apis |  | Done | Hussein Abdallah <habdallah@youxel.com> | 3 | 7 | 0 | 2 | [5 empty] | Development | Front End
| 263834 | Task | BE :: Add System Commponents to Host |  | Done | Mahmoud Adel Ali <madeel@youxel.com> | 2 | 2 | 0 | 2 | [5 empty] | Development | Development
| 264506 | Task | Add Flat Relations Table and Trigger |  | Done | Mahmoud Adel Ali <madeel@youxel.com> | 4 | 4 | 0 | 2 | [5 empty] | Development | Development
| 264506 | Task | Search Tree Table |  | Done | Mahmoud Adel Ali <madeel@youxel.com> | 7 | 7 | 0 | 2 | [5 empty] | Development | Development
| 247302 | Task | UI:: Organization Identifier |  | Done | Shimaa Mohamed Elsayed <shhadad@youxel.com> | 3 | 4 | 0 | 2 | [5 empty] | Design | Design
| 247302 | Task | QC:: Design Test Cases |  | Done | Galal Torkey <gtorkey@youxel.com> | 2 | 2 | 0 | 2 | [5 empty] | Write Test Cases | Testing
| 253676 | Task | Setup Finbuckle + Tenant Domain Models – Package integration, Organization entity, UserOrganization entity, EF configs & migration |  | Done | Mahmoud Adel Ali <madeel@youxel.com> | 8 | 8 | 0 | 2 | [5 empty] | Development | Development
| 253676 | Task | Tenant Resolution Strategies – Header-based, subdomain, path resolvers + ICurrentTenant accessor |  | Done | Mahmoud Adel Ali <madeel@youxel.com> | 8 | 8 | 0 | 2 | [5 empty] | Development | Development
| 253676 | Task | Tenant-Aware Seed Data – Seeder infrastructure, refactor existing seeds, org onboarding defaults |  | Done | Mahmoud Adel Ali <madeel@youxel.com> | 8 | 8 | 0 | 2 | [5 empty] | Development | Development
| 253676 | Task | Add Tenant Entity and New Host Context |  | Done | Mahmoud Adel Ali <madeel@youxel.com> | 8 | 6 | 0 | 2 |  |  |  |  | Ad-hoc | Development | Development
| 247303 | Task | QC:: Design Test Cases |  | Done | Galal Torkey <gtorkey@youxel.com> | 1 | 1 | 0 | 2 | [5 empty] | Write Test Cases | Testing
| 247304 | Task | QC:: Design Test Cases |  | Done | Galal Torkey <gtorkey@youxel.com> | 2 | 1 | 1 | 2 | [5 empty] | Write Test Cases | Testing
| 247305 | Task | QC:: Design Test Cases |  | Done | Galal Torkey <gtorkey@youxel.com> | 2 | 2 | 0 | 2 | [5 empty] | Write Test Cases | Testing
| 247306 | Task | QC:: Design Test Cases |  | Done | Galal Torkey <gtorkey@youxel.com> | 2 | 1 | 1 | 2 | [5 empty] | Write Test Cases | Testing
| 247322 | Task | QC:: Design Test Cases |  | Done | Galal Torkey <gtorkey@youxel.com> | 2 | 2 | 0 | 2 | [5 empty] | Write Test Cases | Testing
| 247321 | Task | QC:: Design Test Cases |  | Done | Galal Torkey <gtorkey@youxel.com> | 3 | 2 | 1 | 2 | [5 empty] | Write Test Cases | Testing
| 247324 | Task | QC:: Design Test Cases |  | Done | Galal Torkey <gtorkey@youxel.com> | 2 | 2 | 0 | 2 | [5 empty] | Write Test Cases | Testing
| 247323 | Task | QC:: Design Test Cases |  | Done | Galal Torkey <gtorkey@youxel.com> | 3 | 2 | 1 | 2 | [5 empty] | Write Test Cases | Testing
| 247308 | Task | QC:: Design Test Cases |  | Done | Galal Torkey <gtorkey@youxel.com> | 1 | 1 | 0 | 2 | [5 empty] | Write Test Cases | Testing
| 247315 | Task | UI: Loading, error handle, Saving Location Types |  | Ready For Review | Shimaa Mohamed Elsayed <shhadad@youxel.com> | 2 | 1 | 1 | 2 | [5 empty] | Design | Design
| 247313 | Task | QC:: Design Test Cases |  | Done | Galal Torkey <gtorkey@youxel.com> | 2 | 2 | 0 | 2 | [5 empty] | Write Test Cases | Testing
| 247314 | Task | QC:: Design Test Cases |  | Done | Galal Torkey <gtorkey@youxel.com> | 2 | 2 | 0 | 2 | [5 empty] | Write Test Cases | Testing
| 247316 | Task | QC:: Design Test Cases |  | Done | Galal Torkey <gtorkey@youxel.com> | 2 | 2 | 0 | 2 | [5 empty] | Write Test Cases | Testing
| 247312 | Task | UI: Revisit The UX of the Delete Dialog |  | Done | Shimaa Mohamed Elsayed <shhadad@youxel.com> | 1 | 0.52 | 0 | 2 | [5 empty] | Design | Design
| 247312 | Task | QC:: Design Test Cases |  | Done | Galal Torkey <gtorkey@youxel.com> | 2 | 2 | 0 | 2 | [5 empty] | Write Test Cases | Testing
| 247310 | Task | UI: Check this action to reflect it in location listing |  | Done | Shimaa Mohamed Elsayed <shhadad@youxel.com> | 3 | 4 | 0 | 2 | [5 empty] | Design | Design
| 247310 | Task | BE :: Activate-Deactivate Locations |  | Done | Mahmoud Adel Ali <madeel@youxel.com> | 4 | 4 | 0 | 2 | [5 empty] | Development | Development
| 247310 | Task | UI:: Update All tables: Active & Inactive Status |  | Done | Shimaa Mohamed Elsayed <shhadad@youxel.com> | 1.5 | 1.5 | 0 | 2 |  |  |  |  | Ad-hoc | Design | Design
| 247319 | Task | QC:: Design Test Cases |  | Done | Galal Torkey <gtorkey@youxel.com> | 1 | 1 | 0 | 2 | [5 empty] | Write Test Cases | Testing
| 247311 | Task | QC:: Design Test Cases |  | Done | Galal Torkey <gtorkey@youxel.com> | 2 | 2 | 0 | 2 | [5 empty] | Write Test Cases | Testing
| 252836 | Task | Design:: update kpi indicator table |  | Done | Shimaa Mohamed Elsayed <shhadad@youxel.com> | 3 | 3 | 0 | 2 |  |  |  |  | Ad-hoc | Design | Design
| 252836 | Task | BE:: fix kpi indicators list translation |  | Done | Mahmoud Adel Ali <madeel@youxel.com> | 4 | 4 | 0 | 2 | [5 empty] | Development | Development
| 252836 | Task | BE:: fix kpi indicator delete api |  | Done | Mahmoud Adel Ali <madeel@youxel.com> | 4 | 4 | 0 | 2 | [5 empty] | Development | Development
| 252836 | Task | BE :: Implement Activate and Deactivate Features |  | Done | Mahmoud Adel Ali <madeel@youxel.com> | 4 | 2 | 0 | 2 | [5 empty] | Development | Development
| 264492 | Task | FE:: Create routes and components - service -interfaces |  | Done | Hussein Abdallah <habdallah@youxel.com> | 4 | 4 | 0 | 2 | [5 empty] | Development | Front End
| 264492 | Task | FE:: create KPI criteria form Ui |  | Done | Hussein Abdallah <habdallah@youxel.com> | 5 | 5 | 0 | 2 | [5 empty] | Development | Front End
| 264492 | Task | FE:: KPI criteria integration |  | Done | Hussein Abdallah <habdallah@youxel.com> | 5 | 5 | 0 | 2 | [5 empty] | Development | Front End
| 264492 | Task | FE:: Weight form ui |  | Ready For Review | Hussein Abdallah <habdallah@youxel.com> | 4 | 4 | 0 | 2 | [5 empty] | Development | Front End
| 264492 | Task | FE:: Weight form integration |  | Ready For Review | Hussein Abdallah <habdallah@youxel.com> | 4 | 3.5 | 0.5 | 2 | [5 empty] | Development | Front End
| 264492 | Task | Design :: add responsive design |  | Done | Shimaa Mohamed Elsayed <shhadad@youxel.com> | 2 | 1 | 0 | 2 |  |  |  |  | MidSprint_Addition | Design | Design
| 264494 | Task | FE:: create kpi definision view page ui |  | Done | Hussein Abdallah <habdallah@youxel.com> | 4 | 4 | 0 | 2 | [5 empty] | Development | Front End
| 264494 | Task | FE:: kpi definistion view integration |  | Done | Hussein Abdallah <habdallah@youxel.com> | 4 | 4 | 0 | 2 | [5 empty] | Development | Front End
| 252825 | Task | UX/Ideate: SCENARIO 3: Creae user task |  | Done | Salma Sameh <ssameh@youxel.com> | 7 | 10.65 | 0 | 2 | [5 empty] | Design | Design
| 252825 | Task | UX/Ideate: SCENARIO 6: Working With Variables & Data |  | Done | Salma Sameh <ssameh@youxel.com> | 7 | 10 | 0 | 2 | [5 empty] | Design | Design
| 252825 | Task | UX/Ideate: SCENARIO 5: Creating routers (gateways) |  | Done | Salma Sameh <ssameh@youxel.com> | 7 | 8 | 0 | 2 | [5 empty] | Design | Design
| 252825 | Task | UX/Ideate: SCENARIO 4: Creating events |  | Done | Salma Sameh <ssameh@youxel.com> | 7 | 7 | 0 | 2 | [5 empty] | Design | Design
| 252825 | Task | UX/Wireframes: Node space |  | Done | Salma Sameh <ssameh@youxel.com> | 6 | 10 | 0 | 2 | [5 empty] | Design | Design
| 252825 | Task | UX/Ideate: SCENARIO 9: Editing & Scaling Existing Workflows |  | Done | Salma Sameh <ssameh@youxel.com> | 4 | 7.25 | 0 | 2 | [5 empty] | Design | Design
| 252825 | Task | UX/Ideate: SCENARIO 7: Testing the Workflow & Handle errors |  | Done | Salma Sameh <ssameh@youxel.com> | 7 | 7 | 0 | 2 | [5 empty] | Design | Design
| 252825 | Task | UX/Ideate: Finalize all builder wireframes |  | Done | Salma Sameh <ssameh@youxel.com> | 6 | 7 | 0 | 2 | [5 empty] | Design | Design
| 252825 | Task | UX: Plan for usability testing |  | Done | Salma Sameh <ssameh@youxel.com> | 7 | 7.5 | 0 | 2 |  |  |  |  | Recurring | Design | Design
| 252825 | Task | UX: Prep + structure UI phase |  | Done | Salma Sameh <ssameh@youxel.com> | 7 | 5.5 | 1.5 | 2 | [5 empty] | Design | Design
| 252825 | Task | UX/Define: Builder Information architecture |  | Done | Salma Sameh <ssameh@youxel.com> | 5 | 5 | 0 | 2 | [5 empty] | Design | Design
| 252825 | Task | UX/Define: Create user flows (start event & user task) |  | Done | Salma Sameh <ssameh@youxel.com> | 4 | 4 | 0 | 2 | [5 empty] | Design | Design
| 252825 | Task | UX: Create workflow user personas (hypothesis) |  | Done | Salma Sameh <ssameh@youxel.com> | 7 | 3 | 4 | 2 | [5 empty] | Design | Design
| 252825 | Task | BE :: Creat Workflows Project Template |  | Done | Mahmoud Adel Ali <madeel@youxel.com> | 5 | 5 | 0 | 2 | [5 empty] | Development | Development
| 252825 | Task | UX/Define: Document all builder wireframes results |  | Done | Salma Sameh <ssameh@youxel.com> | 4 | 4 | 0 | 2 | [5 empty] | Design | Design
| 252825 | Task | Feqy :: Study FormBuilder & Survey Implementation |  | Done | Mahmoud Ibrahim Elfeqy <mfeqy@youxel.com> | 7 | 7 | 0 | 2 |  |  |  |  | Ad-hoc | Development | Development
| 252825 | Task | BE :: Template Adjusment (Version & Multi-Tenant) |  | Done | Mahmoud Adel Ali <madeel@youxel.com> | 7 | 7 | 0 | 2 | [5 empty] | Development | Development
| 252825 | Task | BE :: Setup Vault Configuration in Base Template |  | Done | Mahmoud Adel Ali <madeel@youxel.com> | 7 | 7 | 0 | 2 | [5 empty] | Development | Development
| 252825 | Task | BE :: Create Workflow Base Entities |  | Done | Ahmed Talaat <atalaat@youxel.com> | 7 | 7 | 0 | 2 | [5 empty] | Development | Development
| 252825 | Task | BE :: Redis Function Investigation & Research |  | Done | Mahmoud Ibrahim Elfeqy <mfeqy@youxel.com> | 7 | 7 | 0 | 2 | [5 empty] | Development | Development
| 252825 | Task | BE :: Redis Function POC |  | Done | Mahmoud Ibrahim Elfeqy <mfeqy@youxel.com> | 7 | 7 | 0 | 2 | [5 empty] | Development | Development
| 252825 | Task | BE :: Configure Entities And Add Database Migrations |  | Done | Ahmed Talaat <atalaat@youxel.com> | 14 | 4 | 10 | 2 |  |  |  |  | Next Sprint | Development | Development
| 252825 | Task | BE :: Add Complete Node Types Reference Document |  | Done | Mahmoud Ibrahim Elfeqy <mfeqy@youxel.com> | 7 | 7 | 0 | 2 |  |  |  |  | Ad-hoc | Development | Development
| 252825 | Task | Edit "Complete Node Types Reference" Document on Notion |  | Done | Ahmed Talaat <atalaat@youxel.com> | 5 | 5 | 0 | 2 | [5 empty] | Development | Development
| 252825 | Task | Investigate Flowable Multi-Instance Output |  | Done | Mahmoud Adel Ali <madeel@youxel.com> | 7 | 7 | 0 | 2 | [5 empty] | Development | Development
| 252825 | Task | Investigate Camunda Multi-Instance Output |  | Done | Mahmoud Ibrahim Elfeqy <mfeqy@youxel.com> | 7 | 7 | 0 | 2 | [5 empty] | Development | Development
| 252825 | Task | Update Business Status to be on Nodes |  | Done | Mahmoud Ibrahim Elfeqy <mfeqy@youxel.com> | 3 | 3 | 0 | 2 | [5 empty] | Development | Development
| 252825 | Task | Investigate Removing Edges |  | Done | Mahmoud Adel Ali <madeel@youxel.com> | 7 | 7 | 0 | 2 | [5 empty] | Development | Development
| 252825 | Task | UI: Prepare the wireframes for the UI phase V2.2 |  | Done | Salma Sameh <ssameh@youxel.com> | 4 | 3 | 1 | 2 |  |  |  |  | Next Sprint | Design | Design
| 262102 | Task | API Requests integration with Playwright |  | New | Galal Torkey <gtorkey@youxel.com> | 5 | 5 | 0 | 2 | [5 empty] | Documentation | Testing
| 260487 | Task | CMMI Documentation Preparing |  | Done | Galal Torkey <gtorkey@youxel.com> | 2 | 0 | 2 | 2 | [5 empty] | Documentation | Testing
| 263833 | Task | Maryam: Stand ups and Meetings |  | Done | Mariam Mohamed Saeed <msaeed@youxel.com> | 0 | 7.08 | 0 | 2 | [5 empty] | Meetings | Design
| 263833 | Task | Salma: Meetings |  | Done | Salma Sameh <ssameh@youxel.com> | 0 | 11.02 | 0 | 2 | [5 empty] | Design | Design
| 263833 | Task | Talaat :: Stand-Ups, Meetings and Team Support |  | Done | Ahmed Talaat <atalaat@youxel.com> | 0 | 47 | 0 | 2 | [5 empty] | Development | Development
| 263833 | Task | Alhussien :: stand-up - meetings |  | Done | Hussein Abdallah <habdallah@youxel.com> | 0 | 22 | 0 | 2 | [5 empty] | Documentation | Front End
| 263833 | Task | Feqy :: Stand-Ups, Meetings and Team Support |  | Done | Mahmoud Ibrahim Elfeqy <mfeqy@youxel.com> | 0 | 21 | 0 | 2 | [5 empty] | Development | Development
| 263833 | Task | Galal::Meetings and Logs |  | Done | Galal Torkey <gtorkey@youxel.com> | 10 | 9 | 1 | 2 | [5 empty] | Meetings | Testing
| 263833 | Task | M Adel :: Stand-Ups, Meetings and Team Support |  | Done | Mahmoud Adel Ali <madeel@youxel.com> | 0 | 14 | 0 | 2 | [5 empty] | Development | Development
| 263833 | Task | Shaimaa:: Stand-ups, Meetings, Reviews and Team Support |  | Done | Shimaa Mohamed Elsayed <shhadad@youxel.com> | 0 | 13.67 | 0 | 2 | [5 empty] | Meetings | Design
| 263833 | Task | Alaa:: Meetings |  | Done | Alaa Ezzat <aezzat@youxel.com> | 0 | 16 | 0 | 2 | [5 empty] | Development | Front End
Bugs
EPIC | Parent | Work Item Type | Title | Story Points | State | Assigned To | Original Estimate | Completed Work | Remaining Work | Priority | Severity | Phase | Dev delivery date | QC Delivery date | Tags | Task Category | Activity
| 242628 | Bug | Typing indicator appears immediately upon opening a conversation without typing |  | Closed | Galal Torkey <gtorkey@youxel.com> | 0 | 0.5 | 0 | 3 | 2 - High | [5 empty] | Front End
| 242628 | Bug | Typing indicator is triggered when focusing and unfocusing the input field without typing |  | Closed | Galal Torkey <gtorkey@youxel.com> | 0 | 0 | 0 | 3 | 2 - High | [5 empty] | Front End
| 242628 | Bug | Typing indicator is displayed to the receiver after the sender successfully sends image attachments, even though no text input or typing action occurs. |  | Closed | Galal Torkey <gtorkey@youxel.com> | 0 | 0 | 0 | 3 | 2 - High | [5 empty] | Front End
| 242628 | Bug | New Messages Indicator does not appear when a new message is received in Full Screen Chat |  | Closed | Galal Torkey <gtorkey@youxel.com> | 0 | 0 | 0 | 3 | 4 - Low | [5 empty] | Front End
| 247747 | Bug | Conversation list does not show latest conversations after login until page refresh |  | New | Mohamed Mustafa Farrag <mfarrag@youxel.com> | 0 | 0 | 0.5 | 2 | 2 - High | [5 empty] | Front End
| 247748 | Bug | Search does not return user when typing the full exact name while creating a new conversation |  | Resolved | Galal Torkey <gtorkey@youxel.com> | 0 | 2 | 0 | 2 | 2 - High | [5 empty] | Development
| 244764 | Bug | Undo option disappears after switching to another conversation |  | On Hold | Alaa Ezzat <aezzat@youxel.com> | 0 | 0 | 0 | 3 | 2 - High | [5 empty] | Front End
| 244770 | Bug | Unread marker is displayed above a deleted message when marking the following message as unread |  | Closed | Galal Torkey <gtorkey@youxel.com> | 0 | 2 | 0 | 3 | 2 - High | [5 empty] | Development
DEV
EPIC | Parent | Work Item Type | Title | Story Points | State | Assigned To | Original Estimate | Completed Work | Remaining Work | Priority | Severity | Phase | Dev delivery date | QC Delivery date | Tags | Task Category | Activity
| 260177 | Task | Breadcrumb inputs/outputs |  | Done | Enas Diab <ediab@youxel.com> | 3 | 6 | 0 | 2 | [5 empty] | Development | Front End
| 260177 | Task | BreadCrumb-menu |  | Done | Enas Diab <ediab@youxel.com> | 5 | 4 | 1 | 2 | [5 empty] | Development | Front End
| 251892 | Task | Create Lottie Component Structure & inputs |  | Done | Hussein Abdallah <habdallah@youxel.com> | 2 | 2 | 0 | 2 |  |  |  |  | MidSprint_Addition | Development | Front End
| 251892 | Task | UI: Lottie Color |  | Done | Shimaa Mohamed Elsayed <shhadad@youxel.com> | 4 | 13.67 | 0 | 2 | [5 empty] | Design | Design
| 233816 | Task | UI:: Toggle Button |  | Done | Shimaa Mohamed Elsayed <shhadad@youxel.com> | 4 | 2.5 | 0 | 2 | [5 empty] | Design | Design
| 233934 | Task | FE :: Edit in galleria component in UI kit |  | Done | Hussein Abdallah <habdallah@youxel.com> | 3 | 3 | 0 | 2 | [5 empty] | Development | Front End
| 255495 | Task | FE:: Add action menu column to table |  | Done | Hussein Abdallah <habdallah@youxel.com> | 4 | 4 | 0 | 2 | [5 empty] | Development | Front End
| 255495 | Task | Design :: Unify status and tag components |  | Active | Mariam Mohamed Saeed <msaeed@youxel.com> | 5 | 4.4 | 0.6 | 2 | [5 empty] | Design | Design
| 250832 | Task | UI:: Contextual Button Component |  | Ready For Review | Shimaa Mohamed Elsayed <shhadad@youxel.com> | 5 | 5 | 0 | 2 | [5 empty] | Design | Design
| 250832 | Task | Design system: date and time documentation |  | Done | Mariam Mohamed Saeed <msaeed@youxel.com> | 3 | 7.67 | 0 | 2 | [5 empty] | Design | Design
| 250832 | Task | design systems: create date and time component |  | Done | Mariam Mohamed Saeed <msaeed@youxel.com> | 5 | 16.34 | 0 | 2 | [5 empty] | Design | Design
| 250832 | Task | UI:: DropDown/Checkboxes/Radio:: Add other option & Input |  | Done | Mariam Mohamed Saeed <msaeed@youxel.com> | 3 | 3.5 | 0 | 2 | [5 empty] | Design | Design
| 250832 | Task | Design system: typography |  | Done | Mariam Mohamed Saeed <msaeed@youxel.com> | 2 | 14.5 | 0 | 2 | [5 empty] | Design | Design
| 250832 | Task | UI:: Text Area:: Rich text editor |  | Done | Mariam Mohamed Saeed <msaeed@youxel.com> | 3 | 3.92 | 0 | 2 | [5 empty] | Design | Design
| 250832 | Task | Design system: Side Menu Documentation and add new variants |  | Done | Mariam Mohamed Saeed <msaeed@youxel.com> | 6 | 7.07 | 0 | 2 | [5 empty] | Design | Design
| 250832 | Task | UI:: Tree Select:: Documentation |  | Done | Mariam Mohamed Saeed <msaeed@youxel.com> | 4 | 6 | 0 | 2 | [5 empty] | Documentation | Design
| 250832 | Task | UI:: Tree Select:: Build Component |  | Done | Mariam Mohamed Saeed <msaeed@youxel.com> | 5 | 10.5 | 0 | 2 | [5 empty] | Design | Design
| 250832 | Task | UI:: Split button- Documentation |  | Done | Mariam Mohamed Saeed <msaeed@youxel.com> | 3 | 4.5 | 0 | 2 | [5 empty] | Documentation | Design
| 250832 | Task | UI:: Split button- Create Components |  | Ready For Review | Mariam Mohamed Saeed <msaeed@youxel.com> | 7 | 17 | 0 | 2 | [5 empty] | Design | Design
| 250832 | Task | UX:: Documentation Tabs / Tab Category |  | Done | Mariam Mohamed Saeed <msaeed@youxel.com> | 4 | 2 | 2 | 2 | [5 empty] | Documentation | Design
| 250832 | Task | UI:: Tabs Variants>> Survey |  | Done | Mariam Mohamed Saeed <msaeed@youxel.com> | 3 | 1.5 | 1.5 | 2 | [5 empty] | Design | Design
| 250832 | Task | Design system: pagination documentation |  | Ready For Review | Mariam Mohamed Saeed <msaeed@youxel.com> | 2 | 1.85 | 0.15 | 2 | [5 empty] | Design | Design
| 250832 | Task | Design system: spaces |  | New | Mariam Mohamed Saeed <msaeed@youxel.com> | 1 | 0 | 1 | 2 | [5 empty] | Design | Design
| 250832 | Task | Design system: recall text colors from semantics |  | New | Mariam Mohamed Saeed <msaeed@youxel.com> | 1 | 0 | 1 | 2 | [5 empty] | Design | Design
| 250832 | Task | UI:: Focus status For Inputs |  | New | Mariam Mohamed Saeed <msaeed@youxel.com> | 2 | 0 | 2 | 2 | [5 empty] | Design | Design
| 250832 | Task | UI: Progress icon shape |  | Done | Mariam Mohamed Saeed <msaeed@youxel.com> | 5 | 4 | 1 | 2 | [5 empty] | Design | Design
| 250832 | Task | UI:: File Upload/Multi Upload- Documentation |  | Ready For Review | Shimaa Mohamed Elsayed <shhadad@youxel.com> | 4 | 4 | 0 | 2 | [5 empty] | Documentation | Design
| 250832 | Task | UI:: File Upload/Multi Upload- View all component Variations |  | Ready For Review | Shimaa Mohamed Elsayed <shhadad@youxel.com> | 5 | 4 | 1 | 2 | [5 empty] | Design | Design
| 250832 | Task | UX:: Contextual Buttons Documentation |  | Ready For Review | Shimaa Mohamed Elsayed <shhadad@youxel.com> | 7 | 10.58 | 0 | 2 | [5 empty] | Documentation | Design
| 250832 | Task | UI:: File Upload Progress- Documentation |  | Ready For Review | Shimaa Mohamed Elsayed <shhadad@youxel.com> | 2 | 2 | 0 | 2 | [5 empty] | Documentation | Design
| 250832 | Task | UI:: File Upload Progress- View All Variations |  | Ready For Review | Shimaa Mohamed Elsayed <shhadad@youxel.com> | 3 | 5 | 0 | 2 | [5 empty] | Design | Design
| 250832 | Task | UI:: File Upload/ Single- Documentation |  | Ready For Review | Shimaa Mohamed Elsayed <shhadad@youxel.com> | 2 | 3.27 | 0 | 2 | [5 empty] | Design | Design
| 250832 | Task | UX:: Documentation:: Difference between Contextual Button / Link |  | Ready For Review | Shimaa Mohamed Elsayed <shhadad@youxel.com> | 3 | 4.25 | 0 | 2 | [5 empty] | Documentation | Design
| 242628 | Task | FE:: Seen Message Logic |  | Done | Enas Diab <ediab@youxel.com> | 4 | 4 | 0 | 2 |  |  |  |  | Next Sprint | Development | Front End
| 242628 | Task | FE:: Scroll to bottom and "New Messages" Button Cycle |  | Done | Alaa Ezzat <aezzat@youxel.com> | 4 | 4 | 0 | 2 |  |  |  |  | Ad-hoc | Development | Front End
| 247747 | Task | UI:: Message Types Enhancement |  | Done | Shimaa Mohamed Elsayed <shhadad@youxel.com> | 2 | 1.5 | 0 | 2 |  |  |  |  | Ad-hoc | Design | Design
| 247747 | Bug | Conversation list does not show latest conversations after login until page refresh |  | New | Mohamed Mustafa Farrag <mfarrag@youxel.com> | 0 | 0 | 0.5 | 2 | 2 - High | [5 empty] | Front End
| 244767 | Task | FE:: Jump to Message integration |  | Done | Alaa Ezzat <aezzat@youxel.com> | 4 | 4 | 0 | 2 | [5 empty] | Development | Front End
| 244767 | Task | FE:: Fetch Messages while Scrolling Up/Down |  | Done | Alaa Ezzat <aezzat@youxel.com> | 5 | 5 | 0 | 2 | [5 empty] | Development | Front End
| 244767 | Task | FE:: Handle Socket Updates in Anchor Mode |  | Done | Alaa Ezzat <aezzat@youxel.com> | 2 | 3 | 0 | 2 | [5 empty] | Development | Front End
| 244767 | Task | FE:: Start Point for anchor Mode |  | Done | Alaa Ezzat <aezzat@youxel.com> | 3 | 3 | 0 | 2 | [5 empty] | Development | Front End
| 244767 | Task | FE:: Verify common properties (notes) with anchor mode |  | Ready For Review | Alaa Ezzat <aezzat@youxel.com> | 4 | 3 | 1 | 2 | [5 empty] | Development | Front End
| 244767 | Task | FE:: Exit Anchor Mode When Sending Message to see pending messages |  | Done | Alaa Ezzat <aezzat@youxel.com> | 2 | 5 | 0 | 2 | [5 empty] | Development | Front End
| 244767 | Task | FE:: Update Has More Flags |  | Done | Alaa Ezzat <aezzat@youxel.com> | 4 | 4 | 0 | 2 |  |  |  |  | Ad-hoc | Development | Front End
| 244767 | Task | FE:: Anchor Mode Investigation |  | Done | Alaa Ezzat <aezzat@youxel.com> | 0 | 20.5 | 0 | 2 | [5 empty] | Development | Front End
| 244764 | Bug | Undo option disappears after switching to another conversation |  | On Hold | Alaa Ezzat <aezzat@youxel.com> | 0 | 0 | 0 | 3 | 2 - High | [5 empty] | Front End
| 244764 | Task | FE:: Add Undo Text button type |  | Done | Alaa Ezzat <aezzat@youxel.com> | 0.5 | 0.5 | 0 | 2 | [5 empty] | Development | Front End
| 244770 | Task | Fix::. Unread marker is displayed above a deleted message when marking the following message as unread |  | Done | Mahmoud Ibrahim Elfeqy <mfeqy@youxel.com> | 2 | 2 | 0 | 2 |  |  |  |  | Bug Fixing Actual Effort | Development | Development
| 242629 | Task | UX:: Limitations for Files Uploaded/ Voice Messages |  | Ready For Review | Shimaa Mohamed Elsayed <shhadad@youxel.com> | 2 | 2 | 0 | 2 | [5 empty] | Design | Design
| 242629 | Task | UI: Error: on image |  | Ready For Review | Shimaa Mohamed Elsayed <shhadad@youxel.com> | 2 | 2 | 0 | 2 | [5 empty] | Design | Design
| 242629 | Task | UI UX :: handle error case when open image first time |  | Ready For Review | Shimaa Mohamed Elsayed <shhadad@youxel.com> | 2 | 0.25 | 1.75 | 2 | [5 empty] | Design | Design
| 242629 | Task | UI/UX:: Show Case Multiple Files in Message Bubble |  | Done | Shimaa Mohamed Elsayed <shhadad@youxel.com> | 2 | 1 | 0 | 2 | [5 empty] | Design | Design
| 244768 | Task | UI/UX: Create popup for Access Denied when try to go to message |  | Done | Shimaa Mohamed Elsayed <shhadad@youxel.com> | 2 | 1 | 0 | 2 | [5 empty] | Design | Design
| 244768 | Task | FE:: Create Forward Popup UI |  | Ready For Review | Alaa Ezzat <aezzat@youxel.com> | 7 | 6 | 1 | 2 | [5 empty] | Development | Front End
| 244768 | Task | FE:: Forward Message Integration |  | In Development | Alaa Ezzat <aezzat@youxel.com> | 4 | 5 | 1 | 2 | [5 empty] | Development | Front End
| 244768 | Task | FE:: Use Forward-message-box in input-message and message-box |  | In Development | Alaa Ezzat <aezzat@youxel.com> | 3 | 0 | 3 | 2 | [5 empty] | Development | Front End
| 244768 | Task | FE:: Update Input-message with Forward Mode |  | Ready For Review | Alaa Ezzat <aezzat@youxel.com> | 2 | 1 | 1 | 2 | [5 empty] | Development | Front End
| 244768 | Task | FE:: Jump to Forwarded Message |  | In Development | Alaa Ezzat <aezzat@youxel.com> | 3 | 2 | 1 | 2 | [5 empty] | Development | Front End
| 244768 | Task | FE:: Create popup for Access Denied when try to go to message |  | In Development | Alaa Ezzat <aezzat@youxel.com> | 4 | 3 | 1 | 2 | [5 empty] | Development | Front End
| 244768 | Task | FE :: Use content display component in replay and forward component |  | Done | Alaa Ezzat <aezzat@youxel.com> | 2 | 2 | 0 | 2 | [5 empty] | Development | Front End
| 244768 | Task | FE:: Create Reusable Component select-users |  | Done | Alaa Ezzat <aezzat@youxel.com> | 3 | 3 | 0 | 2 |  |  |  |  | Ad-hoc | Development | Front End
| 244772 | Task | FE:: Go To selected Message |  | Done | Mohamed Mustafa Farrag <mfarrag@youxel.com> | 2 | 2 | 0 | 2 | [5 empty] | Development | Front End
| 244772 | Task | FE:: Update Message Box UI for the selected searched Message |  | Done | Mohamed Mustafa Farrag <mfarrag@youxel.com> | 2 | 2 | 0 | 2 | [5 empty] | Development | Front End
| 244756 | Task | FE :: Add edit group name popups |  | Done | Mohamed Mustafa Farrag <mfarrag@youxel.com> | 4 | 4 | 0 | 2 | [5 empty] | Development | Front End
| 244756 | Task | FE :: Integrate with api to change group name |  | Done | Mohamed Mustafa Farrag <mfarrag@youxel.com> | 4 | 4 | 0 | 2 | [5 empty] | Development | Front End
| 244756 | Task | FE:: Update Caching after changing group name |  | Done | Mohamed Mustafa Farrag <mfarrag@youxel.com> | 4 | 4 | 0 | 2 | [5 empty] | Development | Front End
| 244761 | Task | FE:: Voice Recorder Component Logic |  | Done | Mohamed Mustafa Farrag <mfarrag@youxel.com> | 7 | 7 | 0 | 2 |  |  |  |  | Communication Module (Messages) | Development | Front End
| 244761 | Task | FE:: Get voice from storage and show it in message box |  | Ready For Review | Mohamed Mustafa Farrag <mfarrag@youxel.com> | 6 | 0 | 6 | 2 |  |  |  |  | Communication Module (Messages) | Development | Front End
| 244761 | Task | FE :: Indicate users when someone is recording |  | Done | Mohamed Mustafa Farrag <mfarrag@youxel.com> | 3 | 3 | 0 | 2 | [5 empty] | Development | Front End
| 244761 | Task | BE :: Update Messages to Support Sending Voice Records |  | Done | Mahmoud Ibrahim Elfeqy <mfeqy@youxel.com> | 8 | 8 | 0 | 2 |  |  |  |  | Communication Module (Messages) | Development | Development
| 244761 | Task | BE :: Searching for the possibility of implementation FFmpeg |  | Done | Mahmoud Ibrahim Elfeqy <mfeqy@youxel.com> | 6 | 6 | 0 | 2 | [5 empty] | Development | Development
| 244761 | Task | BE :: Add Essential Ffmpeg binaries |  | Done | Mahmoud Ibrahim Elfeqy <mfeqy@youxel.com> | 10 | 10 | 0 | 2 |  |  |  |  | Ad-hoc | Development | Development
| 244757 | Task | FE:: Change Group image Integration |  | Ready For Review | Mohamed Mustafa Farrag <mfarrag@youxel.com> | 5 | 5 | 0 | 2 | [5 empty] | Development | Front End
| 244757 | Task | FE:: Update Cashing after change group image |  | New | Mohamed Mustafa Farrag <mfarrag@youxel.com> | 2 | 0 | 2 | 2 | [5 empty] | Development | Front End
| 244758 | Task | FE:: Remove Group Image integration |  | New | Mohamed Mustafa Farrag <mfarrag@youxel.com> | 4 | 0 | 4 | 2 | [5 empty] | Development | Front End
| 244758 | Task | FE:: Update Caching after remove group image |  | New | Mohamed Mustafa Farrag <mfarrag@youxel.com> | 2 | 0 | 2 | 2 | [5 empty] | Development | Front End
| 244758 | Task | FE:: Remove Popup UI |  | New | Mohamed Mustafa Farrag <mfarrag@youxel.com> | 4 | 0 | 4 | 2 | [5 empty] | Development | Front End
| 263834 | Task | FE:: add organization identifier input field with custom validations |  | Done | Hussein Abdallah <habdallah@youxel.com> | 3 | 6.5 | 0 | 2 | [5 empty] | Development | Front End
| 263834 | Task | FE:: add identfier to url domain |  | Done | Hussein Abdallah <habdallah@youxel.com> | 3 | 3 | 0 | 2 | [5 empty] | Development | Front End
| 263834 | Task | FE:: updated changed apis |  | Done | Hussein Abdallah <habdallah@youxel.com> | 3 | 7 | 0 | 2 | [5 empty] | Development | Front End
| 263834 | Task | BE :: Add System Commponents to Host |  | Done | Mahmoud Adel Ali <madeel@youxel.com> | 2 | 2 | 0 | 2 | [5 empty] | Development | Development
| 264506 | Task | Add Flat Relations Table and Trigger |  | Done | Mahmoud Adel Ali <madeel@youxel.com> | 4 | 4 | 0 | 2 | [5 empty] | Development | Development
| 264506 | Task | Search Tree Table |  | Done | Mahmoud Adel Ali <madeel@youxel.com> | 7 | 7 | 0 | 2 | [5 empty] | Development | Development
| 247302 | Task | UI:: Organization Identifier |  | Done | Shimaa Mohamed Elsayed <shhadad@youxel.com> | 3 | 4 | 0 | 2 | [5 empty] | Design | Design
| 253676 | Task | Setup Finbuckle + Tenant Domain Models – Package integration, Organization entity, UserOrganization entity, EF configs & migration |  | Done | Mahmoud Adel Ali <madeel@youxel.com> | 8 | 8 | 0 | 2 | [5 empty] | Development | Development
| 253676 | Task | Tenant Resolution Strategies – Header-based, subdomain, path resolvers + ICurrentTenant accessor |  | Done | Mahmoud Adel Ali <madeel@youxel.com> | 8 | 8 | 0 | 2 | [5 empty] | Development | Development
| 253676 | Task | Tenant-Aware Seed Data – Seeder infrastructure, refactor existing seeds, org onboarding defaults |  | Done | Mahmoud Adel Ali <madeel@youxel.com> | 8 | 8 | 0 | 2 | [5 empty] | Development | Development
| 253676 | Task | Add Tenant Entity and New Host Context |  | Done | Mahmoud Adel Ali <madeel@youxel.com> | 8 | 6 | 0 | 2 |  |  |  |  | Ad-hoc | Development | Development
| 247315 | Task | UI: Loading, error handle, Saving Location Types |  | Ready For Review | Shimaa Mohamed Elsayed <shhadad@youxel.com> | 2 | 1 | 1 | 2 | [5 empty] | Design | Design
| 247312 | Task | UI: Revisit The UX of the Delete Dialog |  | Done | Shimaa Mohamed Elsayed <shhadad@youxel.com> | 1 | 0.52 | 0 | 2 | [5 empty] | Design | Design
| 247310 | Task | UI: Check this action to reflect it in location listing |  | Done | Shimaa Mohamed Elsayed <shhadad@youxel.com> | 3 | 4 | 0 | 2 | [5 empty] | Design | Design
| 247310 | Task | BE :: Activate-Deactivate Locations |  | Done | Mahmoud Adel Ali <madeel@youxel.com> | 4 | 4 | 0 | 2 | [5 empty] | Development | Development
| 247310 | Task | UI:: Update All tables: Active & Inactive Status |  | Done | Shimaa Mohamed Elsayed <shhadad@youxel.com> | 1.5 | 1.5 | 0 | 2 |  |  |  |  | Ad-hoc | Design | Design
| 252836 | Task | Design:: update kpi indicator table |  | Done | Shimaa Mohamed Elsayed <shhadad@youxel.com> | 3 | 3 | 0 | 2 |  |  |  |  | Ad-hoc | Design | Design
| 252836 | Task | BE:: fix kpi indicators list translation |  | Done | Mahmoud Adel Ali <madeel@youxel.com> | 4 | 4 | 0 | 2 | [5 empty] | Development | Development
| 252836 | Task | BE:: fix kpi indicator delete api |  | Done | Mahmoud Adel Ali <madeel@youxel.com> | 4 | 4 | 0 | 2 | [5 empty] | Development | Development
| 252836 | Task | BE :: Implement Activate and Deactivate Features |  | Done | Mahmoud Adel Ali <madeel@youxel.com> | 4 | 2 | 0 | 2 | [5 empty] | Development | Development
| 264492 | Task | FE:: Create routes and components - service -interfaces |  | Done | Hussein Abdallah <habdallah@youxel.com> | 4 | 4 | 0 | 2 | [5 empty] | Development | Front End
| 264492 | Task | FE:: create KPI criteria form Ui |  | Done | Hussein Abdallah <habdallah@youxel.com> | 5 | 5 | 0 | 2 | [5 empty] | Development | Front End
| 264492 | Task | FE:: KPI criteria integration |  | Done | Hussein Abdallah <habdallah@youxel.com> | 5 | 5 | 0 | 2 | [5 empty] | Development | Front End
| 264492 | Task | FE:: Weight form ui |  | Ready For Review | Hussein Abdallah <habdallah@youxel.com> | 4 | 4 | 0 | 2 | [5 empty] | Development | Front End
| 264492 | Task | FE:: Weight form integration |  | Ready For Review | Hussein Abdallah <habdallah@youxel.com> | 4 | 3.5 | 0.5 | 2 | [5 empty] | Development | Front End
| 264492 | Task | Design :: add responsive design |  | Done | Shimaa Mohamed Elsayed <shhadad@youxel.com> | 2 | 1 | 0 | 2 |  |  |  |  | MidSprint_Addition | Design | Design
| 264494 | Task | FE:: create kpi definision view page ui |  | Done | Hussein Abdallah <habdallah@youxel.com> | 4 | 4 | 0 | 2 | [5 empty] | Development | Front End
| 264494 | Task | FE:: kpi definistion view integration |  | Done | Hussein Abdallah <habdallah@youxel.com> | 4 | 4 | 0 | 2 | [5 empty] | Development | Front End
| 252825 | Task | UX/Ideate: SCENARIO 3: Creae user task |  | Done | Salma Sameh <ssameh@youxel.com> | 7 | 10.65 | 0 | 2 | [5 empty] | Design | Design
| 252825 | Task | UX/Ideate: SCENARIO 6: Working With Variables & Data |  | Done | Salma Sameh <ssameh@youxel.com> | 7 | 10 | 0 | 2 | [5 empty] | Design | Design
| 252825 | Task | UX/Ideate: SCENARIO 5: Creating routers (gateways) |  | Done | Salma Sameh <ssameh@youxel.com> | 7 | 8 | 0 | 2 | [5 empty] | Design | Design
| 252825 | Task | UX/Ideate: SCENARIO 4: Creating events |  | Done | Salma Sameh <ssameh@youxel.com> | 7 | 7 | 0 | 2 | [5 empty] | Design | Design
| 252825 | Task | UX/Wireframes: Node space |  | Done | Salma Sameh <ssameh@youxel.com> | 6 | 10 | 0 | 2 | [5 empty] | Design | Design
| 252825 | Task | UX/Ideate: SCENARIO 9: Editing & Scaling Existing Workflows |  | Done | Salma Sameh <ssameh@youxel.com> | 4 | 7.25 | 0 | 2 | [5 empty] | Design | Design
| 252825 | Task | UX/Ideate: SCENARIO 7: Testing the Workflow & Handle errors |  | Done | Salma Sameh <ssameh@youxel.com> | 7 | 7 | 0 | 2 | [5 empty] | Design | Design
| 252825 | Task | UX/Ideate: Finalize all builder wireframes |  | Done | Salma Sameh <ssameh@youxel.com> | 6 | 7 | 0 | 2 | [5 empty] | Design | Design
| 252825 | Task | UX: Plan for usability testing |  | Done | Salma Sameh <ssameh@youxel.com> | 7 | 7.5 | 0 | 2 |  |  |  |  | Recurring | Design | Design
| 252825 | Task | UX: Prep + structure UI phase |  | Done | Salma Sameh <ssameh@youxel.com> | 7 | 5.5 | 1.5 | 2 | [5 empty] | Design | Design
| 252825 | Task | UX/Define: Builder Information architecture |  | Done | Salma Sameh <ssameh@youxel.com> | 5 | 5 | 0 | 2 | [5 empty] | Design | Design
| 252825 | Task | UX/Define: Create user flows (start event & user task) |  | Done | Salma Sameh <ssameh@youxel.com> | 4 | 4 | 0 | 2 | [5 empty] | Design | Design
| 252825 | Task | UX: Create workflow user personas (hypothesis) |  | Done | Salma Sameh <ssameh@youxel.com> | 7 | 3 | 4 | 2 | [5 empty] | Design | Design
| 252825 | Task | BE :: Creat Workflows Project Template |  | Done | Mahmoud Adel Ali <madeel@youxel.com> | 5 | 5 | 0 | 2 | [5 empty] | Development | Development
| 252825 | Task | UX/Define: Document all builder wireframes results |  | Done | Salma Sameh <ssameh@youxel.com> | 4 | 4 | 0 | 2 | [5 empty] | Design | Design
| 252825 | Task | Feqy :: Study FormBuilder & Survey Implementation |  | Done | Mahmoud Ibrahim Elfeqy <mfeqy@youxel.com> | 7 | 7 | 0 | 2 |  |  |  |  | Ad-hoc | Development | Development
| 252825 | Task | BE :: Template Adjusment (Version & Multi-Tenant) |  | Done | Mahmoud Adel Ali <madeel@youxel.com> | 7 | 7 | 0 | 2 | [5 empty] | Development | Development
| 252825 | Task | BE :: Setup Vault Configuration in Base Template |  | Done | Mahmoud Adel Ali <madeel@youxel.com> | 7 | 7 | 0 | 2 | [5 empty] | Development | Development
| 252825 | Task | BE :: Create Workflow Base Entities |  | Done | Ahmed Talaat <atalaat@youxel.com> | 7 | 7 | 0 | 2 | [5 empty] | Development | Development
| 252825 | Task | BE :: Redis Function Investigation & Research |  | Done | Mahmoud Ibrahim Elfeqy <mfeqy@youxel.com> | 7 | 7 | 0 | 2 | [5 empty] | Development | Development
| 252825 | Task | BE :: Redis Function POC |  | Done | Mahmoud Ibrahim Elfeqy <mfeqy@youxel.com> | 7 | 7 | 0 | 2 | [5 empty] | Development | Development
| 252825 | Task | BE :: Configure Entities And Add Database Migrations |  | Done | Ahmed Talaat <atalaat@youxel.com> | 14 | 4 | 10 | 2 |  |  |  |  | Next Sprint | Development | Development
| 252825 | Task | BE :: Add Complete Node Types Reference Document |  | Done | Mahmoud Ibrahim Elfeqy <mfeqy@youxel.com> | 7 | 7 | 0 | 2 |  |  |  |  | Ad-hoc | Development | Development
| 252825 | Task | Edit "Complete Node Types Reference" Document on Notion |  | Done | Ahmed Talaat <atalaat@youxel.com> | 5 | 5 | 0 | 2 | [5 empty] | Development | Development
| 252825 | Task | Investigate Flowable Multi-Instance Output |  | Done | Mahmoud Adel Ali <madeel@youxel.com> | 7 | 7 | 0 | 2 | [5 empty] | Development | Development
| 252825 | Task | Investigate Camunda Multi-Instance Output |  | Done | Mahmoud Ibrahim Elfeqy <mfeqy@youxel.com> | 7 | 7 | 0 | 2 | [5 empty] | Development | Development
| 252825 | Task | Update Business Status to be on Nodes |  | Done | Mahmoud Ibrahim Elfeqy <mfeqy@youxel.com> | 3 | 3 | 0 | 2 | [5 empty] | Development | Development
| 252825 | Task | Investigate Removing Edges |  | Done | Mahmoud Adel Ali <madeel@youxel.com> | 7 | 7 | 0 | 2 | [5 empty] | Development | Development
| 252825 | Task | UI: Prepare the wireframes for the UI phase V2.2 |  | Done | Salma Sameh <ssameh@youxel.com> | 4 | 3 | 1 | 2 |  |  |  |  | Next Sprint | Design | Design
| 263833 | Task | Maryam: Stand ups and Meetings |  | Done | Mariam Mohamed Saeed <msaeed@youxel.com> | 0 | 7.08 | 0 | 2 | [5 empty] | Meetings | Design
| 263833 | Task | Salma: Meetings |  | Done | Salma Sameh <ssameh@youxel.com> | 0 | 11.02 | 0 | 2 | [5 empty] | Design | Design
| 263833 | Task | Talaat :: Stand-Ups, Meetings and Team Support |  | Done | Ahmed Talaat <atalaat@youxel.com> | 0 | 47 | 0 | 2 | [5 empty] | Development | Development
| 263833 | Task | Alhussien :: stand-up - meetings |  | Done | Hussein Abdallah <habdallah@youxel.com> | 0 | 22 | 0 | 2 | [5 empty] | Documentation | Front End
| 263833 | Task | Feqy :: Stand-Ups, Meetings and Team Support |  | Done | Mahmoud Ibrahim Elfeqy <mfeqy@youxel.com> | 0 | 21 | 0 | 2 | [5 empty] | Development | Development
| 263833 | Task | M Adel :: Stand-Ups, Meetings and Team Support |  | Done | Mahmoud Adel Ali <madeel@youxel.com> | 0 | 14 | 0 | 2 | [5 empty] | Development | Development
| 263833 | Task | Shaimaa:: Stand-ups, Meetings, Reviews and Team Support |  | Done | Shimaa Mohamed Elsayed <shhadad@youxel.com> | 0 | 13.67 | 0 | 2 | [5 empty] | Meetings | Design
| 263833 | Task | Alaa:: Meetings |  | Done | Alaa Ezzat <aezzat@youxel.com> | 0 | 16 | 0 | 2 | [5 empty] | Development | Front End
[7 empty] | 569 | 776.46 | 58.5
TESTING
EPIC | Parent | Work Item Type | Title | Story Points | State | Assigned To | Original Estimate | Completed Work | Remaining Work | Priority | Severity | Phase | Dev delivery date | QC Delivery date | Tags | Task Category | Activity
| 242628 | Bug | Typing indicator appears immediately upon opening a conversation without typing |  | Closed | Galal Torkey <gtorkey@youxel.com> | 0 | 0.5 | 0 | 3 | 2 - High | [5 empty] | Front End
| 242628 | Bug | Typing indicator is triggered when focusing and unfocusing the input field without typing |  | Closed | Galal Torkey <gtorkey@youxel.com> | 0 | 0 | 0 | 3 | 2 - High | [5 empty] | Front End
| 242628 | Bug | Typing indicator is displayed to the receiver after the sender successfully sends image attachments, even though no text input or typing action occurs. |  | Closed | Galal Torkey <gtorkey@youxel.com> | 0 | 0 | 0 | 3 | 2 - High | [5 empty] | Front End
| 242628 | Bug | New Messages Indicator does not appear when a new message is received in Full Screen Chat |  | Closed | Galal Torkey <gtorkey@youxel.com> | 0 | 0 | 0 | 3 | 4 - Low | [5 empty] | Front End
| 242628 | Task | QC:: Automate Test Cases |  | Done | Galal Torkey <gtorkey@youxel.com> | 14 | 15 | 0 | 2 | [5 empty] | Test Automation | Testing
| 247748 | Task | QC:: Automate Test Cases |  | Done | Galal Torkey <gtorkey@youxel.com> | 14 | 15 | 0 | 2 | [5 empty] | Test Automation | Testing
| 247748 | Bug | Search does not return user when typing the full exact name while creating a new conversation |  | Resolved | Galal Torkey <gtorkey@youxel.com> | 0 | 2 | 0 | 2 | 2 - High | [5 empty] | Development
| 244770 | Bug | Unread marker is displayed above a deleted message when marking the following message as unread |  | Closed | Galal Torkey <gtorkey@youxel.com> | 0 | 2 | 0 | 3 | 2 - High | [5 empty] | Development
| 263534 | Task | Analyze Requirements & Videos |  | Done | Galal Torkey <gtorkey@youxel.com> | 7 | 10 | 0 | 2 | [5 empty] | Gather Requirements | Business
| 263534 | Task | Reviewing CheckNow System (new) |  | Done | Galal Torkey <gtorkey@youxel.com> | 7 | 7 | 0 | 2 | [5 empty] | Review | Business
| 263534 | Task | QC:: Analyze Requirements & Identify Business Gaps |  | Done | Galal Torkey <gtorkey@youxel.com> | 7 | 7 | 0 | 2 | [5 empty] | Documentation | Testing
| 247302 | Task | QC:: Design Test Cases |  | Done | Galal Torkey <gtorkey@youxel.com> | 2 | 2 | 0 | 2 | [5 empty] | Write Test Cases | Testing
| 247303 | Task | QC:: Design Test Cases |  | Done | Galal Torkey <gtorkey@youxel.com> | 1 | 1 | 0 | 2 | [5 empty] | Write Test Cases | Testing
| 247304 | Task | QC:: Design Test Cases |  | Done | Galal Torkey <gtorkey@youxel.com> | 2 | 1 | 1 | 2 | [5 empty] | Write Test Cases | Testing
| 247305 | Task | QC:: Design Test Cases |  | Done | Galal Torkey <gtorkey@youxel.com> | 2 | 2 | 0 | 2 | [5 empty] | Write Test Cases | Testing
| 247306 | Task | QC:: Design Test Cases |  | Done | Galal Torkey <gtorkey@youxel.com> | 2 | 1 | 1 | 2 | [5 empty] | Write Test Cases | Testing
| 247322 | Task | QC:: Design Test Cases |  | Done | Galal Torkey <gtorkey@youxel.com> | 2 | 2 | 0 | 2 | [5 empty] | Write Test Cases | Testing
| 247321 | Task | QC:: Design Test Cases |  | Done | Galal Torkey <gtorkey@youxel.com> | 3 | 2 | 1 | 2 | [5 empty] | Write Test Cases | Testing
| 247324 | Task | QC:: Design Test Cases |  | Done | Galal Torkey <gtorkey@youxel.com> | 2 | 2 | 0 | 2 | [5 empty] | Write Test Cases | Testing
| 247323 | Task | QC:: Design Test Cases |  | Done | Galal Torkey <gtorkey@youxel.com> | 3 | 2 | 1 | 2 | [5 empty] | Write Test Cases | Testing
| 247308 | Task | QC:: Design Test Cases |  | Done | Galal Torkey <gtorkey@youxel.com> | 1 | 1 | 0 | 2 | [5 empty] | Write Test Cases | Testing
| 247313 | Task | QC:: Design Test Cases |  | Done | Galal Torkey <gtorkey@youxel.com> | 2 | 2 | 0 | 2 | [5 empty] | Write Test Cases | Testing
| 247314 | Task | QC:: Design Test Cases |  | Done | Galal Torkey <gtorkey@youxel.com> | 2 | 2 | 0 | 2 | [5 empty] | Write Test Cases | Testing
| 247316 | Task | QC:: Design Test Cases |  | Done | Galal Torkey <gtorkey@youxel.com> | 2 | 2 | 0 | 2 | [5 empty] | Write Test Cases | Testing
| 247312 | Task | QC:: Design Test Cases |  | Done | Galal Torkey <gtorkey@youxel.com> | 2 | 2 | 0 | 2 | [5 empty] | Write Test Cases | Testing
| 247319 | Task | QC:: Design Test Cases |  | Done | Galal Torkey <gtorkey@youxel.com> | 1 | 1 | 0 | 2 | [5 empty] | Write Test Cases | Testing
| 247311 | Task | QC:: Design Test Cases |  | Done | Galal Torkey <gtorkey@youxel.com> | 2 | 2 | 0 | 2 | [5 empty] | Write Test Cases | Testing
| 262102 | Task | API Requests integration with Playwright |  | New | Galal Torkey <gtorkey@youxel.com> | 5 | 5 | 0 | 2 | [5 empty] | Documentation | Testing
| 260487 | Task | CMMI Documentation Preparing |  | Done | Galal Torkey <gtorkey@youxel.com> | 2 | 0 | 2 | 2 | [5 empty] | Documentation | Testing
| 263833 | Task | Galal::Meetings and Logs |  | Done | Galal Torkey <gtorkey@youxel.com> | 10 | 9 | 1 | 2 | [5 empty] | Meetings | Testing
[7 empty] | 97 | 99.5 | 7
Bug Fixing Actual Effort
EPIC | Parent | Work Item Type | Title | Story Points | State | Assigned To | Original Estimate | Completed Work | Remaining Work | Priority | Severity | Phase | Dev delivery date | QC Delivery date | Tags | Task Category | Activity
| 244770 | Task | Fix::. Unread marker is displayed above a deleted message when marking the following message as unread |  | Done | Mahmoud Ibrahim Elfeqy <mfeqy@youxel.com> | 2 | 2 | 0 | 2 |  |  |  |  | Bug Fixing Actual Effort | Development | Development

## Check Now 26.17 Analysis
Sprint Name: Check Now 26.17
Date: 25 JAN to 05 FEB
Item | Check Now 26.17
Escaped Bugs | 0
MidSprint_Addition | 2
Ad-hoc | 10
Planned SP | 57
Actual SP | 102
Estimated Development Effort | 569
Total Actual Development Effort | 776.46
Estimated Testing Effort | 97
Total Actual Testing Effort | 99.5
Bug Fixing Actual Effort | 2
Sum of Actual Hours | 875.96
Sum of Working Hours | 680
Measure | Description | Calculation | Frequency | Analysis
Completion rate | Measures the difference between the actual done story points VS. the Planned story points | Actual SP / Planned SP | Sprint | +90%
Effort estimation accuracy percentage | Total Planned Development hours / Total Actual Development Hours | Sum Total Planned hours/Total Actual Dev. Effort) | Sprint | 90% - till 120%
Project Rework Rate | Project Calculate man hours used in fixing the bugs returned from testing compared to the total actual dev. hours. | Bug Fixing Actual Effort /Total Actual Dev. Effort) *100 | Sprint | 0% – 10%
Escaped Bugs | defects that bypass one or more testing or quality assurance stages and are later post released | Number of bypass one or more testing or quality assurance stages | Sprint / release | 2% -15%
Utilization | This measure is related to the Actual effort VS. working hours | (Sum of Actual hours / Sum working hours) *100 | Sprint | (90%-100%
Effort Variance | Calculate the variance of the estimated dev. Hours compared to the total actual dev. hours. | ((Total Actual Dev. Effort - Estimated Dev. Effort)/ Estimated Dev. Effort )*100 | Sprint | 5 – 10%
Measure | Description | Formula | Value | Target Range | Status
Completion Rate | Measures the difference between the actual done story points vs. the planned story points | 102 / 57 | 179% | ≥ 90% | ⚠️ Over-commitment
Effort Estimation Accuracy % (Dev) | Planned development hours vs. actual development hours | 569 / 776 | 73.32% | 90% – 120% | ❌ Under-estimated
Project Rework Rate | Bug fixing effort compared to total actual development effort | (2 / 776) × 100 | 0.26% | 0% – 10% | ✅ Healthy
Escaped Bugs | Defects found after release | Count = 0 | 0 bugs | 2% – 15% | ⚠️ Below Expected*
Utilization | Actual effort vs. available working hours | (876 / 680) × 100 | 128.8% | 90% – 100% | ❌ Over-utilized
Effort Variance (Dev) | Variance between estimated and actual development effort | ((776 − 569) / 569) × 100 | 36.4% | 5% – 10% | ❌ High Variance
Row Labels | Sum of Original Estimate | Sum of Completed Work | Sum of Remaining Work
Ahmed Talaat <atalaat@youxel.com> | 26 | 63 | 10
Alaa Ezzat <aezzat@youxel.com> | 56.5 | 90 | 9
Enas Diab <ediab@youxel.com> | 12 | 14 | 1
Galal Torkey <gtorkey@youxel.com> | 97 | 99.5 | 7
Hussein Abdallah <habdallah@youxel.com> | 48 | 77 | 0.5
Mahmoud Adel Ali <madeel@youxel.com> | 94 | 104 | 0
Mahmoud Ibrahim Elfeqy <mfeqy@youxel.com> | 64 | 85 | 0
Mariam Mohamed Saeed <msaeed@youxel.com> | 64 | 111.83 | 9.25
Mohamed Mustafa Farrag <mfarrag@youxel.com> | 49 | 31 | 18.5
Salma Sameh <ssameh@youxel.com> | 89 | 109.92 | 6.5
Shimaa Mohamed Elsayed <shhadad@youxel.com> | 66.5 | 90.71 | 3.75
Grand Total | 666 | 875.96 | 65.5
Row Labels | Sum of Original Estimate | Sum of Completed Work | Sum of Remaining Work | Performance Rate | Capacity | Utilization Per Staff | [5 empty] | Row Labels | Performance Rate | Utilization Per Staff
Ahmed Talaat <atalaat@youxel.com> | 26 | 63 | 10 | 35.62% | 63 | 100% | [5 empty] | Ahmed Talaat <atalaat@youxel.com> | 35.62% | 100%
Alaa Ezzat <aezzat@youxel.com> | 56.5 | 90 | 9 | 57.07% | 63 | 142.9% | [5 empty] | Alaa Ezzat <aezzat@youxel.com> | 57.07% | 142.9%
Enas Diab <ediab@youxel.com> | 12 | 14 | 1 | 80% | 36 | 38.89% | [5 empty] | Enas Diab <ediab@youxel.com> | 80% | 38.89%
Galal Torkey <gtorkey@youxel.com> | 97 | 99.5 | 7 | 91.08% | 70 | 142.1% | [5 empty] | Galal Torkey <gtorkey@youxel.com> | 91.08% | 142.1%
Hussein Abdallah <habdallah@youxel.com> | 48 | 77 | 0.5 | 61.94% | 70 | 110% | [5 empty] | Hussein Abdallah <habdallah@youxel.com> | 61.94% | 110%
Mahmoud Adel Ali <madeel@youxel.com> | 94 | 104 | 0 | 90.38% | 56 | 185.7% | [5 empty] | Mahmoud Adel Ali <madeel@youxel.com> | 90.38% | 185.7%
Mahmoud Ibrahim Elfeqy <mfeqy@youxel.com> | 64 | 85 | 0 | 75.29% | 70 | 121.4% | [5 empty] | Mahmoud Ibrahim Elfeqy <mfeqy@youxel.com> | 75.29% | 121.4%
Mariam Mohamed Saeed <msaeed@youxel.com> | 64 | 111.83 | 9.25 | 52.86% | 70 | 159.8% | [5 empty] | Mariam Mohamed Saeed <msaeed@youxel.com> | 52.86% | 159.8%
Mohamed Mustafa Farrag <mfarrag@youxel.com> | 49 | 31 | 18.5 | 98.99% | 49 | 63.27% | [5 empty] | Mohamed Mustafa Farrag <mfarrag@youxel.com> | 98.99% | 63.27%
Salma Sameh <ssameh@youxel.com> | 89 | 109.92 | 6.5 | 76.45% | 70 | 157% | [5 empty] | Salma Sameh <ssameh@youxel.com> | 76.45% | 157%
Shimaa Mohamed Elsayed <shhadad@youxel.com> | 66.5 | 90.71 | 3.75 | 70.4% | 63 | 144% | [5 empty] | Shimaa Mohamed Elsayed <shhadad@youxel.com> | 70.4% | 144%
Grand Total | 666 | 875.96 | 65.5 | 70.74% | 680 | 128.8% | [5 empty] | Grand Total | 70.74% | 128.8%
Row Labels | Sum of Original Estimate | Sum of Completed Work | Sum of Remaining Work | Performance Rate | Capacity | Utilization Per Staff
Mariam Mohamed Saeed <msaeed@youxel.com> | 64 | 111.83 | 9.25 | 52.86% | 70 | 159.8%
Salma Sameh <ssameh@youxel.com> | 89 | 109.92 | 6.5 | 76.45% | 70 | 157%
Shimaa Mohamed Elsayed <shhadad@youxel.com> | 66.5 | 90.71 | 3.75 | 70.4% | 63 | 144%
Grand Total | 219.5 | 312.46 | 19.5 | 66.12% | 203 | 153.9%
Row Labels | Sum of Original Estimate | Sum of Completed Work | Sum of Remaining Work | Performance Rate | Capacity | Utilization Per Staff
Ahmed Talaat <atalaat@youxel.com> | 26 | 63 | 10 | 35.62% | 63 | 100%
Mahmoud Adel Ali <madeel@youxel.com> | 94 | 104 | 0 | 90.38% | 56 | 185.7%
Mahmoud Ibrahim Elfeqy <mfeqy@youxel.com> | 64 | 85 | 0 | 75.29% | 70 | 121.4%
Grand Total | 184 | 252 | 10 | 70.23% | 189 | 133.3% | [9 empty] | Resolved | Grand Total
4
Row Labels | Sum of Original Estimate | Sum of Completed Work | Sum of Remaining Work | Performance Rate | Capacity | Utilization Per Staff | [10 empty] | 20
Alaa Ezzat <aezzat@youxel.com> | 56.5 | 90 | 9 | 57.07% | 63 | 142.9% | [10 empty] | 3
Enas Diab <ediab@youxel.com> | 12 | 14 | 1 | 80% | 36 | 38.89% | [9 empty] | 1 | 30
Hussein Abdallah <habdallah@youxel.com> | 48 | 77 | 0.5 | 61.94% | 70 | 110% | [10 empty] | 14
Mohamed Mustafa Farrag <mfarrag@youxel.com> | 49 | 31 | 18.5 | 98.99% | 49 | 63.27% | [10 empty] | 17
Grand Total | 165.5 | 212 | 29 | 68.67% | 218 | 97.25% | [10 empty] | 11
19
Row Labels | Sum of Original Estimate | Sum of Completed Work | Sum of Remaining Work | Performance Rate | Capacity | Utilization Per Staff | [10 empty] | 14
Galal Torkey <gtorkey@youxel.com> | 97 | 99.5 | 7 | 91.08% | 70 | 142.1% | [10 empty] | 16
Grand Total | 97 | 99.5 | 7 | 91.08% | 70 | 142.1% | [10 empty] | 24
[16 empty] | 1 | 172
Team | Sum of Original Estimate | Sum of Completed Work | Sum of Remaining Work | Performance Rate | Capacity | Utilization Per Staff | [5 empty] | Team | Performance Rate | Utilization Per Staff
Design | 219.5 | 312.46 | 19.5 | 66.12% | 203 | 153.9% | [5 empty] | Design | 66.12% | 153.9%
Development | 184 | 252 | 10 | 70.23% | 189 | 133.3% | [5 empty] | Development | 70.23% | 133.3%
Front End | 165.5 | 212 | 29 | 68.67% | 218 | 97.25% | [5 empty] | Front End | 68.67% | 97.25%
Testing | 97 | 99.5 | 7 | 91.08% | 70 | 142.1% | [5 empty] | Testing | 91.08% | 142.1%
Grand Total | 666 | 875.96 | 65.5 | 70.74% | 680 | 128.8% | [5 empty] | Grand Total | 70.74% | 128.8%
Row Labels | Active | Closed | Done | In Development | In Review | New | On Hold | Ready For Review | Resolved | Grand Total | Done Tasks % | Row Labels | Grand Total | Done Tasks %
Ahmed Talaat <atalaat@youxel.com> |  |  | 4 | [6 empty] | 4 | 100% | Ahmed Talaat <atalaat@youxel.com> | 4 | 100%
Alaa Ezzat <aezzat@youxel.com> |  |  | 12 | 4 |  |  | 1 | 3 |  | 20 | 80% | Alaa Ezzat <aezzat@youxel.com> | 20 | 80%
Enas Diab <ediab@youxel.com> |  |  | 3 | [6 empty] | 3 | 100% | Enas Diab <ediab@youxel.com> | 3 | 100%
Galal Torkey <gtorkey@youxel.com> |  | 5 | 23 |  |  | 1 |  |  | 1 | 30 | 96.67% | Galal Torkey <gtorkey@youxel.com> | 30 | 96.67%
Hussein Abdallah <habdallah@youxel.com> |  |  | 12 |  |  |  |  | 2 |  | 14 | 100% | Hussein Abdallah <habdallah@youxel.com> | 14 | 100%
Mahmoud Adel Ali <madeel@youxel.com> |  |  | 17 | [6 empty] | 17 | 100% | Mahmoud Adel Ali <madeel@youxel.com> | 17 | 100%
Mahmoud Ibrahim Elfeqy <mfeqy@youxel.com> |  |  | 11 | [6 empty] | 11 | 100% | Mahmoud Ibrahim Elfeqy <mfeqy@youxel.com> | 11 | 100%
Mariam Mohamed Saeed <msaeed@youxel.com> | 1 |  | 13 |  |  | 3 |  | 2 |  | 19 | 78.95% | Mariam Mohamed Saeed <msaeed@youxel.com> | 19 | 78.95%
Mohamed Mustafa Farrag <mfarrag@youxel.com> |  |  | 7 |  |  | 5 |  | 2 |  | 14 | 64.29% | Mohamed Mustafa Farrag <mfarrag@youxel.com> | 14 | 64.29%
Salma Sameh <ssameh@youxel.com> |  |  | 16 | [6 empty] | 16 | 100% | Salma Sameh <ssameh@youxel.com> | 16 | 100%
Shimaa Mohamed Elsayed <shhadad@youxel.com> |  |  | 12 |  |  |  |  | 12 |  | 24 | 100% | Shimaa Mohamed Elsayed <shhadad@youxel.com> | 24 | 100%
Grand Total | 1 | 5 | 130 | 4 | 0 | 9 | 1 | 21 | 1 | 172 | 91.86% | Grand Total | 172 | 91.86%
Row Labels | Active | Closed | Done | In Development | In Review | New | On Hold | Ready For Review | Resolved | Grand Total | Done Tasks %
Mariam Mohamed Saeed <msaeed@youxel.com> | 1 | 0 | 13 | 0 | 0 | 3 | 0 | 2 | 0 | 19 | 78.95%
Salma Sameh <ssameh@youxel.com> | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 100%
Shimaa Mohamed Elsayed <shhadad@youxel.com> | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 12 | 0 | 24 | 100%
Grand Total | 1 | 0 | 41 | 0 | 0 | 3 | 0 | 14 | 0 | 59 | 93.22%
Row Labels | Active | Closed | Done | In Development | In Review | New | On Hold | Ready For Review | Resolved | Grand Total | Done Tasks %
Ahmed Talaat <atalaat@youxel.com> | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 100%
Mahmoud Adel Ali <madeel@youxel.com> | 0 | 0 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 100%
Mahmoud Ibrahim Elfeqy <mfeqy@youxel.com> | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 100%
Grand Total | 0 | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 100%
Row Labels | Active | Closed | Done | In Development | In Review | New | On Hold | Ready For Review | Resolved | Grand Total | Done Tasks %
Alaa Ezzat <aezzat@youxel.com> | 0 | 0 | 12 | 4 | 0 | 0 | 1 | 3 | 0 | 20 | 80%
Enas Diab <ediab@youxel.com> | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 100%
Hussein Abdallah <habdallah@youxel.com> | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 2 | 0 | 14 | 100%
Mohamed Mustafa Farrag <mfarrag@youxel.com> | 0 | 0 | 7 | 0 | 0 | 5 | 0 | 2 | 0 | 14 | 64.29%
Grand Total | 0 | 0 | 34 | 4 | 0 | 5 | 1 | 7 | 0 | 51 | 82.35%
Row Labels | Active | Closed | Done | In Development | In Review | New | On Hold | Ready For Review | Resolved | Grand Total | Done Tasks %
Galal Torkey <gtorkey@youxel.com> | 0 | 5 | 23 | 0 | 0 | 1 | 0 | 0 | 1 | 30 | 96.67%
Grand Total | 0 | 5 | 23 | 0 | 0 | 1 | 0 | 0 | 1 | 30 | 96.67%
Row Labels | Active | Closed | Done | In Development | In Review | New | On Hold | Ready For Review | Resolved | Grand Total | Done Tasks % | Row Labels | Grand Total | Done Tasks %
Design | 1 | 0 | 41 | 0 | 0 | 3 | 0 | 14 | 0 | 59 | 93.22% | Design | 59 | 93.22%
Development | 0 | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 100% | Development | 32 | 100%
Front End | 0 | 0 | 34 | 4 | 0 | 5 | 1 | 7 | 0 | 51 | 82.35% | Front End | 51 | 82.35%
Testing | 0 | 5 | 23 | 0 | 0 | 1 | 0 | 0 | 1 | 30 | 96.67% | Testing | 30 | 96.67%
Grand Total | 1 | 5 | 130 | 4 | 0 | 9 | 1 | 21 | 1 | 172 | 91.86% | Grand Total | 172 | 91.86%
MidSprint_Addition | [11 empty] | MidSprint_Addition
Team member | Team | MidSprint_Addition | Total Tasks | MidSprint_Addition % | [7 empty] | Team member | Team | MidSprint_Addition %
Ahmed Talaat <atalaat@youxel.com> | Development | 0 | 4 | 0% | from the same tag name | [6 empty] | Ahmed Talaat <atalaat@youxel.com> | Development | 0%
Alaa Ezzat <aezzat@youxel.com> | Frontend | 0 | 20 | 0% | [7 empty] | Alaa Ezzat <aezzat@youxel.com> | Frontend | 0%
Enas Diab <ediab@youxel.com> | Frontend | 0 | 3 | 0% | [7 empty] | Enas Diab <ediab@youxel.com> | Frontend | 0%
Galal Torkey <gtorkey@youxel.com> | Testing | 0 | 30 | 0% | [7 empty] | Galal Torkey <gtorkey@youxel.com> | Testing | 0%
Hussein Abdallah <habdallah@youxel.com> | Frontend | 1 | 14 | 7.143% | [7 empty] | Hussein Abdallah <habdallah@youxel.com> | Frontend | 7.143%
Mahmoud Adel Ali <madeel@youxel.com> | Development | 0 | 17 | 0% | [7 empty] | Mahmoud Adel Ali <madeel@youxel.com> | Development | 0%
Mahmoud Ibrahim Elfeqy <mfeqy@youxel.com> | Development | 0 | 11 | 0% | [7 empty] | Mahmoud Ibrahim Elfeqy <mfeqy@youxel.com> | Development | 0%
Mariam Mohamed Saeed <msaeed@youxel.com> | Design | 0 | 19 | 0% | [7 empty] | Mariam Mohamed Saeed <msaeed@youxel.com> | Design | 0%
Mohamed Mustafa Farrag <mfarrag@youxel.com> | Frontend | 0 | 14 | 0% | [7 empty] | Mohamed Mustafa Farrag <mfarrag@youxel.com> | Frontend | 0%
Salma Sameh <ssameh@youxel.com> | Design | 0 | 16 | 0% | [7 empty] | Salma Sameh <ssameh@youxel.com> | Design | 0%
Shimaa Mohamed Elsayed <shhadad@youxel.com> | Design | 1 | 24 | 4.167% | [7 empty] | Shimaa Mohamed Elsayed <shhadad@youxel.com> | Design | 4.167%
Grand Total |  | 2 | 172 | 1.163% | [7 empty] | Grand Total |  | 1.163%
MidSprint_Addition
Team member | Team | MidSprint_Addition | Total Tasks | MidSprint_Addition %
Mariam Mohamed Saeed <msaeed@youxel.com> | Design | 0 | 19 | 0%
Salma Sameh <ssameh@youxel.com> | Design | 0 | 16 | 0%
Shimaa Mohamed Elsayed <shhadad@youxel.com> | Design | 1 | 24 | 4.167%
Grand Total |  | 1 | 59 | 1.695%
MidSprint_Addition
Team member | Team | MidSprint_Addition | Total Tasks | MidSprint_Addition %
Ahmed Talaat <atalaat@youxel.com> | Development | 0 | 4 | 0%
Mahmoud Adel Ali <madeel@youxel.com> | Development | 0 | 17 | 0%
Mahmoud Ibrahim Elfeqy <mfeqy@youxel.com> | Development | 0 | 11 | 0%
Grand Total |  | 0 | 32 | 0%
MidSprint_Addition
Team member | Team | MidSprint_Addition | Total Tasks | MidSprint_Addition %
Alaa Ezzat <aezzat@youxel.com> | Frontend | 0 | 20 | 0%
Enas Diab <ediab@youxel.com> | Frontend | 0 | 3 | 0%
Hussein Abdallah <habdallah@youxel.com> | Frontend | 1 | 14 | 7.143%
Mohamed Mustafa Farrag <mfarrag@youxel.com> | Frontend | 0 | 14 | 0%
Grand Total |  | 1 | 51 | 1.961%
MidSprint_Addition
Team member | Team | MidSprint_Addition | Total Tasks | MidSprint_Addition %
Galal Torkey <gtorkey@youxel.com> | Testing | 0 | 30 | 0%
Grand Total |  | 0 | 30 | 0%
Team | MidSprint_Addition | Total Tasks | MidSprint_Addition % | [8 empty] | Team | MidSprint_Addition %
Design | 1 | 59 | 1.695% | [8 empty] | Design | 1.695%
Development | 0 | 32 | 0% | [8 empty] | Development | 0%
Front End | 1 | 51 | 1.961% | [8 empty] | Front End | 1.961%
Testing | 0 | 30 | 0% | [8 empty] | Testing | 0%
Grand Total | 2 | 172 | 1.163% | [8 empty] | Grand Total | 1.163%
Ad-hoc | [11 empty] | Ad-hoc
Team member | Team | Ad-hoc | Total Tasks | Ad-hoc % | [7 empty] | Team member | Team | Ad-hoc %
Ahmed Talaat <atalaat@youxel.com> | Development | 0 | 4 | 0% | from the same tag name | [6 empty] | Ahmed Talaat <atalaat@youxel.com> | Development | 0%
Alaa Ezzat <aezzat@youxel.com> | Frontend | 3 | 20 | 15% | [7 empty] | Alaa Ezzat <aezzat@youxel.com> | Frontend | 15%
Enas Diab <ediab@youxel.com> | Frontend | 0 | 3 | 0% | [7 empty] | Enas Diab <ediab@youxel.com> | Frontend | 0%
Galal Torkey <gtorkey@youxel.com> | Testing | 0 | 30 | 0% | [7 empty] | Galal Torkey <gtorkey@youxel.com> | Testing | 0%
Hussein Abdallah <habdallah@youxel.com> | Frontend | 0 | 14 | 0% | [7 empty] | Hussein Abdallah <habdallah@youxel.com> | Frontend | 0%
Mahmoud Adel Ali <madeel@youxel.com> | Development | 1 | 17 | 5.882% | [7 empty] | Mahmoud Adel Ali <madeel@youxel.com> | Development | 5.882%
Mahmoud Ibrahim Elfeqy <mfeqy@youxel.com> | Development | 3 | 11 | 27.27% | [7 empty] | Mahmoud Ibrahim Elfeqy <mfeqy@youxel.com> | Development | 27.27%
Mariam Mohamed Saeed <msaeed@youxel.com> | Design | 0 | 19 | 0% | [7 empty] | Mariam Mohamed Saeed <msaeed@youxel.com> | Design | 0%
Mohamed Mustafa Farrag <mfarrag@youxel.com> | Frontend | 0 | 14 | 0% | [7 empty] | Mohamed Mustafa Farrag <mfarrag@youxel.com> | Frontend | 0%
Salma Sameh <ssameh@youxel.com> | Design | 0 | 16 | 0% | [7 empty] | Salma Sameh <ssameh@youxel.com> | Design | 0%
Shimaa Mohamed Elsayed <shhadad@youxel.com> | Design | 3 | 24 | 12.5% | [7 empty] | Shimaa Mohamed Elsayed <shhadad@youxel.com> | Design | 12.5%
Grand Total |  | 10 | 172 | 5.814% | [7 empty] | Grand Total |  | 5.814%
MidSprint_Addition
Team member | Team | Ad-hoc | Total Tasks | Ad-hoc %
Mariam Mohamed Saeed <msaeed@youxel.com> | Design | 0 | 19 | 0%
Salma Sameh <ssameh@youxel.com> | Design | 0 | 16 | 0%
Shimaa Mohamed Elsayed <shhadad@youxel.com> | Design | 3 | 24 | 12.5%
Grand Total |  | 3 | 59 | 5.085%
MidSprint_Addition
Team member | Team | Ad-hoc | Total Tasks | Ad-hoc %
Ahmed Talaat <atalaat@youxel.com> | Development | 0 | 4 | 0%
Mahmoud Adel Ali <madeel@youxel.com> | Development | 1 | 17 | 5.882%
Mahmoud Ibrahim Elfeqy <mfeqy@youxel.com> | Development | 3 | 11 | 27.27%
Grand Total |  | 4 | 32 | 12.5%
MidSprint_Addition
Team member | Team | Ad-hoc | Total Tasks | Ad-hoc %
Alaa Ezzat <aezzat@youxel.com> | Frontend | 3 | 20 | 15%
Enas Diab <ediab@youxel.com> | Frontend | 0 | 3 | 0%
Hussein Abdallah <habdallah@youxel.com> | Frontend | 0 | 14 | 0%
Mohamed Mustafa Farrag <mfarrag@youxel.com> | Frontend | 0 | 14 | 0%
Grand Total |  | 3 | 51 | 5.882%
MidSprint_Addition
Team member | Team | Ad-hoc | Total Tasks | Ad-hoc %
Galal Torkey <gtorkey@youxel.com> | Testing | 0 | 30 | 0%
Grand Total |  | 0 | 30 | 0%
Team | Ad-hoc | Total Tasks | Ad-hoc % | [8 empty] | Team | Ad-hoc %
Design | 3 | 59 | 5.085% | [8 empty] | Design | 5.085%
Development | 4 | 32 | 12.5% | [8 empty] | Development | 12.5%
Front End | 3 | 51 | 5.882% | [8 empty] | Front End | 5.882%
Testing | 0 | 30 | 0% | [8 empty] | Testing | 0%
Grand Total | 10 | 172 | 5.814% | [8 empty] | Grand Total | 5.814%
CMMI Productivity | [14 empty] | CMMI Productivity
Team member | Team | Total Expected Working Hours per Sprint | Total official vacation | Total personal Days Off | Remaining Capacity | Total orignal estimation | Total working hours | Actual productivity | Productivity Index | [5 empty] | Team member | Team | Actual productivity | Productivity Index
Ahmed Talaat <atalaat@youxel.com> | Development | 70 | 0 | 1 | 63 | 26 | 63 | 1 | 2.4231 | [5 empty] | Ahmed Talaat <atalaat@youxel.com> | Development | 1 | 2.4231
Alaa Ezzat <aezzat@youxel.com> | Frontend | 70 | 0 | 1 | 63 | 56.5 | 90 | 1.4286 | 1.5929 | [5 empty] | Alaa Ezzat <aezzat@youxel.com> | Frontend | 1.4286 | 1.5929
Enas Diab <ediab@youxel.com> | Frontend | 40 | 0 | 1 | 36 | 12 | 14 | 0.38889 | 1.1667 | [5 empty] | Enas Diab <ediab@youxel.com> | Frontend | 0.38889 | 1.1667
Galal Torkey <gtorkey@youxel.com> | Testing | 70 | 0 | 0 | 70 | 97 | 99.5 | 1.4214 | 1.0258 | [5 empty] | Galal Torkey <gtorkey@youxel.com> | Testing | 1.4214 | 1.0258
Hussein Abdallah <habdallah@youxel.com> | Frontend | 70 | 0 | 0 | 70 | 48 | 77 | 1.1 | 1.6042 | [5 empty] | Hussein Abdallah <habdallah@youxel.com> | Frontend | 1.1 | 1.6042
Mahmoud Adel Ali <madeel@youxel.com> | Development | 70 | 0 | 2 | 56 | 94 | 104 | 1.8571 | 1.1064 | [5 empty] | Mahmoud Adel Ali <madeel@youxel.com> | Development | 1.8571 | 1.1064
Mahmoud Ibrahim Elfeqy <mfeqy@youxel.com> | Development | 70 | 0 | 0 | 70 | 64 | 85 | 1.2143 | 1.3281 | [5 empty] | Mahmoud Ibrahim Elfeqy <mfeqy@youxel.com> | Development | 1.2143 | 1.3281
Mariam Mohamed Saeed <msaeed@youxel.com> | Design | 70 | 0 | 0 | 70 | 64 | 111.83 | 1.5976 | 1.7473 | [5 empty] | Mariam Mohamed Saeed <msaeed@youxel.com> | Design | 1.5976 | 1.7473
Mohamed Mustafa Farrag <mfarrag@youxel.com> | Frontend | 70 | 0 | 3 | 49 | 49 | 31 | 0.63265 | 0.63265 | [5 empty] | Mohamed Mustafa Farrag <mfarrag@youxel.com> | Frontend | 0.63265 | 0.63265
Salma Sameh <ssameh@youxel.com> | Design | 70 | 0 | 0 | 70 | 89 | 109.92 | 1.5703 | 1.2351 | [5 empty] | Salma Sameh <ssameh@youxel.com> | Design | 1.5703 | 1.2351
Shimaa Mohamed Elsayed <shhadad@youxel.com> | Design | 70 | 0 | 1 | 63 | 66.5 | 90.71 | 1.4398 | 1.3641 | [5 empty] | Shimaa Mohamed Elsayed <shhadad@youxel.com> | Design | 1.4398 | 1.3641
Grand Total |  | 740 | 0 | 9 | 680 | 666 | 875.96 | 1.2882 | 1.3153 | [5 empty] | Grand Total |  | 1.2882 | 1.3153
CMMI Productivity
Team member | Team | Total Expected Working Hours per Sprint | Total official vacation | Total personal Days Off | Remaining Capacity | Total orignal estimation | Total working hours | Actual productivity | Productivity Index
Mariam Mohamed Saeed <msaeed@youxel.com> | Design | 70 | 0 | 0 | 70 | 64 | 111.83 | 1.5976 | 1.7473
Salma Sameh <ssameh@youxel.com> | Design | 70 | 0 | 0 | 70 | 89 | 109.92 | 1.5703 | 1.2351
Shimaa Mohamed Elsayed <shhadad@youxel.com> | Design | 70 | 0 | 1 | 63 | 66.5 | 90.71 | 1.4398 | 1.3641
Grand Total |  | 210 | 0 | 1 | 203 | 219.5 | 312.46 | 1.5392 | 1.4235
CMMI Productivity
Team member | Team | Total Expected Working Hours per Sprint | Total official vacation | Total personal Days Off | Remaining Capacity | Total orignal estimation | Total working hours | Actual productivity | Productivity Index
Ahmed Talaat <atalaat@youxel.com> | Development | 70 | 0 | 1 | 63 | 26 | 63 | 1 | 2.4231
Mahmoud Adel Ali <madeel@youxel.com> | Development | 70 | 0 | 2 | 56 | 94 | 104 | 1.8571 | 1.1064
Mahmoud Ibrahim Elfeqy <mfeqy@youxel.com> | Development | 70 | 0 | 0 | 70 | 64 | 85 | 1.2143 | 1.3281
Grand Total |  | 210 | 0 | 3 | 189 | 184 | 252 | 1.3333 | 1.3696
CMMI Productivity
Team member | Team | Total Expected Working Hours per Sprint | Total official vacation | Total personal Days Off | Remaining Capacity | Total orignal estimation | Total working hours | Actual productivity | Productivity Index
Alaa Ezzat <aezzat@youxel.com> | Frontend | 70 | 0 | 1 | 63 | 56.5 | 90 | 1.4286 | 1.5929
Enas Diab <ediab@youxel.com> | Frontend | 40 | 0 | 1 | 36 | 12 | 14 | 0.38889 | 1.1667
Mohamed Mustafa Farrag <mfarrag@youxel.com> | Frontend | 70 | 0 | 3 | 49 | 49 | 31 | 0.63265 | 0.63265
Grand Total |  | 180 | 0 | 5 | 148 | 117.5 | 135 | 0.91216 | 1.1489
CMMI Productivity
Team member | Team | Total Expected Working Hours per Sprint | Total official vacation | Total personal Days Off | Remaining Capacity | Total orignal estimation | Total working hours | Actual productivity | Productivity Index
Galal Torkey <gtorkey@youxel.com> | Testing | 70 | 0 | 0 | 70 | 97 | 99.5 | 1.4214 | 1.0258
Grand Total |  | 70 | 0 | 0 | 70 | 97 | 99.5 | 1.4214 | 1.0258

## CMMI Template
Measure | Description | Calculation | Frequency | Target Range | Check Now 25.9 | Check Now 25.10 | Check Now 25.11 | Check Now 25.12 | Check Now 25.13 | Check Now 25.14 | Check Now 26.15 | Check Now 26.16 | Check Now 26.17
Completion rate | Measures the difference between the actual done story points VS. the Planned story points | Actual SP / Planned SP | Sprint | +90% | 35.6% | 31.96% | 58.41% | 58.06% | 54.93% | 29.84% | 112.3% | 72.13% | 179%
Effort estimation accuracy percentage | Total Planned Development hours / Total Actual Development Hours | Sum Total Planned hours/Total Actual Dev. Effort) | Sprint | 90% - till 120% | 128.5% | 119.3% | 116.3% | 96.82% | 79.74% | 99.29% | 76.9% | 84.53% | 73.32%
Project Rework Rate | Project Calculate man hours used in fixing the bugs returned from testing compared to the total actual dev. hours. | Bug Fixing Actual Effort /Total Actual Dev. Effort) *100 | Sprint | 0% – 10% | 0% | 0% | 0% | 0% | 0% | 0% | 2.26% | 0.92% | 0.26%
Escaped Bugs | defects that bypass one or more testing or quality assurance stages and are later post released | Number of bypass one or more testing or quality assurance stages | Sprint / release | 2% -15% | 0 bugs | 0 bugs | 0 bugs | 0 bugs | 0 bugs | 0 bugs | 0 bugs | 0 bugs | 0 bugs
utilization | This measure is related to the Actual effort VS. working hours | (Sum of Actual hours / Sum working hours) *100 | Sprint | (90%-100% | 83.5% | 131.9% | 129% | 118% | 123.2% | 132.5% | 105.9% | 118.6% | 128.8%
Dev. Effort Variance | Calculate the variance of the estimated dev. Hours compared to the total actual dev. hours. | ((Total Actual Dev. Effort - Estimated Dev. Effort)/ Estimated Dev. Effort )*100 | Sprint | 5 – 10% | −22.2% | −16.20% | −14.05% | 3.28% | 25.4% | 0.72% | 30.04% | 18.28% | 36.4%

## CMMI Productivity
Sprint Name: Check Now 26.17
Date: 25 JAN to 05 FEB
CMMI Productivity
Team member | Team | Total Expected Working Hours per Sprint | Total official vacation | Total personal Days Off | Remaining Capacity | Total orignal estimation | Total working hours | Actual productivity | Productivity Index
Ahmed Talaat <atalaat@youxel.com> | Development | 70 | 0 | 1 | 63 | 26 | 63 | 1 | 2.4231
Alaa Ezzat <aezzat@youxel.com> | Frontend | 70 | 0 | 1 | 63 | 56.5 | 90 | 1.4286 | 1.5929
Enas Diab <ediab@youxel.com> | Frontend | 40 | 0 | 1 | 36 | 12 | 14 | 0.38889 | 1.1667
Galal Torkey <gtorkey@youxel.com> | Testing | 70 | 0 | 0 | 70 | 97 | 99.5 | 1.4214 | 1.0258
Hussein Abdallah <habdallah@youxel.com> | Frontend | 70 | 0 | 0 | 70 | 48 | 77 | 1.1 | 1.6042
Mahmoud Adel Ali <madeel@youxel.com> | Development | 70 | 0 | 2 | 56 | 94 | 104 | 1.8571 | 1.1064
Mahmoud Ibrahim Elfeqy <mfeqy@youxel.com> | Development | 70 | 0 | 0 | 70 | 64 | 85 | 1.2143 | 1.3281
Mohamed Mustafa Farrag <mfarrag@youxel.com> | Frontend | 70 | 0 | 0 | 70 | 64 | 111.83 | 1.5976 | 1.7473
Salma Sameh <ssameh@youxel.com> | Design | 70 | 0 | 3 | 49 | 49 | 31 | 0.63265 | 0.63265
Shimaa Mohamed Elsayed <shhadad@youxel.com> | Design | 70 | 0 | 0 | 70 | 89 | 109.92 | 1.5703 | 1.2351
Grand Total |  | 670 | 0 | 8 | 617 | 599.5 | 785.25 | 1.2727 | 1.3098

## Actual SP
Sprint Name: Check Now 26.15 | [7 empty] | Sprint Name: Check Now 26.16 | [7 empty] | Sprint Name: Check Now 26.17
EPIC | Parent | Work Item Type | Title | Story Points | State | CHECK UI Library | 6 | EPIC | Parent | Work Item Type | Title | Story Points | State | CHECK UI Library | 12 | EPIC | Parent | Work Item Type | Title | Story Points | State | CHECK UI Library | 14
Administration Module | 241399 | User Story | Lookups Bulk Create | 1 | In Development | Administration Module | 13 | CHECK UI Library | 228373 | User Story | Select Button | 3 | Done Development | Administration Module | 29 | CHECK UI Library | 260293 | User Story | Breadcrumb Component | 3 | Ready for release | Administration Module | 16
Administration Module | 241399 | User Story | Administration Gateway | 1 | In Development | Communication Module (Messages) | 63 | CHECK UI Library | 260293 | User Story | Breadcrumb Component | 3 | Ready For Review | Communication Module (Messages) | 3 | CHECK UI Library | 227974 | User Story | Lottie Component | 3 | Ready for release | Communication Module (Messages) | 72
Administration Module | 195967 | User Story | Set/Edit Company information | 3 | In Development | Workflow Library | 0 | CHECK UI Library | 227974 | User Story | Lottie Component | 3 | Ready For Review | Workflow Library | 0 | CHECK UI Library | 228363 | User Story | Input Switch Component | 5 | Ready for release | Workflow Library | 0
Administration Module | 195967 | User Story | Multitenancy | 0 | In Development |  | 82 | CHECK UI Library | 251864 | User Story | Org Chart Component | 3 | In Development |  | 44 | CHECK UI Library | 228369 | User Story | Galleria Component | 3 | Ready for release |  | 102
Administration Module | 195968 | User Story | User should be able to manage location types | 0 | In Development |  |  | CHECK UI Library | 228369 | User Story | Galleria Component | 3 | Ready For Review |  |  | CHECK UI Library | 255494 | User Story | Table component | 3 | In Development
Administration Module | 195968 | User Story | User should be able to manage location subcategory | 0 | In Development |  |  | CHECK UI Library | 255494 | User Story | Table component | 3 | In Development |  |  | CHECK UI Library | 227974 | User Story | Design System Adjustments | 5 | Active
Administration Module | 195968 | User Story | User should be able to manage Location categories | 0 | In Development |  |  | CHECK UI Library | 227974 | User Story | Design System Adjustments | 5 | Active |  |  | Communication Module (Messages) | 228964 | User Story | Create Chat App | 8 | In Development
Administration Module | 195968 | User Story | User should be able to manage location importance | 0 | In Development |  |  | CHECK UI Library | 242852 | User Story | Tree Table component | 3 | In Development |  |  | Communication Module (Messages) | 228960 | User Story | As a user I can send text message in a conversation | 5 | In Development
Administration Module | 195968 | User Story | User should be able to manage location account | 0 | In Development |  |  | Communication Module (Messages) | 228964 | User Story | End-to-End (E2E) Scenarios Testing | 0 | Released |  |  | Communication Module (Messages) | 228960 | User Story | As a user I can see list of my conversations | 3 | In Development
Administration Module | 195968 | User Story | User should be able to view location tree (org chart) | 0 | In Development |  |  | Communication Module (Messages) | 228964 | User Story | Create Chat App | 8 | In Development |  |  | Communication Module (Messages) | 228960 | User Story | As a user I can start new conversation | 3 | Ready For Testing
Administration Module | 195968 | User Story | User should be able to view Locations List | 0 | In Development |  |  | Communication Module (Messages) | 228960 | User Story | As a user I can send text message in a conversation | 5 | In Development |  |  | Communication Module (Messages) | 228960 | User Story | As a user I can reply on any message | 5 | Ready For Review
Administration Module | 195968 | User Story | User should be able to add location optional information | 0 | In Development |  |  | Communication Module (Messages) | 228960 | User Story | As a user I can see list of my conversations | 3 | In Bug Fixing |  |  | Communication Module (Messages) | 228960 | User Story | As a user I can delete my messages | 3 | Done Development
Administration Module | 195968 | User Story | User should be able to view location details screen | 0 | In Development |  |  | Communication Module (Messages) | 228960 | User Story | As a user I can reply on any message | 5 | In Development |  |  | Communication Module (Messages) | 228960 | User Story | As a user I can mark message as unread | 5 | Ready For Testing
Administration Module | 195968 | User Story | User should be able to search for location by (name/shortcode) | 3 | New |  |  | Communication Module (Messages) | 228960 | User Story | As a user I can react on any message | 3 | In Development |  |  | Communication Module (Messages) | 228960 | User Story | As a user I can send attachment in a conversation | 5 | In Development
Administration Module | 195968 | User Story | User should be able to delete parent location | 0 | In Development |  |  | Communication Module (Messages) | 228960 | User Story | As a user I can mark message as unread | 5 | In Development |  |  | Communication Module (Messages) | 228960 | User Story | As a user I can forward a message | 5 | In Development
Administration Module | 195968 | User Story | User should be able to move location from one parent to another | 0 | In Development |  |  | Communication Module (Messages) | 228960 | User Story | As a user I can edit my messages | 3 | In Development |  |  | Communication Module (Messages) | 228960 | User Story | As a user I can search in the conversation for certain message (Full screen) | 5 | Ready For Testing
Administration Module | 195968 | User Story | User should be able to handle location translation | 5 | In Development |  |  | Communication Module (Messages) | 228960 | User Story | As a user I can send attachment in a conversation | 5 | In Development |  |  | Communication Module (Messages) | 228961 | User Story | As a owner of a group I can change the group name | 3 | Ready For Testing
CHECK UI Library | 228373 | User Story | Select Button | 0 | Ready For Review |  |  | Communication Module (Messages) | 228960 | User Story | As a user I can forward a message | 5 | In Development |  |  | Communication Module (Messages) | 228960 | User Story | As a user I can record an audio and send it over conversation | 5 | Ready For Review
CHECK UI Library | 260293 | User Story | Breadcrumb Component | 0 | Ready For Review |  |  | Communication Module (Messages) | 228960 | User Story | As a user I can search in the conversation for certain message (Full screen) | 5 | In Development |  |  | Communication Module (Messages) | 228961 | User Story | As a owner of the group I can change the group image | 3 | In Development
CHECK UI Library | 242852 | User Story | Tree Table component | 0 | In Development |  |  | Communication Module (Messages) | 228960 | User Story | As a user I can see the shared files (full screen) | 3 | In Development |  |  | Communication Module (Messages) | 228961 | User Story | As owner of the group I can remove the group image | 3 | New
CHECK UI Library | 251864 | User Story | Org Chart Component | 3 | In Development |  |  | Communication Module (Messages) | 228960 | User Story | As a user I can record an audio and send it over conversation | 5 | In Development |  |  | Administration Module | 241399 | User Story | QC Review (Design & BRD) | 0 | Done Development
CHECK UI Library | 255494 | User Story | Table component | 3 | In Development |  |  | Communication Module (Messages) | 228960 | User Story | As a user I can pin a message | 5 | In Development |  |  | Administration Module | 241399 | User Story | Administration Portal API | 5 | In Development
Communication Module (Messages) | 228960 | User Story | Chat Testing | 0 | In Development |  |  | Administration Module | 247298 | User Story | View Onboarding progress indicator (progress menu) | 3 | In Development |  |  | Administration Module | 241399 | User Story | Locations Flat Relations | 3 | Done Development
Communication Module (Messages) | 228960 | User Story | As a user I can start new conversation | 3 | In Development |  |  | Administration Module | 195967 | User Story | Set/Edit Company information | 3 | In Development |  |  | Administration Module | 195967 | User Story | Set/Edit Company information | 3 | Ready For Testing
Communication Module (Messages) | 228960 | User Story | As a user I can send text message in a conversation | 5 | In Development |  |  | Administration Module | 195967 | User Story | Multitenancy | 8 | Ready For Review |  |  | Administration Module | 195967 | User Story | Multitenancy | 8 | Done Development
Communication Module (Messages) | 228960 | User Story | As a user I can interact with sent messages | 5 | In Development |  |  | Administration Module | 241399 | User Story | QC Review (Design & BRD) | 0 | Active |  |  | Administration Module | 195967 | User Story | Upload/Change Company Logo | 3 | Ready For Testing
Communication Module (Messages) | 228960 | User Story | As a user I can see list of my conversations | 3 | In Bug Fixing |  |  | Administration Module | 195968 | User Story | User should be able to view location tree (org chart) | 8 | Ready For Testing |  |  | Administration Module | 195967 | User Story | Set Company Identity | 5 | Ready For Testing
Communication Module (Messages) | 228960 | User Story | As a user I can react on any message | 3 | In Bug Fixing |  |  | Administration Module | 195968 | User Story | User should be able to view Locations List | 5 | In Development |  |  | Administration Module | 195967 | User Story | Set / Edit the supported langauges | 5 | Ready For Testing
Communication Module (Messages) | 228960 | User Story | As a user I can delete my messages | 3 | In Development |  |  | Administration Module | 195968 | User Story | User should be able to add location optional information | 5 | Ready For Review |  |  | Administration Module | 195968 | User Story | User should be able to view POI categories | 3 | Ready For Testing
Communication Module (Messages) | 228960 | User Story | As a user I can mark message as unread | 5 | In Development |  |  | Administration Module | 195968 | User Story | User should be able to view location details screen | 5 | In Development |  |  | Administration Module | 195968 | User Story | User should be able to manage location subcategory | 5 | Ready For Testing
Communication Module (Messages) | 228960 | User Story | As a user I can edit my messages | 3 | In Development |  |  | Administration Module | 195968 | User Story | User should be able to search for location by (name/shortcode) | 3 | In Development |  |  | Administration Module | 195968 | User Story | User should be able to manage Location categories | 5 | Ready For Testing
Communication Module (Messages) | 228960 | User Story | As a user I can send attachment in a conversation | 5 | In Development |  |  | Administration Module | 195968 | User Story | User should be able to delete parent location | 3 | In Development |  |  | Administration Module | 195968 | User Story | User should be able to manage location importance | 5 | Ready For Testing
Communication Module (Messages) | 228960 | User Story | As a user I can reply on any message | 5 | In Development |  |  | Administration Module | 195968 | User Story | User should be able to activate/deactivate Location | 3 | Ready For Review |  |  | Administration Module | 195968 | User Story | User should be able to manage location account | 5 | Ready For Testing
Communication Module (Messages) | 228960 | User Story | As a user I can forward a message | 5 | In Development |  |  | Administration Module | 195968 | User Story | User should be able to handle location translation | 5 | Ready For Testing |  |  | Administration Module | 195968 | User Story | User should be able to view location tree (org chart) | 8 | Ready For Testing
Communication Module (Messages) | 228960 | User Story | As a user I can search in the conversation for certain message (Full screen) | 5 | In Development |  |  | Administration Module | 195968 | User Story | User should be able to delete sub location | 3 | In Development |  |  | Administration Module | 195968 | User Story | User should be able to add location optional information | 5 | Ready For Review
Communication Module (Messages) | 228960 | User Story | As a user I can see the shared files (full screen) | 3 | In Development |  |  | Administration Module | 195969 | User Story | Manage KPI Indicators (CRUD + Localization) | 5 | In Development |  |  | Administration Module | 195968 | User Story | User should be able to add loction with its mandatory information | 5 | Ready For Testing
Communication Module (Messages) | 228960 | User Story | As a user I can record an audio and send it over conversation | 5 | In Development |  |  | Workflow Library | 193289 | User Story | Create Workflow System | 5 | Active |  |  | Administration Module | 195968 | User Story | User should be able to add location attachments | 5 | Ready For Testing
Communication Module (Messages) | 228960 | User Story | As a user I can send link in the conversation | 0 | In Development |  |  | Learning, Development, and Process Improvement | 240010 | User Story | Automation Testing Cycle | 0 | Active |  |  | Administration Module | 195968 | User Story | User should be able to edit locations | 5 | Ready For Testing
Communication Module (Messages) | 228960 | User Story | As a user I can pin a message | 5 | In Development |  |  | Learning, Development, and Process Improvement | 260486 | User Story | CMMI Reports | 0 | Released |  |  | Administration Module | 195968 | User Story | User should be able to delete parent location | 3 | In Development
[8 empty] | Meetings & Support | 247821 | User Story | Meeting logs iteration 26.16 | 0 | Released |  |  | Administration Module | 195968 | User Story | User should be able to move sub-locations from one parent to another | 5 | In Development
[16 empty] | Administration Module | 195968 | User Story | User should be able to activate/deactivate Location | 3 | Ready For Review
[16 empty] | Administration Module | 195968 | User Story | User should be able to handle location translation | 5 | Ready For Testing
[16 empty] | Administration Module | 195968 | User Story | User should be able to delete sub location | 3 | In Development
[16 empty] | Administration Module | 195969 | User Story | Manage KPI Indicators (CRUD + Localization) | 5 | In Development
[16 empty] | Administration Module | 195969 | User Story | Kpi Definistion Form | 5 | Ready For Review
[16 empty] | Administration Module | 195969 | User Story | Kpi Definisions View | 5 | Ready For Testing
[16 empty] | Workflow Library | 193289 | User Story | Create Workflow System | 5 | In Development
[16 empty] | Learning, Development, and Process Improvement | 240010 | User Story | Automation Testing Cycle | 0 | Active
[16 empty] | Learning, Development, and Process Improvement | 260486 | User Story | CMMI Reports | 0 | Released
[16 empty] | Meetings & Support | 247821 | User Story | Meeting logs iteration 26.17 | 0 | Released